## NPA Status
NPAs | Most recent PED | Most Recent NRUF | Relief Date | Latest CRTC Decision | Notes | Relief Planning Milestones
204/431/584 Manitoba | 2032-10-01 | January 2023 NRUF |  |  | Not in Relief Planning
226/382/519/548 Southwestern Ontario | 2024-05-01 | January 2023 NRUF |  |  | Not in Relief Planning
236/250/604/672/778 (257) British Columbia | 2025-11-01 | July 2023 NRUF | CRTC-Approved Date 24-May-2025 | TD 2023-135 | CRTC issued NOC CRTC 2021-244 on 2021-07-30. The CNA issued PROC and proposed relief schedule on 2022-09-15. CRTC released Telecom Decision CRTC 2023-135 approving the PD/RIP. | Enter RP Window: 2021-02 Initial R-NRUF: 2021-08-19 CRTC issues NOC: CRTC-2021-244 on 2021-07-30 CNA issues PROC: 2022-09-15 PD/RIP sent to CISC: 2022-11-04 PD/RIP approved by CISC: 2023-01-19 CRTC Decision: CRTC 2023-135 on 2023-05-10 for Relief Date of 2025-05-24 New NPA: 257 Relief Date: 2025-05-24 Relief Completed: n/a
249/683/705 North/Central Ontario | 2029-06-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
263/438/514 Metro Montréal | 2033-09-01 | January 2023 NRUF |  |  | Not in Relief Planning
289/365/742/905 Southern Ontario | 2028-07-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
306/474/639 Saskatchewan | 2032-09-01 | January 2023 NRUF |  |  | Not in Relief Planning
343/613/753 Eastern Ontario | 2029-03-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
354/450/579 Suburban Montréal Area | 2037-02-01 | January 2023 NRUF |  |  | Not in Relief Planning
367/418/581 Eastern Québec | 2027-06-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
368/403/587/780/825 Alberta | 2028-04-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
416/437/647 (942) Toronto | 2025-12-01 | July 2023 NRUF | CRTC-Approved Date 26-Apr-2025 | TD 2023-135 | The CNA issued PROC and proposed relief schedule on 2022-09-15. CRTC released Telecom Decision CRTC 2023-135 approving the PD/RIP. | Enter RP Window: 2019-03 Initial R-NRUF: 2019-09 CRTC issues NOC: CRTC 2020-35 on 2020-01-30 CNA issues PROC: 2022-09-15 PD/RIP Sent to CISC: 2022-11-04 PD/RIP Approved by CISC: 2023-01-19 CRTC Decision: CRTC 2023-135 on 2023-05-10 for Relief Date of 2025-04-26 New NPA: 942 Relief Date: 2025-04-26 Relief Completed: n/a
428/506 New Brunswick | 2024-07-01 | January 2023 NRUF |  |  | Not in Relief Planning
468/819/873 Northern and Western Québec | 2032-06-01 | January 2023 NRUF |  |  | Not in Relief Planning
709 (879) Newfoundland and Labrador | 2024-10-01 | July 2023 NRUF | CRTC-Approved Date 2024-02-17 Deferred Indefinitely (Proposed date is 24-Feb-2024) | TD 2023-319 | *7- to 10-digit local dialling may be required. See CRTC NoC 2021-191 In accordance with Telecom Regulatory Policy CRTC 2022-234 10-digit dialling was implemented on 31 May 2023. | Enter RP Window: 2016-03 Initial R-NRUF: 2016-05 CNA Declres Jeopardy condition: 2016-03-11 CRTC issues NOC: CRTC 2016-205 on 2016-15-31 CNA issues IPD: 2016-08-05 PD/RIP sent to CISC: 2016-10 CRTC Decision: CRTC 2017-35 on 2017-02-02 with Relief Date of 2018-11-24 CNA Declares end of Jeopardy condition: 2017-09-05 Dispute Information Form submitted: 2017-11-29 regarding defering Relief Date CRTC Decision: CRTC 2018-59 on 2018-02-14 Dispute Resolution regarding relief deferral Revised RIP sent to Secretary General of CRTC: 2018-05-17 with Relief Date of 2022-05-20 CRTC Decision: CRTC 2018-333 on 2018-07-30 with Relief Date of 2022-05-20 Revised RIP sent to CISC: 2020-07-27 to delay Relief Date to 2023-05-27 TIF Report #4 sent to CISC: 2020-07-27 to defer Relief Date indefinitely CRTC Decision: CRTC 2021-13 on 2021-01-18 for indefinite deferral of Relief Date TIF Report #5 sent to CISC: 2023-05-19 with Relief Date 2024-02-17 CRTC Decision: CRTC 2023-319 on 2023-09-15 with Relief Date of 2024-02-17 New NPA: 879 Relief Date: 2024-02-17 Deferred Indefinitely (Proposed date is 2024-02-17) Relief Completed: n/a
782/902 Nova Scotia and PEI | 2028-02-01 | July 2023 NRUF |  |  | Not in Relief Planning / In R-NRUF window
807 Northwestern Ontario | 2040-08-01 | January 2023 NRUF |  |  | Not in Relief Planning *7- to 10-digit local dialling may be required. See CRTC NoC 2021-191. In accordance with Telecom Regulatory Policy CRTC 2022-234 10-digit dialling was implemented on 31 May 2023.
867 NWT, Nunavut and Yukon | 2072-10-01 | January 2023 NRUF |  |  | Not in Relief Planning *7- to 10-digit local dialling may be required. See CRTC NoC 2021-191. In accordance with Telecom Regulatory Policy CRTC 2022-234 10-digit dialling was implemented in the Yellowknife LIR on 31 May 2023.

## Chronological PEDs
NPA Exhausts forecast for the next 20 years |  | Updated as of 2023-09-26
NPA Complex | Projected Exhuast Date | Source
709/879 | 2024-10-01 | July 2023 NRUF
236/250/604/672/778 | 2025-11-01 | July 2023 NRUF
416/437/647 | 2025-12-01 | July 2023 NRUF
367/418/581 | 2027-06-01 | July 2023 NRUF
782/902 | 2028-02-01 | July 2023 NRUF
368/403/587/780/825 | 2028-04-01 | July 2023 NRUF
289/365/742/905 | 2028-07-01 | July 2023 NRUF
343/613/753 | 2029-03-01 | July 2023 NRUF
249/683/705 | 2029-06-01 | July 2023 NRUF
226/382/519/548 | 2030-06-01 | January 2023 NRUF
236/250/604/672/778 | 2031-04-01 | July 2023 NRUF
468/819/873 | 2032-06-01 | January 2023 NRUF
306/474/639 | 2032-09-01 | January 2023 NRUF
204/431/584 | 2032-10-01 | January 2023 NRUF
416/437/647 | 2033-07-01 | July 2023 NRUF
263/438/514 | 2033-09-01 | January 2023 NRUF
367/418/581 | 2035-07-01 | July 2023 NRUF
289/365/742/905 | 2036-05-01 | July 2023 NRUF
354/450/579 | 2037-02-01 | January 2023 NRUF
368/403/587/780/825 | 2037-03-01 | July 2023 NRUF
226/382/519/548 | 2037-07-01 | January 2023 NRUF
343/613/753 | 2039-01-01 | July 2023 NRUF
236/250/604/672/778 | 2039-02-01 | July 2023 NRUF
807 | 2040-08-01 | January 2023 NRUF
782/902 | 2040-10-01 | July 2023 NRUF
249/683/705 | 2041-04-01 | July 2023 NRUF
416/437/647 | 2041-10-01 | July 2023 NRUF
468/819/873 | 2043-02-01 | January 2023 NRUF
289/365/742/905 | 2044-02-01 | July 2023 NRUF
367/418/581 | 2044-05-01 | July 2023 NRUF
306/474/639 | 2044-06-01 | January 2023 NRUF
428/506 | 2044-08-01 | January 2023 NRUF
226/382/519/548 | 2044-09-01 | January 2023 NRUF

## Completed Relief
NPAs | Most recent PED | Most Recent NRUF | Relief Date | Latest CRTC Decision | Notes | Relief Planning Milestones
226/519/548 (382) Southwestern Ontario | 2024-05-01 | January 2023 NRUF | CRTC-Approved Date 17 -Jun-2023 | TD 2022-50 | CRTC issued NOC CRTC 2021-245 on 2021-07-30. The CNA issued PROC and proposed relief schedule on 2021-09-17. The Initial RPC meeting was held on 2021-10-14. TIF Report #1, PD and RIP were finalized on 2021-10-28 and sent to the CISC for consideration. CRTC released Telecom Decision CRTC 2022-50 approving the PD/RIP. | Enter RP Window: 2021-02 Initial R-NRUF: 2021-08-19 CRTC issues NOC: CRTC 2021-245 on 2021-07-30 CNA issues PROC: 2021-09-17 PD/RIP Sent to CISC: 2021-10-28 PD/RIP approved by CISC: 2021-12-20 CRTC Decision: CRTC 2022-50 on 2022-02-24 for Relief Date of 2023-06-17 New NPA: 382 Relief Date: 2023-06-17 Relief Completed: Yes
289/365/905 (742) Southern Ontario | 2029-05-01 | January 2022 NRUF | CRTC-Approved Date 16-Oct-2021 | TD 2021-184 | The RPC reviewed NITF and CATF Progress Report #1 on 2021-07-02. The RPC reviewed NITF and CATF Progress Report #2 on 2021-08-23. | Enter RP Window: 2017-03 CRTC issues NOC: CRTC 2018-235 on 2018-07-11 Initial R-NRUF: 2017-09 CNA issues Initial Planning Document (IPD): 2018-11-02 PD/RIP sent to CISC: 2020-06 CRTC Decision: CRTC 2020-362 on 2020-10-28 for Relief Date of 2021-10-16 PD/RIP sent to CISC: 2020-12-03 to revise Relief Date to 2022-05-14 CRTC Decision: CRTC 2021-184 on 2021-05-28 to deny delayed Relief Date CNA Declares Jeopardy Condition: 2021-06-04 CNA Suspends Jeopardy Condition: 2021-06-09 New NPA: 742 Relief Date: 2021-10-16 Relief Completed: Yes
306/639 (474) Saskatchewan | 2038-01-01 | January 2022 NRUF | CRTC-Approved Date 2-Oct-2021 | TD 2019-129 | The RPC reviewed NITF and CATF Progress Report #2 on 2021-08-09. The RPC reviewed the final NITF and CATF Progress Reports (#3) on 2021-11-16. | Enter RP Window: 2018-03 Initial R-NRUF: 2018-05 CRTC issues NOC: CRTC 2018-236 on 2018-07-11 CNA issues IPD: 2018-10-12 PD/RIP sent to CISC: 2018-12 CRTC Decision: CRTC 2019-129 on 2019-05-03 for Relief Date of 2021-10-02 CNA Declares Jeopardy Condition: 2020-03-26 CNA Suspends Jeopardy Condition: 2020-10-19 CRTC Staff Letter: 2020-11-25 Limiting assignments to forecasts New NPA: 474 Relief Date: 2021-10-02 Relief Completed: Yes
343/613 (753) Eastern Ontario | 2023-06-01 | January 2022 NRUF | CRTC-Approved Date 26-Mar-2022 | TD 2021-372 | CRTC released Telecom Decision CRTC 2021-372 approving the PD/RIP. As the CRTC decision was released much later than expected, impacting the RP schedule, the RPC met on 2021-11-17 to revise the schedule based on the delay. The CNA suspended the Jeopardy Condition on 2021-11-22 based on the October J-NRUF results. However, with CRTC staff concurrence, the Code Restrictions will remain in effect to help prevent a Jeopardy Condition until the introduction of the new relief area code. | Enter RP Window: 2018-03 Initial R-NRUF: 2018-08 CRTC issues NOC: CRTC 2018-409 on 2018-10-31 CNA issues IPD: 2018-11-02 CNA issues PROC: 2020-09-30 (based on PED delaying then advancing again) CNA Declares Jeopardy Condition: 2021-02-23 PD/RIP sent to CISC: 2021-03-12 PD/RIP approved by CISC: 2021-05-17 CRTC Decision: CRTC 2021-372 on 2021-11-10 CNA Suspends Jeopardy Contition: 2021-11-22 New NPA: 753 Relief Date: 2022-03-26 Relief Completed: Yes
368/403/587/780/825 Alberta | 2022-08-01 | January 2022 NRUF | CRTC-Approved Date 23-Apr-2022 | TD 2021-101 | The CNA declares a Jeopardy Condition on 2021-08-19 based on the July 2021 R-NRUF results. Relief implemented on 2022-04-23. | Enter RP Window: 2017-03 Initial R-NRUF: 2017-09 CRTC issues NOC: CRTC 2018-234 on 2018-07-11 CNA issues IPD: 2018-07-20 PD/RIP sent to CISC: 2018-12 CRTC Decision: CRTC 2019-05 dated 2019-05-03 with Relief Date of 2021-05-15 Revised RIP sent to CISC: 2019-08-30 (to shorten customer communication timeline) CRTC Decision: CRTC 2020-110 dated 2020-03-27 (with shortened schedule) Revised RIP sent to CISC: 2020-11 (recommending delayed Relief Date of 2022-04-23 CRTC Decision: CRTC 2021-101 dated 2021-03-05 with Delayed Relief Date of 2022-04-23 CNA Declares Jeopardy Condition: 2021-06-04 CNA Suspends Jeopardy Condition: 2021-06-09 CNA Declares Jeopardy Condition: 2021-08-19 New NPA: 368 Relief Date: 2022-04-23 Relief Completed: Yes
204/431 (584) Manitoba | 2023-06-01 | April 2022 S-NRUF | CRTC-Approved Date 29-Oct-2022 | TD 2022-51 | The CNA issued PROC and proposed relief schedule on 2021-08-26. The CNA declares a Jeopardy Condition on 2021-08-19 based on the July 2021 R-NRUF results. The Initial RPC meeting was held on 2021-09-06. TIF Report #1, PD and RIP were finalized on 2021-09-30 and sent to the CISC for consideration. The CNA suspended the Jeopardy Condition on 2021-11-22 based on the October 2021 J-NRUF results. However, with CRTC staff concurrence, the Code Restrictions will remain in effect to help prevent a Jeopardy Condition until the introduction of the new relief area code. CRTC released Telecom Decision CRTC 2022-51 approving the PD/RIP. | Enter RP (Relief Planning) Window: 2020-03 Initial R-NRUF: 2020-08-18 CRTC issues Notice of Consultation (NOC): CRTC 2021-6 on 2021-01-11 CNA issues Proposal for Relief of an Overlay [NPA] Complex (PROC): 2021-08-06 CNA Declares Jeopardy: 2021-08-19 Planning Document (PD)/Relief Implementation Plan (RIP) sent to CISC: 2021-09-30 CNA Suspends Jeopardy: 2021-11-22 PD/RIP approved by CISC: 2021-12-20 CRTC Decision: CRTC 2022-51 on 2022-02-24 for Relief Date of 2022-10-29 New NPA: 584 Relief Date: 2022-10-29 Relief Completed: Yes
249/705 (683) North/Central Ontario | 2023-10-01 | January 2022 NRUF | CRTC-Approved Date 18-Jun-2022 | TD 2021-371 | TIF Report #1 (RIP/PD) sent to CISC on 2021-04-08. CRTC released Telecom Decision CRTC 2021-371 approving the PD/RIP. The CNA suspended the Jeopardy Condition on 2021-11-16 based on the release of the Telecom Decision. As the CRTC decision was released much later than expected, impacting the RP schedule, the RPC met on 2021-11-17 to revise the schedule based on the delay. | Enter RP Window: 2019-03 Initial R-NRUF: 2019-09 CRTC issues NOC: CRTC 2020-36 on 2020-01-30 CNA declares Jeopardy: 2021-02-26 CNA issues PROC: 2021-03-03 PD/RIP sent to CISC: 2021-04-08 PD/RIP approved by CISC: 2021-05-17 CRTC Decision: CRTC 2021-371 on 2021-11-10 CNA Suspends Jeopardy Condition: 2021-11-16 New NPA: 683 Relief Date: 2022-06-18 Relief Completed: Yes
438/514 (263) Metro Montréal | 2024-03-01 | January 2022 NRUF | CRTC-Approved Date 22-Oct-2022 | TD 2021-364 | TIF Report #1 (PD/RIP) sent to CISC on 2021-08-04. CRTC released Telecom Decision CRTC 2021-364 approving the PD/RIP. | Enter RP Window: 2019-03 Initial R-NRUF: 2019-09 CRTC issues NOC: CRTC 2020-37 on 2020-01-30 CNA Declares Jeopardy Condition: 2021-06-04 CNA Suspends Jeopardy Condition: 2021-06-09 CNA issues PROC: 2021-06-17 PD/RIP Sent to CISC: 2021-08-04 PD/RIP Approved by CISC: 2021-09-13 CRTC Decision: CRTC 2021-364 on 2021-11-01 New NPA: 263 Relief Date: 2022-10-22 Relief Completed: Yes
450/579 (354) Suburban Montréal Area | 2024-08-01 | January 2022 NRUF | CRTC-Approved Date 22-Oct-2022 | TD 2021-373 | TIF Report (Revised RIP with relief date of 2022-10-22) sent to CISC on 2021-04-26. CRTC released Telecom Decision CRTC 2021-373 approving the RIP. | Enter RP Window: 2017-03 Initial R-NRUF: 2017-09 CNA issue IPD: 2018-06-15 CRTC issues NOC: CRTC 2018-233 on 2018-07-11 PD/RIP Sent to CISC: 2018-09 CRTC Decision: CRTC 2019-13 on 2019-01-18 with Relief Date of 2020-10-24 TIF Report sent to CISC: 2019-05-09 requesting indefinite deferral of Relief Date CRTC Decision: CRTC 2019-347 on 2019-10-08 Deferring Relief Date indefinetly TIF Report sent to CISC: 2021-04-26 Revised RIP with Relief Date of 2022-10-22 RIP Approved by CISC: 2021-05-17 CRTC Decision: CRTC 2021-373 on 2021-11-12 New NPA: 354 Relief Date: 2022-10-22 Relief Completed: Yes
819/873 (468) Northern and Western Québec | 2023-06-01 | April 2022 S-NRUF | CRTC-Approved Date 22-Oct-2022 | TD 2020-393 | The CNA declares a Jeopardy Condition on 2021-08-19 based on the July 2021 R-NRUF results. CRTC released Telecom Decision CRTC 2021-393 approving the PD/RIP with a Relief Date of 2022-10-22. The CNA suspended the Jeopardy Condition on 2021-12-02 based on the release of the decicion. However, with CRTC staff concurrence, the Code Restrictions will remain in effect to help prevent a Jeopardy Condition until the introduction of the new relief area code. | Enter RP Window: 2019-03 Initial R-NRUF: 2019-09 CRTC issues NOC: CRTC 2020-34 on 2020-01-30 CNA issue PROC: 2020-09-21 PD/RIP sent to CISC: 2021-06-04 PD/RIP approved by CISC: 2021-06-04 CNA Declares Jeopardy Condition: 2021-08-19 CRTC Decision: CRTC 2021-393 on 2021-12-02 with Relief Date of 2021-10-22 CNA Suspends Jeopardy Condition: 2021-12-02 New NPA: 468 Relief Date: 2022-10-22 Relief Completed: Yes
506 (428) New Brunswick | 2024-07-01 | January 2023 NRUF | CRTC-Approved Date 29-Apr-2023 | TD 2020-363 | The RPC reviewed Progress Report #2 on 2021-11-29. *7- to 10-digit local dialling date may advance. See CRTC NoC 2021-191. | Enter RP Window: 2016-03 Initial R-NRUF: 2016-10 CRTC issues NOC: CRTC 2016-206 on 2016-05-31 CNA issues IPD: 2017-06-30 PD/RIP sent to CISC: 2018-05 CRTC Decision: CRTC 2018-332 on 2018-08-30 with Relief Date of 2020-11-21 Revised RIP sent to CISC: 2019-11-26 delaying Relief Date to 2022-04-23 CRTC Decision: CRTC 2020-135 on 2020-04-24 Delaying Relief Date to 2022-04-23 Revised RIP sent to CISC: 2020-06-25 delaying Relief Date to 2023-04-29 CRTC Decision: CRTC 2020-363 on 2020-10-28 Delaying Relief Date to 2023-04-29 New NPA: 428 Relief Date: 2023-04-29 Relief Completed: Yes

## NRUFs
This tab is serving as a bookmark.
The tabs to the right of this include the NRUF results for each NPA complex starting from when that NPA complex entered the relief planning window. If the tab is blank, it is because that NPA Complex is not in the relief window.

## 204-431-584
NPA 204/431/584 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 226-382-519-548
NPA 226/382/519/548 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 236-250-604-672-778
NPA 236/250/604/672/778 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
236/250/604/672/778 | January 2021 G-NRUF | 2021-02-23 | 2027-02-01
236/250/604/672/778 | July 2021 R-NRUF | 2021-08-19 | 2027-03-01
236/250/604/672/778 | January 2022 R-NRUF | 2022-03-01 | 2027-03-01
236/250/604/672/778 | July 2022 R-NRUF | 2022-08-19 | 2026-07-01
236/250/604/672/778 | January 2023 R-NRUF | 2023-03-29 | 2024-05-01
236/250/604/672/778 | July 2023 R-NRUF | 2023-08-18 | 2025-11-01

## 249-683-705
NPA 249/683/705 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
249/683/705 | January 2023 G-NRUF | 2023-03-29 | 2029-01-01
249/683/705 | July 2023 R-NRUF | 2023-08-18 | 2029-06-01

## 263-438-514
NPA 263/438/514 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 289-365-742-905
NPA 289/365/742/905 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
289/365/742/905 | January 2023 G-NRUF | 2023-03-29 | 2028-10-01
289/365/742/905 | July 2023 R-NRUF | 2023-08-18 | 2025-12-01

## 306-474-639
NPA 306/474/639 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 343-613-753
NPA 343/613/753 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
343/613/753 | January 2023 G-NRUF | 2023-03-29 | 2029-04-01
343/613/753 | July 2023 R-NRUF | 2023-08-18 | 2029-03-01

## 354-450-579
NPA 354/450/579 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 367-418-581
NPA 367/418/581 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
367/418/581 | January 2023 G-NRUF | 2023-03-29 | 2027-06-01
367/418/581 | July 2023 R-NRUF | 2023-08-18 | 2027-06-01

## 368-403-587-780-825
NPA 368/403/587/780/825 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
368/403/587/780/825 | January 2023 G-NRUF | 2023-03-29 | 2028-06-01
368/403/587/780/825 | July 2023 R-NRUF | 2023-08-18 | 2028-04-01

## 416-437-647
NPA 416/437/647 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
416/437/647 | January 2019 G-NRUF | 2019-03-26 | 2024-01-01
416/437/647 | July 2019 R-NRUF | 2019-09-20 | 2025-06-01
416/437/647 | January 2020 G-NRUF | 2020-03-24 | 2025-01-01
416/437/647 | July 2020 R-NRUF | 2020-08-18 | 2025-11-01
416/437/647 | January 2021 R-NRUF | 2021-02-23 | 2026-07-01
416/437/647 | July 2021 R-NRUF | 2021-08-19 | 2025-09-01
416/437/647 | January 2022 R-NRUF | 2022-03-01 | 2026-03-01
416/437/647 | July 2022 R-NRUF | 2022-08-19 | 2026-11-01
416/437/647 | January 2023 R-NRUF | 2023-03-29 | 2025-11-01
416/437/647 | July 2023 R-NRUF | 2023-08-18 | 2025-12-01

## 428-506
NPA 428/506 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 468-819-873
NPA 468/819/873 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 709-879
NPA 709/879 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
709/879 | January 2015 G-NRUF | 2015-03-27 | 2024-08-01
709/879 | January 2016 G-NRUF | 2016-03-21 | 2019-05-01
709/879 | April 2016 J-NRUF | 2016-05-15 | 2019-03-01
709/879 | July 2016 J-NRUF | 2016-09-02 | 2019-03-01
709/879 | October 2016 J-NRUF | 2016-12-05 | 2019-03-01
709/879 | January 2017 J-NRUF | 2017-03-29 | 2019-08-01
709/879 | April 2017 J-NRUF | 2017-06-02 | 2019-08-01
709/879 | July 2017 J-NRUF | 2017-09-05 | 2023-05-01
709/879 | January 2018 R-NRUF | 2018-03-20 | 2023-04-01
709/879 | July 2018 R-NRUF | 2018-09-05 | 2023-03-01
709/879 | January 2019 R-NRUF | 2019-03-26 | 2023-08-01
709/879 | July 2019 R-NRUF | 2019-09-20 | 2023-10-01
709/879 | January 2020 G-NRUF | 2020-03-24 | 2023-03-01
709/879 | July 2020 R-NRUF | 2020-08-18 | 2028-06-01
709/879 | January 2021 R-NRUF | 2021-02-23 | 2026-09-01
709/879 | July 2021 R-NRUF | 2021-08-19 | 2026-12-01
709/879 | January 2022 R-NRUF | 2022-03-01 | 2028-11-01
709/879 | January 2023 G-NRUF | 2023-03-29 | 2024-12-01
709/879 | April 2023 J-NRUF | 2023-05-04 | 2025-03-01
709/879 | July 2023 S-NRUF | 2023-08-18 | 2024-10-01

## 782-902
NPA 782/902 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date
782/902 | January 2023 G-NRUF | 2023-03-29 | 2028-02-01
782/902 | July 2023 R-NRUF | 2023-08-18 | 2028-02-01

## 807
NPA 807 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date

## 867
NPA 867 Summary of Projected Exhaust Dates
NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date