NPA 418/581 RELIEF

(Implementation of New Overlay NPA 367)

NETWORK IMPLEMENTATION TASK FORCE (NITF)

FINAL PROGRESS REPORT TO THE RELIEF PLANNING COMMITTEE (RPC)

18 December 2018

INTRODUCTION

This FINAL NITF Progress Report is submitted to the Relief Planning Committee (RPC) and CRTC staff for NPA 418/581 as required under Telecom Decision CRTC 2017-32.

The objective of the Network Implementation Plan (NIP) is to implement all necessary network modifications for the introduction of new NPA Code 367 in the NPA 418/581 area.

The NPA Relief Implementation Plan (RIP) requires periodic progress reports by each Telecommunications Service Provider (TSP) operating in the NPA and by the Network Implementation Task Forces (NITF) established for each NPA relief project.

The Relief Implementation Plan Schedule indicates that the Final Progress Reports are required as follows:

| 46 | TSPs submit Final Report to CATF and NITF (starts on the Relief Date and provides 2 weeks for preparation & submission) | TSPs | 24-Nov-18 | 7-Dec-18 |
| --- | --- | --- | --- | --- |
| 47 | NITF and CATF develop & submit Final Progress Report to the RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 7-Dec-18 | 14-Dec-18 |
| 48 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 14-Dec-18 | # 7-Jan-19 |

Carrier Progress Reports:

Attached to this NITF Progress Report are the individual Progress Reports submitted by the following Carriers (CO Code Holders):

- 9144-3036 Quebec Inc (Navigue.com)

- Allstream

- Bell Canada (including Bell Mobility and Telebec)

- Comwave

- Distributel Communications Ltd

- Fibernetics

- Iristel

- Navigata Communications Ltd

- TELUS (TELUS Mobility and TELUS Communications (Quebec))

The known TSPs that did not submit a progress report to the NITF are:

- 9163-7918 Quebec Inc (CoopTel)

- ISP Telecom

- IVIC Telecom

- La Cie de Telephone de Courcelles Inc.

- Maskatel Group (Maskatel – Xittel – Téléphone St-Victor – Téléphone St-Éphrem – Téléphone Upton)

- Rogers Communications

- Sogetel Inc.

- Videotron

NETWORK IMPLEMENTATION PLAN PROGRESS

The NITF has followed the schedule in the RIP for this NPA (see Attachment 1).  All network implementation activities have been implemented in accordance with the schedule contained in the Relief Implementation Plan (RIP).

The NITF reports that no major problems were identified by TSPs during the implementation of relief of NPA 418/587.

However, the NITF advises that there are several known TSPs that did not submit a progress report to the NITF.  It is expected that those TSPs will submit their reports directly to the CRTC.

Submitted by:

Laurie Bowie

Chair NITF

RELIEF IMPLEMENTATION SCHEDULE

For a Distributed Overlay of new NPA 367 over NPA 418/581

| Item | Task or Event | PRIME | START | END |
| --- | --- | --- | --- | --- |
| 1 | CNA identifies NPA exhaust and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within 72 months | CNA |  | 11-Mar-16 |
| 2 | CNA conducts S-NRUF & releases results | CNA | 14-Mar-16 | 16-May-16 |
| 3 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee (RPC) and declares a Jeopardy Condition | CRTC |  | 31-May-16 |
| 4 | CNA announces the date for the initial NPA Relief Planning face-to-face meeting & requests contributions | CNA | 09-Sep-16 | 18-Oct-16 |
| 5 | CNA develops and distributes the Initial Planning Document (IPD) to the RPC | CNA | 31-May-16 | 09-Sep-16 |
| 6 | RPC participants review the IPD & submit contributions to the RPC | RPC | 09-Sep-16 | 18-Oct-16 |
| 7 | CNA chairs initial RPC meeting to start development of the Planning Document (PD) & Relief Implementation Plan (RIP) & schedules future meetings/conference calls | CNA, RPC | 26-Oct-16 | 28-Oct-16 |
| 8 | CNA chairs subsequent RPC meetings/conference calls to finalize the PD and RIP | CNA, RPC | 28-Oct-16 | 25-Nov-16 |
| 9 | The RPC creates Consumer Awareness (CATF) and Network implementation (NITF) Task Forces | RPC | 28-Oct-16 | 25-Nov-16 |
| 10 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 25-Nov-16 | 9-Dec-16 |
| 11 | Special Types of Telecommunications Service Users (9-1-1 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to the RPC & CRTC | Special Users | 31-May-16 | 25-Nov-16 |
| 12 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & RIP | CRTC | 9-Dec-16 | 9-Mar-17 |
| 13 | CNA obtains relief NPA from NANPA | CNA | 9-Mar-17 | 23-Mar-17 |
| 14 | RPC develops the Planning Letter (PL) |  | 23-Mar-17 | 6-Apr-17 |
| 15 | Task Forces, Telecommunications Service Providers (TSPs) and users implement relief (starts at CRTC approval of Relief Option & Date and ends on Relief Date) | TSPs | 9-Mar-17 | 24-Nov-18 |
| 16 | All TSPs to develop and file individual consumer awareness programs with the CRTC (may be done collectively by a Telecommunications Alliance) (starts at CRTC approval of RIP and should be completed about 24 months prior to the Relief Date) | TSPs | 9-Mar-17 | 30-Mar-17 |
| 17 | CNA issues media release (in coordination with the Telecommunications Alliance) (may start on CRTC approval of the RIP and should be issued at least 18 months prior to the Relief Date) | CNA | 23-Mar-17 | 24-May-17 |
| 18 | CNA submits the PL to NANPA (should be submitted at least 18 months prior to the Relief Date) | CNA | 6-Apr-17 | 20-Apr-17 |
| 19 | NANPA receives and posts the PL to the NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 20-Apr-17 | 4-May-17 |
| 20 | All TSPs implement consumer awareness activities (starts on filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 30-Mar-17 | 24-Nov-18 |
| 21 | All TSPs to notify all customers (residence, business & special customers) of the new overlay NPA (may start with the filing of Consumer Awareness Programs with the CRTC and all customers should be notified at least 18 months prior to the Relief Date) | TSPs | 30-Mar-17 | 24-May-17 |
| 22 | TSPs to submit Progress Report #1 to NITF and Consumer Awareness Task Force (CATF) (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 24-May-17 | 7-Jun-17 |
| 23 | NITF and CATF develop & submit Progress Report #1 to the RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 7-Jun-17 | 21-Jun-17 |
| 24 | RPC submits Progress Report #1 to CRTC staff (linked to NITF and CATF reports) | RPC | 21-Jun-17 | 5-Jul-17 |
| 25 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts on the date that the PL is posted to the NANPA web site and must be completed by 6 months prior to the Relief Date) | Telcordia TRA | 7-Jun-17 | 24-May-18 |
| 26 | All TSPs and Telecommunications Service Users (including Special Users 9-1-1 PSAPs, alarm companies, ISPs, paging companies, payphone providers, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts on CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 9-Mar-17 | 24-Nov-18 |
| 27 | Payphone Providers Reprogram Payphones (starts on CRTC approval of the RIP and ends on the Relief Date) | Payphone Providers | 9-Mar-17 | 24-Nov-18 |
| 28 | TSPs and database owners/operators to modify systems and industry databases (starts on CRTC approval of the RIP and ends on the Relief Date) | TSPs & Database Owners | 9-Mar-17 | 24-Nov-18 |
| 29 | Operator Services & Directory Assistance Readiness (starts on CRTC approval of the RIP and ends on the Relief Date) | TSPs | 9-Mar-17 | 24-Nov-18 |
| 30 | Directory Publisher Readiness for relief (ability to identify the NPA in telephone numbers in the directory published after the new NPA is activated) (starts on CRTC approval of the RIP and ends on the Relief Date) | Directory Publishers | 9-Mar-17 | 24-Nov-18 |
| 31 | 9-1-1 Systems and Databases Readiness (starts on CRTC approval of the RIP and ends on the Relief Date) | PSAPS, 9-1-1 Service Providers & TSPs | 9-Mar-17 | 24-Nov-18 |
| 32 | Network Systems & Equipment Readiness (starts on CRTC approval of the RIP and ends on the Relief Date) | TSPs | 9-Mar-17 | 24-Nov-18 |
| 33 | Service Order & Business System Readiness (starts on CRTC approval of the RIP and ends on the Relief Date) | TSPs | 9-Mar-17 | 24-Nov-18 |
| 34 | International Gateway Switch Translations Readiness for new NPA (starts on CRTC approval of the RIP and ends on the Relief Date) | Int’l TSPs | 9-Mar-17 | 24-Nov-18 |
| 35 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts on CRTC approval of the RIP and ends on the Relief Date) | CLNPC & NPAC | 9-Mar-17 | 24-Nov-18 |
| 36 | Toll Free SMS Database Readiness for new NPA (starts on CRTC approval of the RIP and ends on the Relief Date) | Toll TSPs | 9-Mar-17 | 24-Nov-18 |
| 37 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 of the Guideline) | TSPs | 24-Feb-18 | 19-Jun-18 |
| 38 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start on CRTC approval of the RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 9-Mar-17 | 24-Aug-18 |
| 39 | All international and domestic TSPs must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 9-Mar-17 | 24-Aug-18 |
| 40 | Activation date for new NPA Test CO Codes and Test Numbers in the network must be completed by the start date for the Inter-Carrier Testing Period | TSPs |  | 24-Aug-18 |
| 41 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) | NITF & TSPs | 24-Aug-18 | 24-Nov-18 |
| 42 | TSPs to submit Progress Report #2 to NITF and CATF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 24-Aug-18 | 7-Sep-18 |
| 43 | NITF and CATF develop & submit Progress Report #2 to the RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 7-Sep-18 | 14-Sep-18 |
| 44 | The RPC submits Progress Report #2 to CRTC staff (linked to NITF and CATF reports) | RPC | 14-Sep-18 | 21-Sep-18 |
| 45 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 24-Nov-18 |
| 46 | TSPs submit Final Report to CATF and NITF (starts on the Relief Date and provides 2 weeks for preparation & submission) | TSPs | 24-Nov-18 | 7-Dec-18 |
| 47 | NITF and CATF develop & submit Final Progress Report to the RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 7-Dec-18 | 14-Dec-18 |
| 48 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 14-Dec-18 | # 7-Jan-19 |
| 49 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2-Jan-19 | 2-Feb-19 |