NPA 819/873 Planning Document (PD)

Version 1.0 – 10 March 2021

TABLE OF CONTENTS

1.	INTRODUCTION	1

2.	NPA RELIEF PLANNING PROCESS	2

3.	NPA RELIEF METHODS	3

4.	NPA EXHAUST INFORMATION	3

5.	RELIEF OPTION	3

5.1.	Distributed Overlay	4

6.	SUMMARY OF RELIEF OPTION	4

7.	DIALLING CHANGES FOR LOCAL CALLS	4

8.	PROPOSED SCHEDULE	5

9.	JEOPARDY CONTINGENCY PLAN (JCP)	0

10.	SELECTION OF RELIEF NPA CODE	7

11.	RECOMMENDATIONS	8

ANNEXES	9

LIST OF ANNEXES

ANNEX A

Figure 1 – Overview Map of NPA 819/873	1

Figure 2 – NPA 819/873 Actual and Forecast CO Code Assignments	2

Figure 3 – NPA 819/873 CO Code Exhaust – January 2021 R-NRUF	3

Figure 4 – NPA 819/873 CO Code Exhaust – July 2020 R-NRUF	3

Figure 5 – Distributed Overlay	5

ANNEX B

Table 1 – NPA 468/819/873 Exchange Areas After Distributed Overlay 	B-1

ANNEX C

Distribution List

ACRONYM LIST

| CATF | Consumer Awareness Task Force |
| --- | --- |
| CNA | Canadian Numbering Administrator |
| CISC | CRTC Interconnection Steering Committee |
| CLEC | Competitive Local Exchange Carrier |
| CLNPC | Canadian Local Number Portability Consortium |
| CO | Central Office |
| CRTC | Canadian Radio-television and Telecommunications Commission |
| CSCN | Canadian Steering Committee on Numbering |
| EAS | Extended Area Service |
| G-NRUF | General Numbering Resource Utilization Forecast |
| ILEC | Incumbent Local Exchange Carrier |
| IPD | Initial Planning Document |
| ISP | Internet Service Provider |
| JCP | Jeopardy Contingency Plan |
| J-NRUF | Jeopardy Numbering Resource Utilization Forecast |
| LEC | Local Exchange Carrier |
| LIR | Local Interconnection Region |
| LNP | Local Number Portability |
| NANP | North American Numbering Plan |
| NANPA | North American Numbering Plan Administrator |
| NITF | Network Implementation Task Force |
| NoC | Notice of Consultation |
| NPA | Numbering Plan Area (Area Code) |
| NRUF | Numbering Resource Utilization Forecast |
| PD | Planning Document |
| PED | Projected Exhaust Date |
| PL | Planning Letter |
| POI | Point of Interconnection |
| PROC | Proposal for Relief of an Overlay NPA Complex |
| PSAP | Public Safety Answering Point |
| RIP | Relief Implementation Plan |
| R-NRUF | Relief Planning Numbering Resource Utilization Forecast |
| RPC | Relief Planning Committee |
| TSP | Telecommunications Service Provider |
| WNP | Wireless Number Portability |
| WSP | Wireless Service Provider |

Planning Document (PD) Numbering Plan Area (NPA) 819/873

# INTRODUCTION

Numbering Plan Areas (NPAs) 418 and 514, commonly referred to as area codes, were originally assigned to Québec by AT&T in 1947 as two of the 86 area codes to be used in Canada and the continental United States. In 1957 new area code 819 for Québec was split from parts of 514 and 418.  The following table provides a high-level summary of the history of area code usage in the area currently served by NPA 819/873 since 1947.

| Year | Activity |
| --- | --- |
| 1947 | Area Codes 418 and 514 are assigned to Québec by AT&T |
| 1957 | New Area Code 819 is split from 418 and 514 to serve western Québec |
| 2012 | New Area Code 873 overlays 819 in western Québec |

The 819/873 area code or NPA consists of 211 Exchange Areas serving western Québec, and includes the major communities of Hull, Drummondville, Gatineau, Shawinigan, Sherbrooke, Trois-Rivières, Val d’Or and Victoriaville.  A list of the Exchange Areas in NPA 819/873 is provided in Annex B, Table 1.

The table below provides a brief overview of recent activities leading to the development of this PD for NPA 819/873.

| Date | Activity |
| --- | --- |
| 3 February 2017 | NPA 468 is set aside for future relief of NPA complex 819/873 per Telecom Decision CRTC 2017-38 but could be used elsewhere if required. For the purpose of this document the new NPA will be 468. |
| 26 March 2019 | The Canadian Numbering Administrator (CNA) published the January 2019 G-NRUF results which indicated that the Projected Exhaust Date (PED) had advanced to October 2025. |
| 20 September 2019 | The CNA published the July 2019 R-NRUF results which indicated that the PED had advanced to March 2025. |
| 30 January 2020 | The CRTC released Telecom Notice of Consultation CRTC 2020-34 - The Commission announces the establishment of a CRTC Interconnection Steering Committee ad hoc relief planning committee (RPC) to examine options and make recommendations for providing numbering relief to area codes 819 and 873 in western Quebec |
| 24 March 2020 | The CNA published the January 2020 R-NRUF results which indicated that the PED had moved out to July 2025. |
| 18 August 2020 | The CNA published the July 2020 R-NRUF results which indicated that the PED had advanced to December 2023. |
| 21 September 2020 | The CNA issued the PROC and announced the date of the initial Relief Planning Committee (RPC) conference call. |
| 23 February 2021 | The CNA published the January 2021 R-NRUF results which indicated that the PED had advanced to July 2023 |

This Planning Document is prepared by the RPC in accordance with Telecom Notice of Consultation CRTC 2018-409 and the Canadian NPA Relief Planning Guideline, Version 7.0 dated 29 January 2019 (the Guideline).  A copy of the Guideline is available from the Canadian Radio-Television and Telecommunications Commission (CRTC), CRTC Interconnection Steering Committee (CISC), Canadian Steering Committee on Numbering (CSCN) guidelines web page at: https://crtc.gc.ca/cisc/eng/cisf3fg.htm.

The objective of the NPA Relief Planning process is to ensure that CO Codes and telephone numbers are always available for use by TSPs and their customers in the geographic area requiring relief.

It is very important to closely monitor the CO Code requirements of all existing and prospective CO Code Holders so that relief can be timed to ensure that CO Codes and telephone numbers are always available for service providers and customers.

In this PD, a single option is identified for providing NPA relief in the NPA 819/873 geographic area. Given the magnitude of this undertaking, intercompany commitment and co-operation are essential throughout the planning, provisioning and implementation stages of the introduction of the new NPA.

# NPA RELIEF PLANNING PROCESS

The NPA Relief Planning process and the roles of the participants (i.e. CRTC, CNA, CISC, Relief Planning Committee (RPC) participants and Interested Parties) for NPA Relief Planning are identified in the Guideline.

To increase public awareness and participation in the NPA Relief Planning process, the CRTC has determined that NPA RPCs will be established as ad hoc committees of the CISC.  Generally, a separate ad hoc committee is created to deal with relief in each area code.  The CNA, in its function as NPA Relief Planning Coordinator, acts as chair of these ad hoc committees.  Meetings and conference calls of the ad hoc NPA RPCs are all open to public participation and are conducted in accordance with the CISC Administrative Guidelines which are available from the CRTC website at: https://www.crtc.gc.ca/cisc/eng/cag.htm.

NPA Relief Planning is conducted under the regulatory oversight of the CRTC.  Notwithstanding the process detailed in the Guideline, the CRTC may exercise its authority under the Telecommunications Act to alter this process at any time.  The CRTC has the authority under the Telecommunications Act to review, modify and give final approval to the Planning Document (PD) and the Relief Implementation Plan (RIP) developed and submitted by the RPC to the CRTC via the CISC process.

Section 7.1.6 of the Canadian NPA Relief Planning Guideline requires the CNA to create and maintain a distribution list of parties who may be interested in participating in the RPC and to provide them with advance notice of the initial RPC meeting and the release of a PROC.

Any person wishing to participate in the NPA Relief Planning process can contact the CNA and request to be added to the RPC distribution list.  More information on how to participate in CRTC public processes is available at: http://www.crtc.gc.ca/eng/info_sht/g4.htm.

A summary of Canadian geographic area code relief history is available at: https://www.cnac.ca/npa_codes/NPA_History.pdf.

# NPA RELIEF METHODS

The purpose of this section is to identify and briefly describe NPA Relief Methods.

The Guideline states that: “The only NPA Relief Method considered in Canada is the Distributed Overlay Method which superimposes or “overlays” a Relief NPA on top of an entire existing NPA or NPAs.” There are three types of Distributed Overlay:

- a Distributed Overlay over an existing geographic area served by a single existing NPA (a new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by a single NPA);

- a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs (a new NPA is overlaid over a single existing NPA (i.e., the geographic area) that is served by multiple existing overlay NPAs) and,

- a Distributed Overlay over multiple existing geographic areas, each served by one or more existing NPAs (a new NPA is overlaid over multiple existing NPAs (i.e., different geographic areas served by multiple NPAs. This type of overlay may be considered for NPA relief for two or more adjacent NPAs (i.e., geographic areas) within a province).

# NPA EXHAUST INFORMATION

As indicated in the following table, NRUFs for NPA 819/873 were used to determine PEDs, (i.e. the dates when CO Codes in NPA 819/873 would be expected to exhaust).

| NRUF | Projected Exhaust Date (PED) |
| --- | --- |
| G-NRUF January 2019 | October 2025 |
| R-NRUF July 2019 | March 2025 |
| R-NRUF January 2020 | July 2025 |
| R-NRUF July 2020 | December 2023 |
| R-NRUF January 2021 | July 2023 |

Refer to Annex A, Figures 2 through to 4 for graphs of forecast CO Code demand from current and prospective CO Code Holders and Administrative Codes set aside in area code 819/873 for the two most recent NRUFs (January 2021 and July 2020).

# RELIEF OPTION

The Relief Option as identified and examined in this PD is a Distributed Overlay over an existing geographic area served by multiple existing overlay NPAs.

Using this method, a new NPA is overlaid over an existing NPA (i.e., the geographic area) that is served by the overlay complex of NPAs 819/873.

The Relief Option identified above was evaluated using the following assumption:

- The Relief Date for the Distributed Overlay will be 22 October 2022 (approximately 9 months prior to the NPA 819/873 PED of July 2023 identified using the January 2021 R-NRUF results).

See Annex A, Figure 5 for diagram of the Distributed Overlay Relief Option identified by the RPC.

## Distributed Overlay

A Distributed Overlay Relief Option was evaluated which would overlay the NPA 468 over all 211 Exchange Areas comprising the NPA 819/873 area.  See Annex A, Figure 5.

The introduction of a Distributed Overlay would keep the same number of NPA Relief Planning areas in Québec.

After this Distributed Overlay, CO Codes in NPA 468/819/873 would be expected to exhaust in Q3 2034.

Subsequent exhaust of NPA 819/873 was forecast using the Five-Year Historical growth value of 61 CO Codes per year by comparing the January 2021 R-NRUF data in the table below:

| Statistical Method | Data | Period | Quantity of CO Codes |
| --- | --- | --- | --- |
| median | forecast growth | next six years | 96 |
| average | forecast growth | five-year period (January 2022 until January 2027) | 93 |
| average | forecast growth | next six years | 103 |
| average | historical growth | past five years | 64 |
| median | historical growth | past five years | 61 |

# SUMMARY OF RELIEF OPTION

| Relief Option | Projected Exhaust Dates |  | Subsequent Relief Dates |
| --- | --- | --- | --- |
|  | NPA 819/873 | NPA 468/819/873 |  |
| Distributed Overlay | July 2023 | July 2034 | July 2033 |

Note:  Distributed Overlay NPA 468 would be in service on 22 October 2022.

# DIALLING CHANGES FOR LOCAL CALLS

Currently 10-digit dialling is mandatory for local calls originating within area code NPA 819/873 and all neighbouring NPAs (i.e., NPA 249/705, NPA 343/613/753, NPA 354/450/579 and NPA 367/418/581).  Local dialling plans will not change with this relief.

# PROPOSED SCHEDULE

The RPC submits the following schedule for NPA 819/873 relief based on the recommendations contained in this PD and the current PED of July 2023. The RPC will monitor the PED, and if it changes significantly in the future, the RPC will assess the situation and, if necessary, submit recommendations including a revised schedule to the CRTC for consideration and approval.

RELIEF IMPLEMENTATION SCHEDULE

For a Distributed Overlay of NPA 468 over NPA 819/873

| Item | Task or Event | PRIME | START | END |
| --- | --- | --- | --- | --- |
| 1 | NPA 468 is set aside for future relief of QC NPAs 819/873 per CRTC decision 2017-38 but could be used elsewhere if required. For the purpose of this document the new NPA will ne 468 | CRTC |  | 2017-02-03 |
| 2 | CNA identifies NPA exhaust of October 2025 and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future six-year time period | CNA |  | 2019-03-26 |
| 3 | CNA published the Initial R-NRUF (July 2019) results which indicated that PED has advanced to March 2025 | CNA | 2019-06-15 | 2019-09-20 |
| 4 | CRTC issues Telecom Notice of Consultation regarding establishment of an ad hoc Relief Planning Committee | CRTC |  | 2020-01-30 |
| 5 | CNA conducts January 2020 R-NRUF results indicating the PED has moved out to July 2025. | CNA |  | 2020-03-24 |
| 6 | CNA identifies NPA exhaust of December 2023 and notifies by e-mail CRTC staff, CSCN, NANPA & CISC that the NPA will exhaust within the future three-year time period | CNA |  | 2020-08-18 |
| 7 | RPC Chair starts preparing and submitting RPC Chair Reports to the CISC, on an as required basis. | RPC Chair | 2020-01-30 | 2023-02-17 |
| 8 | CNA releases the PROC and announces the date for the initial RPC conference call | CNA | 2020-08-18 | 2020-09-21 |
| 9 | RPC participants review PROC & submit contributions to RPC |  | 2020-09-21 | 2020-10-23 |
| 10 | CNA issues July 2020 R-NRUF results indicating the PED has advanced to December 2023. |  |  | 2020-08-18 |
| 11 | At the request of the ILEC, the date of the initial RPC conference call was postponed until after the January 2021 R-NRUF results were published |  |  | 2020-10-20 |
| 12 | CNA issues January 2021 R-NRUF results showing the PED has advanced to July 2023 |  |  | 2021-02-23 |
| 13 | RPC participants review PROC & submit contributions base on January 2021 R-NRUF results to RPC |  | 2021-02-23 | 2021-03-24 |
| 14 | CNA chairs initial RPC conference call to start development of PD, RIP & PL, & schedules future meetings/conference calls including creation & consultation with CATF and NITF | CNA, RPC | 2021-03-24 | 2021-04-01 |
| 15 | CNA chairs subsequent RPC conference calls to finalize PD & RIP | CNA, RPC | 2021-04-06 | 2021-04-20 |
| 16 | CNA forwards the PD and RIP to the CISC and CRTC for approval | CNA | 2021-04-20 | 2021-04-27 |
| 17 | Special Types of Telecommunications Service Users (911 PSAPs, alarm companies, ISPs, paging companies, etc.) to identify any concerns to RPC & CRTC | Special Users | 2021-04-01 | 2021-04-27 |
| 18 | CRTC issues Telecom Decision approving the Relief Method, Relief Date, New NPA & Relief Implementation Plan (RIP) | CRTC | 2021-04-27 | 2021-08-27 |
| 19 | CNA obtains relief NPA from NANPA | CNA | 2021-08-27 | 2021-09-13 |
| 20 | RPC develops the Planning Letter (PL) | RPC | 2021-09-13 | 2021-09-27 |
| 21 | Task Forces, TSPs and users implement relief (starts upon CRTC approval of RIP and ends on Relief Date) | TSPs | 2021-08-27 | 2022-10-22 |
| 22 | All Telecom Service Providers (TSPs) to develop and file individual consumer awareness programs with the CRTC (may be done collectively by Telecommunications Alliance) (starts upon CRTC approval of RIP) | TSPs | 2021-08-27 | 2022-01-22 |
| 23 | CNA submits PL and RIP to NANPA | CNA | 2021-09-27 | 2021-10-12 |
| 24 | NANPA receives and posts Planning Letter to NANPA website (within 2 weeks of receipt from the CNA) | NANPA | 2021-10-12 | 2021-10-26 |
| 25 | All TSPs implement consumer awareness activities (starts upon filing of Consumer Awareness Programs with the CRTC and is completed on the Relief Date) | TSPs | 2022-01-22 | 2022-10-22 |
| 26 | CNA issues media release (in coordination with TSPs and/or Telecommunication Alliance) (may start upon CRTC approval of RIP) | CNA | 2021-08-27 | 2022-03-22 |
| 27 | All TSPs to notify all customers (including residence, business & special customers) of the new overlay NPA (may start upon the filing of Consumer Awareness Programs with the CRTC) | TSPs | 2022-01-22 | 2022-03-22 |
| 28 | TSPs to submit Progress Report #1 to NITF and CATF (starts after completion date for all TSPs to notify their customers and requires 2 weeks) | TSPs | 2022-03-22 | 2022-04-05 |
| 29 | NITF and CATF develop & submit Progress Report #1 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2022-04-05 | 2022-04-21 |
| 30 | RPC submits Progress Report #1 to CISC/CRTC (linked to NITF and CATF reports) | RPC | 2022-04-21 | 2022-05-05 |
| 31 | iconectiv TRA database updates to add Exchange Areas to new overlay NPA (starts on the date that the PL is posted to the NANPA web site) | iconectiv TRA | 2021-10-26 | 2021-12-21 |
| 32 | All Telecommunications Service Users (including Special Users 911 PSAPs, alarm companies, ISPs, paging companies, etc.) to implement changes to their telecom equipment & systems to accommodate the new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Telecom Service Users | 2021-08-27 | 2022-10-22 |
| 33 | Payphone Providers Reprogram Payphones (starts upon CRTC approval of RIP and ends on the Relief Date) | Payphone Providers | 2021-08-27 | 2022-10-22 |
| 34 | TSPs and database owners/operators to modify systems and industry databases (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs & Database Owners | 2021-08-27 | 2022-10-22 |
| 35 | Operator Services & Directory Assistance Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-08-27 | 2022-10-22 |
| 36 | Directory Publisher Readiness for overlays (ability to identify the NPA in telephone numbers in the directory published after the Overlay NPA is activated) (starts upon CRTC approval of RIP and ends on the Relief Date) | Directory Publishers | 2021-08-27 | 2022-10-22 |
| 37 | 9-1-1 Systems and Databases Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | PSAPS, 9 1 1 Service Providers & TSPs | 2021-08-27 | 2022-10-22 |
| 38 | Network Systems & Equipment Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-08-27 | 2022-10-22 |
| 39 | Service Order & Business System Readiness (starts upon CRTC approval of RIP and ends on the Relief Date) | TSPs | 2021-08-27 | 2022-10-22 |
| 40 | International Gateway Switch Translations Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Int’l TSPs | 2021-08-27 | 2022-10-22 |
| 41 | Canadian Local Number Portability Consortium (CLNPC) Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | CLNPC & NPAC | 2021-08-27 | 2022-10-22 |
| 42 | Toll Free SMS Database Readiness for new NPA (starts upon CRTC approval of RIP and ends on the Relief Date) | Toll TSPs | 2021-08-27 | 2022-10-22 |
| 43 | TSPs apply for Test CO Codes in new NPA (applications may be submitted no more than 6 months and no less than 66 days prior to the start date for the Inter-Carrier Testing Period) (Section 7.16.4 Canadian RP GL) | TSPs | 2021-12-22 | 2022-04-17 |
| 44 | Develop Inter-Carrier Network Test Plans and prepare for testing (individual TSPs to make arrangements in accordance with interconnection agreements) (may start upon CRTC approval of RIP and must be completed by start date for the Inter-Carrier Testing Period) | NITF & TSPs | 2021-08-27 | 2022-06-22 |
| 45 | All international and domestic Telecommunications Service Providers (TSPs) must activate the new NPA in their networks by the start date for the Inter-Carrier Testing Period | TSPs | 2021-08-27 | 2022-06-22 |
| 46 | Activation date for Overlay NPA Test CO Codes and Test Numbers in network (should be completed by the start date for the Inter-Carrier Testing Period) | TSPs |  | 2022-06-22 |
| 47 | Inter-Carrier Testing Period (subject to Inter-Carrier Network Test Plans) (starts about 3 months prior to the Relief Date, and ends about 1 month after the Relief Date) | NITF & TSPs | 2022-06-22 | 2022-11-21 |
| 48 | TSPs to submit Progress Report #2 to NITF and CATF (starts on commencement of Inter-Carrier Testing Period) | TSPs | 2022-06-22 | 2022-07-08 |
| 49 | NITF and CATF develops & submits Progress Report #2 to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2022-07-08 | 2022-07-22 |
| 50 | RPC submits Progress Report #2 to CRTC staff (linked to NITF and CATF report) | RPC | 2022-07-22 | 2022-08-08 |
| 51 | Relief Date (earliest date when CO Codes in new NPA may be activated) |  |  | 2022-10-22 |
| 52 | TSPs submit Final Report to CATF and NITF (starts on Relief Date and provides 2 weeks for preparation & submission) | TSPs | 2022-10-24 | 2022-11-07 |
| 53 | NITF and CATF develop & submit Final Progress Report to RPC (linked to TSP reports to NITF and CATF) | NITF & CATF | 2022-11-08 | 2022-11-22 |
| 54 | The RPC submits Final Progress Report to CRTC staff (linked to NITF and CATF reports) | RPC | 2022-11-22 | 2022-12-06 |
| 55 | TSPs disconnect Test Codes & Numbers, and submit Part 1 form to return Test Codes (starts 1 month after Relief Date and allows 1 month for completion) | TSPs | 2022-11-21 | 2023-01-13 |
| 56 | RPC Chair submits, to the CISC, the final RPC Chair report indicating that the NPA 819/873 ad hoc RPC is no longer required | RPC Chair | 2023-01-13 | 2023-02-17 |

# JEOPARDY CONTINGENCY PLAN (JCP)

The RPC has developed the following JCP for inclusion in the PD for NPA 819/873. This JCP is based on the example contained in Appendix F to the Canadian NPA Relief Planning Guideline.

This JCP shall remain in effect until superseded by a CRTC-approved JCP, the Jeopardy Condition is suspended or 66 days prior to the Relief Date.

The following measures shall be implemented in NPA 819/873 while a Jeopardy Condition is in effect.

During a Jeopardy Condition, CO Code Applicants shall submit all CO Code applications and related correspondence for the Jeopardy NPA to CRTC staff in addition to the CNA.  The CNA shall only assign CO Codes from the exhausting NPA to a CO Code Applicant when instructed by CRTC staff.

- Carriers and/or Telecommunications Service Providers (TSPs):

  - shall age disconnected residential wireline telephone numbers for a maximum of two months;

  - shall age disconnected wireless telephone numbers for a maximum of three months;

  - shall age disconnected business wireline telephone numbers for a maximum of six months. Under special circumstances, the six month aging limit for business telephone numbers may be extended to twelve months, if required, to accommodate local directory publishing dates for high volume call-in applications (e.g., heavily advertised local business numbers such as radio talk shows, food ordering services, ticket sales, chat lines), or for numbers associated with public service emergency applications or for numbers advertised in directories for which customers have requested reference of calls;

  - shall return all CO Codes that are not being used, nor intended to be used to directly serve customers to the assignment pool within two months (e.g., plant test codes);

  - should work towards, and encourage existing customers, to either activate or return the reserved numbers to bring the reserved quantity down to a maximum of 10% of the quantity of numbers In-Service for that customer;

  - shall not allow the quantity of reserved numbers to be increased by new reservation requests by existing customers to more than 10% of the quantity of numbers in service for that customer. In the case of new customers, number reservations shall be limited to 10% of the total quantity of telephone numbers being placed into service for that customer;

  - shall, within 45 days from the date that the CNA declares a Jeopardy Condition submit a Part 1 Form for each remaining reserved CO Code either returning the reserved CO Code to the CNA or requesting assignment of the reserved CO Code. Once the 45-day period has elapsed, the CNA shall make available for general assignment all CO Codes that are still reserved and have not been applied for as assignments on a Part 1 Form received by the CNA. Within 60 days from the date that the CNA declares a Jeopardy Condition, the CNA shall report to CRTC staff and the RPC as to how many of these codes have been assigned or made available for general assignment;

  - shall not be permitted to obtain a new CO Code reservation;

  - shall place all CO Codes assigned prior to the Jeopardy Condition being declared In-Service within three months of the effective date for CO Code activation in the network, or within three months of the date that the Jeopardy Condition was declared. If the CO Code is an Initial Code and the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed beyond the applicable timeframe, then the CNA may grant an extension of up to two months to the In-Service date. The CNA shall initiate reclamation procedures for all CO Codes that have not been placed In-Service within these timeframes unless CRTC staff provides a further extension.

- For new applications for Initial Codes, each CO Code Holder shall certify that the CO Code will be activated in the network and placed In-Service within four months of the date of application for the Code. If the CNA does not receive a Part 4 Form within this timeframe, confirming that the CO Code has been placed In-Service, the CNA will initiate reclamation measures. If the CO Code Holder can demonstrate that, due to circumstances beyond its control, the In-Service date has been delayed not more than six months from the original application date, then the CNA may grant an extension to the In-Service date, so long as the In-Service date is not more than six months beyond the original application date. If the In-Service date has been delayed more than six months from the original application date, then the CNA shall reclaim the Code unless CRTC staff provides a further extension.

- When applying for an Additional Code for Growth, a CO Code Holder who is submitting a Part 1 Form and Appendix B worksheet shall also submit a completed Supplementary Form for a Growth CO Code Application (attached) which certifies and/or provides the following information for the specific switching entity/POI and Exchange Area when the Growth CO Code is being requested in a Jeopardy Condition:

  - certification that all held telephone numbers have been released;

  - certification that reserved numbers do not exceed ten percent of the total quantity of numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline;

  - certification that each reseller/dealer had been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two times the highest quantity of customer numbers assigned in any month during the previous 12 months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory;

  - confirmation that the Part 1 form submitted with the application has the Jeopardy Condition box in section 1.6 checked to certify that the existing CO Codes are projected to exhaust within 4 months of the date of application and that the months-to-exhaust is documented on an Appendix B submitted to the CNA;

  - a completed Telephone Number Utilization Report for the applicable switching entity signed by both a company officer and the company’s authorized representative;

  - confirmation that the requested Growth CO Code was forecasted in the most recent NRUF or an explanation as to why it was not is attached; and,

  - confirmation that the requested Growth CO Code will be placed In-Service within four months of the date of assignment.

- Any CO Codes for growth assigned after the implementation of this JCP must be activated in the network and placed In-Service within four months of assignment. In the event that a CO Code Holder is unable to place the CO Code In-Service within four months of the date of assignment, the CO Code Holder must return the assigned CO Codes or submit a written request for extension to the CNA. Such written requests must include documentation explaining the reason(s) for the missed date and proposing the new In-Service date. If the explanation includes reasons beyond the control of the CO Code Holder, the CNA may extend the In-Service date a maximum of one month. If the CO Code Holder does not place the CO Code In-Service within the one-month extension, the CNA shall initiate the reclamation process at the end of the one-month extension unless CRTC staff provides a further extension.

- A Carrier that has multiple switching entities within an Exchange Area shall examine the possibility of, and implement where feasible, number sharing between those switches as a potential method to delay requirements for additional CO Codes.

- The CNA will request two versions (two separate worksheets (Form 1 and Form 2)) of the J-NRUF input from all current and prospective CO Code Holders quarterly until three (3) months before relief is provided.

  - The forecast quantities in Form 1 should be the same as or lower than the last R-NRUF input submitted, prior to declaration of a Jeopardy Condition. CO Code Holder forecasts may reflect an increase in demand in the period subsequent to the Relief Date.

  - Form 2 will reflect the actual demand required by the CO Code Holder's current business plan and will be provided for information purposes only.

- The CNA will compare the initial J-NRUF input to the recent NRUF inputs, to assess forecasting trends. The CNA shall monitor all inputs and shall test them for reasonableness in consultation with the Carrier. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the deviations, then the matter will be referred to the CRTC staff.

- The CNA will request subsequent J-NRUF input from all current and prospective CO Code Holders quarterly until 3 months before relief is provided. If one or more R-NRUFs have already been conducted, and depending on the severity of the Jeopardy Condition, the CNA may defer a J-NRUF by up to two months if such a deferral brings the timing of that J-NRUF and subsequent J-NRUFs into alignment with other NRUFs that are conducted at 12, 6 or 3 month intervals. Subsequent J-NRUF input will be compared with the initial J-NRUF input to evaluate the effectiveness of the JCP. The CNA shall monitor all J-NRUF inputs and shall test them for reasonableness in consultation with the Telecommunications Service Providers. If the CNA is dissatisfied with the reasonableness, or the rationale provided for the changed forecasts, then the matter will be referred to CRTC staff.

- A CO Code Applicant must have submitted a completed J-NRUF to the CNA before the CNA may assign a CO Code to that CO Code Applicant.

- If a CO Code applicant wishes to request more CO Codes than it identified in its most recent J NRUF, the CO Code Applicant should discuss the matter with the CNA. If the CO Code Applicant wishes to proceed with the request, the CO Code Applicant will forward the request and revised forecast to CRTC staff and the CNA for consideration.

- The CO Codes identified in the NPA CO Code Inventory Chart as “Assignable CO Codes in a Jeopardy Condition” will be assigned in the order determined by the RPC after all CO Codes which are “Available for Assignment as of [day month year] have been assigned.

- After each J-NRUF, the CNA shall provide CRTC staff, the RPC and CSCN participants with a report providing an updated NPA CO Code Inventory Chart for the NPA in jeopardy as well as the aggregate results of the most recent J-NRUF.

- Exceptional issues or concerns may be referred by the CNA, or by individual entities (with a courtesy copy to the CNA), to the CRTC staff for resolution.

- In a situation where the Relief Date is on or after the PED, the quantity of CO Codes that may be assigned to a CO Code Applicant prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date) shall be limited to the quantity forecasted by the CO Code Applicant in its most recent NRUF forecast submitted prior to the Jeopardy Condition being declared by the CNA (if no previous NRUF was submitted, then the previous forecast will be deemed to be zero codes). When making requests to obtain CO Codes prior to the end of the Jeopardy Condition (i.e. 66 days prior to the Relief Date), the CO Code Applicant may change the Exchange Area or the month when the CO Code assignment is required, provided a new J-NRUF and explanation accompanies the application. The control imposed by this option may be relaxed if subsequent J-NRUFs defer the PED to after the Relief Date. CO Codes that become available for assignment due to future reduced demand from other current and prospective CO Code Holders may be assigned at the discretion of CRTC staff.

- If the CNA determines that the implementation of the JCP has not extended the Projected Exhaust Date of the NPA beyond the Relief Date, the CNA will consult with CRTC staff and further CO Code conservation and assignment procedures may be ordered by the Commission (e.g., rationing, lottery, etc.).

Supplementary form for a Growth CO Code Application – Page 1 of 2 – Telephone Number Utilization Report

This form is required with each request for an Additional Code for Growth in an NPA where a Jeopardy Condition is in effect. It should be submitted to the CNA together with the Part 1 and Appendix B forms that are required for an application for an Additional Code for Growth. See the Part 1 form for information on how and where to submit the form.

I hereby certify that the following information is true and accurate to the best of my knowledge and has been prepared in accordance with Special Conservation Procedures for a Jeopardy Condition contained in the Canadian NPA Relief Planning Guideline or the applicable approved Jeopardy Contingency Plan.

Name & Signature of Authorized Representative of Code Holder	Title	Date

Name & Signature of Company Officer (see item 3 of this JCP)	Title	Date

Contact information:	Entity Name: 	__________________	Contact Name:	_____________

Address: 	__________________	City, Province, Postal Code:	_____________

Telephone: 	__________________	Facsimile:	_____________

E-mail: 	__________________

Switch Identification (Switching Entity/POI) CLLI: _______________ 	Exchange Area: ________________

For the above Switch Identification and Exchange Area for which a Growth CO Code is requested:

I certify that all held telephone numbers have been released

I certify the total quantity of reserved numbers does not exceed ten percent (10%) of the total quantity of telephone numbers as defined in Appendix G of the Canadian CO Code (NXX) Assignment Guideline

I certify that each reseller/dealer has been advised of the Jeopardy Condition and the requirement that they would only be allocated additional numbers during the Jeopardy Condition on the provision to the CO Code Holder of written confirmation that their number inventory has been reduced to an amount less than two (2) times the highest quantity of customer numbers assigned in any month during the previous twelve (12) months. Additional numbering resources will only be provided by the CO Code Holder to the reseller/dealer to the extent that the reseller's/dealer's inventory can only increase up to a maximum of three months' inventory.

The Part 1 form submitted with the application has the Jeopardy Condition box in section 6 checked (this certifies that the existing CO Codes are projected to exhaust within four (4) months of the date of the application or within the period specified in an approved Jeopardy Contingency Plan, and that the months-to-exhaust is documented on an Appendix B submitted to the CNA).

The Telephone Number Utilization Report on page 2 of this form has been completed.

The requested Growth CO Code was forecasted in the most recent NRUF, or an explanation as to why it was not is attached.

The requested Growth CO Code will be placed In-Service within four (4) months of the date of assignment.

Supplementary Form for a Growth CO Code Application – Page 2 of 2 – Telephone Number Utilization Report

Use Arial 9 to complete this form. (Note: If the spreadsheet below does not show on your display, please change the Work view to "Print Layout" or "Reading Layout")

Remarks: _______________________________________________________________________________

________________________________________________________________________________________

NPA 819/873 CO Code Inventory Chart

The following chart and the instructions it contains will apply in NPA 819/873 in a Jeopardy Condition.

The chart below lists quantities of CO Codes unassignable prior to a Jeopardy Condition, CO Codes that become assignable in a Jeopardy Condition and CO Codes in NPA 819/873 assigned and In-service as of 1 April 2021. The CO Codes that become assignable in a Jeopardy Condition shall only be made available for assignment when all other available CO Codes have been assigned in the order listed below.

|  |  | Quantity |
| --- | --- | --- |
| A | Total CO Codes in NPAs 819/873 (NXX format) | 1600 |
| B | CO Codes unassignable prior to a Jeopardy Condition |  |
|  | N11 Service Codes (211, 311, 411, 511, 611, 711, 811, 911) | 16 |
|  | Special Use Codes (555, 950 & 976) | 5 |
|  | Home NPA Code(s) | 4 |
|  | Current Neighbouring NPA Codes (249, 343, 450, 579, 613, 705) | 12 |
|  | Future Geographic NPA Codes (257, 273, 468, 487, 584, 851, 871 & 942) (Note 1) | 16 |
|  | Plant Test Codes (958 & 959) | 4 |
|  | Special 7-digit Dialling Codes (310, 610 & 810) | 5 |
|  | USA Dialing problem (207 & 802) | 4 |
|  | Total B | 66 |
| C | CO Codes assignable prior to a Jeopardy Condition (C=A-B) | 1534 |
| D | CO Codes unassignable prior to a Jeopardy Condition that become assignable in a Jeopardy Condition: |  |
|  | Future Canadian Geographic NPA Codes (Notes 1 & 2) | 14 |
|  | Current Neighbouring NPA Codes (249, 343, 450, 579, 613, 705) (Note 2) | 12 |
|  | Total D | 26 |
| E | Assignable CO Codes in a Jeopardy Condition (E=C+D) | 1560 |
| F | Assigned CO Codes as of 1 April 2021 | 1280 |
| G | Net CO Codes available for assignment as 1 April 2021 without a Jeopardy Condition (G=C-F) | 254 |
| H | Net CO Codes available for assignment as of 1 April 2021 in a Jeopardy Condition (H=E-F) | 280 |

Notes:

- In Telecom Decision CRTC 2017-38, the Commission determined that area code 468 should be set aside as a potential future relief area code for area codes 819 and 873.

- CO Codes 257, 273, 487, 584, 851, 871 & 942 should become assignable in a Jeopardy Condition.

- In an extreme Jeopardy Condition (i.e. when the Projected Exhaust Date is earlier than the Relief Date), the current Neighbouring NPA Codes 249, 343, 450, 579, 613, and 705 could be assignable with CRTC staff approval.

# SELECTION OF RELIEF NPA CODE

If the recommended Relief Option requires a new NPA Code, the criteria for selection of an appropriate area code for relief is addressed in section 4.11 of the Canadian NPA Relief Planning Guideline. The criteria that should be taken into account when Future Canadian Geographic NPAs are being considered as candidates for relief of a specific current Canadian Geographic NPA include the following:

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in the area that is being relieved (Home NPA(s)).

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in another NPA within the same province where there is a possibility that a single new NPA Code could be overlaid on more than one NPA within the province, or where boundary realignment could occur that affects another NPA.

- The preferred Future Canadian Geographic NPA Code should not be an NPA Code that is assigned as a CO Code in an Exchange Area in a neighbouring NPA, if the neighbouring NPA has 7-digit local calling within the NPA and i) the Exchange Area in the neighbouring NPA where the CO Code is assigned has local calling to the NPA being relieved or ii) the Exchange Area in the neighbouring NPA where the CO Code is assigned does not have local calling to the NPA being relieved, but other Exchange Areas within that neighbouring NPA have 7-digit local calling to the Exchange Area where the CO Code is assigned as well as local calling to the new NPA.

CO Codes corresponding to Future Canadian Geographic NPA Codes which are not assigned in NPA 819/873 and therefore meet criterion a) above are 257, 273, 468, 487, 584, 851, 871 and 942.

CO Codes 257, 273, 468, 487, 584, 851, 871 and 942 are all assigned in at least one neighbouring NPA so none of these resources meet criterion b).

Criterion c) is not applicable since NPA 819/873 and all neighbouring NPAs have 10-digit local calling.

The NPA Code Selection Tool located on the CNA web site at https://www.cnac.ca/npa_codes/relief/NPA_Selection_Tool.xlsx can assist in selecting a relief NPA Code from the pool of NPA Codes reserved for relief of geographic Canadian NPAs. The following table, extracted from the NPA Code Selection Tool, shows all codes corresponding to Future Canadian Geographic NPA Codes that are designated as unassignable CO Codes in the Home NPA, and therefore are preferred candidates when selecting a relief NPA Code for NPA 819/873.

| NXX corresponding to Future NPA | 257 | 273 | 468 | 487 | 584 | 851 | 871 | 942 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Distributed Overlay |  |  |  |  |  |  |  |  |

Indicates that corresponding CO Code is designated as unassignable in Home NPA(s)

NPA Codes (257, 273, 468, 487, 584, 851, 871 and 942) are equally suitable as a new NPA Code for the relief of NPA 819/873, unless analysis of potential future code reservations for NPA reliefs in other areas of Canada, or TSP cost considerations indicate a preference for one code over another for the relief of NPA 819/873.

In Telecom Decision CRTC 2017-38, the Commission determined that area code 468 should be set aside for the potential future relief of Québec NPA complex 819/873 but could be used elsewhere if required.

# RECOMMENDATIONS

The RPC recommends:

- The Relief Method should be a Distributed Overlay of a new NPA Code on NPA 819/873 in Western Québec;

- The Relief NPA Code for NPA 819/873 should be NPA 468 as per Telecom Decision CRTC 2017-38 and

- The Relief Date should be 22 October 2022 to provide Carriers and customers with advanced notification and sufficient lead-time to implement relief in NPA 819/873.

ANNEXES

Planning Document (PD)

Numbering Plan Area (NPA) 819/873

- MAPS AND FIGURES

Figure 1 – Overview Map of NPA 819/873

Figure 2 – NPA 819/873 Actual and Forecast CO Code Assignments

Figure 3 – NPA 819/873 CO Code Exhaust – January 2021 R-NRUF

Figure 4 – NPA 819/873 CO Code Exhaust – July 2020 R-NRUF

Figure 5 –  Distributed Overlay

- NPA 819/873 EXCHANGE AREAS

Table 1 – NPA 468/819/873 Exchange Areas After Distributed Overlay

NPA 468/819/9/873 Exchange Areas

Akulivik

Amos

Angliers

Arthabaska

Arundel

Asbestos

Aston-Jonction

Aupaluk

Ayer's Cliff

Aylmer

Barraute

Bearn

Beaucanton

Becancour

Belleterre

Bishopton

Bouchette

Bromptonville

Buckingham

Bury

Cadillac

Campbell's Bay

Champlain

Chapeau

Charette

Chartierville

Chelsea

Cheneville

Chesterville

Chisasibi

Clericy

Clova

Coaticook

Compton

Cookshire

Danville

Daveluyville

Deauville

Deschaillons

Drummondville

Dubuisson

Duparquet

Dupuy

East Angus

East Hereford

Eastmain

Eastmain 1

Fabre

Ferme-Neuve

Fort-Coulonge

Fortierville

Frontenac

Fugereville

Gatineau

Gentilly

Gracefield

Grand'Mere

Grand-Remous

Grenville

Ham-Nord

Inukjuak

Ivujivik

Joutel

Kangiqsualujjuaq

Kangiqsujuaq

Kangirsuk

Kazabazua

Kingsey-Falls

Kuujjuaq

Kuujjuaraapik

La Corne

La Minerve

La Patrie

La Reine

La Sarre

La Tuque

Labelle

Lac-des-Ecorces

Lac-Drolet

Lac-du-Cerf

Lac-Edouard

Lac-Megantic

Laforge

L'Annonciation

Latulipe

Laurierville

L'Avenir

Laverlochere

Lebel-sur-Quevillon

Lorrainville

Louiseville

Louvicourt

Low

Luskville

Lyster

Macamic

Magog

Malartic

Maniwaki

Manouane

Manseau

Maskinonge

Matagami

Montebello

Mont-Laurier

Nantes

Nedelec

Nemaska

Nicolet

Nominingue

Norbertville

Normetal

North Hatley

Notre-Dame-de-la-Paix

Notre-Dame-de-la-Salette

Notre-Dame-de-Lourdes

Notre-Dame-du-Bon-Conseil

Notre-Dame-du-Laus

Notre-Dame-du-Nord

Obedjiwan

Ottawa-Hull

Palmarolle

Papineauville

Parc De La Verendrye

Parent

Perkins

Plessisville

Princeville

Puvirnituk

Quaqtaq

Quyon

Radisson

Remigny

Richmond

Riviere-Heva

Rochebaucourt

Rock Island

Rouyn-Noranda

Saint-Albert

Saint-Alexis-Des-Monts

Saint-Barnabe

Saint-Ludger

Saint-Paulin

Salluit

Sanmaur

Sawyerville

Scotstown

Senneterre

Shawinigan

Shawville

Sherbrooke

South Durham

St-Adolphe-de-Dudswell

St-Adolphe-D'Howard

St-Andre-Avellin

St-Boniface-de-Shawinigan

St-Bruno-de-Guigues

St-Celestin

St-Cyrille

St-Donat-de-Montcalm

Ste-Agathe

Ste-Angele

Ste-Anne-du-Lac

Ste-Eulalie

Ste-Gertrude

Ste-Marie-de-Blandford

St-Emile-de-Suffolk

Ste-Monique-de-Nicolet

Ste-Sophie-de-Levrard

St-Eugene-de-Guigues

St-Faustin

St-Felix-de-Kingsey

St-Germain-de-Grantham

St-Gregoire

St-Guillaume

St-Jovite

St-Leonard-d'Aston

St-Malo

St-Mathieu

St-Nazaire

Stoke

St-Pierre-de-Wakefield

St-Pierre-Les-Becquets

St-Roch-de-Mekinac

St-Sebastien (Frontenac Co.)

St-Sylvere

St-Wenceslas

Taschereau

Tasiujaq

Temiscaming

Thurso

Tingwick

Trois-Rivieres

Umiujaq

Val David

Val-des-Bois

Val-D'Or

Victoriaville

Ville-Marie

Villeroy

Wakefield

Warwick

Waskaganish

Waswanipi

Waterville

Weedon

Wemindji

Wickham

Windsor

Woburn

Wotton

Yamachiche

- Distribution List

| Bill Barsley Canada Telephone: 416-279-7989 Bill.Barsley@Outlook.com | Doug Birdwise Interested Party 109 Westpark Drive Ottawa, ON Canada K1B 3G4 Telephone: 613-830-0081 douglas.birdwise@sympatico.ca |
| --- | --- |
| Jeffrey DeSarno Chief Tehnology Officer Access Communications Co-operative Limited 2250 Park St Regina, SK S4N 7K7 Telephone: 306-565-5364 Fax: 306-565-5395 jeffrey.desarno@myaccess.coop | Nicola McLaughlin Team Lead Allstream 200 Wellington St W. F12 Toronto, ON Canada M5V 3G2 Telephone: 416-640-5271 Nicola.mclaughlin@allstream.com |
| Ronda Otto Sr. Director Service Delivery Allstream Telephone: 763-270-3557 ronda.otto@allstream.com | Elizabth Pereira Senior Manager, Service Delivery Allstream Telephone: 647-776-1868 elizabeth.pereira@allstream.com |
| NXX Admin Bell Canada nxx.admin@bell.ca | Joey-Lynn Abdulkader Specialist Regulatory Affairs Bell Canada 160 Elgin Street, 19th Floor Ottawa, ON Canada K2P 2C4 Telephone: 613-785-6314 Fax: 613-560-0472 joey-lynn.abdulkader@bell.ca |
| Diane Faillant Associate - Network Management/NSS (National Numbering Solution) Bell Canada 671 LAGAUCHETIERE Ouest. 11 Montreal, QC Canada H3B 2M8 Telephone: 514-870-6044 Fax: 514-786-9062 diane.faillant@bell.ca | Marie-Christine Hudon Network Provisioning Bell Canada 671 Rue De La Gauchetière, O.11 Montreal, QC H3B 2M8 Telephone: 514-870-7839 m-christine.hudon@bell.ca |
| Daniel Morrison Specialist - Voice Network Services Bell Canada 100 Dundas St Flr 3 London, ON Canada N6A 5B6 Telephone: 519-850-6386 daniel.morrison@bell.ca | Marian Hearn Project Executive Canadian LNP Consortium Inc. 350 Palladium Drive, Suite 208 Kanata, ON Canada K2V 1A8 Telephone: 613-287-0225 Fax: 800-406-9250 marian.hearn@clnpc.ca |
| Rodger McNabb Manager Contracts and Receivables Canadian LNP Consortium Inc. 350 Palladium Drive. Suite 208 Kanata, ON Canada K2V 1A8 Telephone: 613-287-0226 rodger.mcnabb@clnpc.ca | Jacques Sarrazin President of the CLNP consortium Canadian LNP Consortium Inc. Suite 208, 350 Palladium Dr Kanata, ON Canada K2V 1A8 Telephone: 613-287-0225 Fax: 613-823-1169 sarrazin@clnpc.ca |
| Pavel Bigarov CNA System Administrator Canadian Numbering Administrator 150 Isabella Street - Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 pavel.bigarov@cnac.ca | Fiona Clegg Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 202 fiona.clegg@cnac.ca |
| David Comrie Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 204 david.comrie@cnac.ca | Suresh Khare CO Code Manager Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 201 suresh.khare@cnac.ca |
| Natalie Lessard Numbering Resource Administration Canadian Numbering Administrator 150 Isabella Street, Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext. 203 natalie.lessard@cnac.ca | Kelly T. Walsh CNA Program Manager Canadian Numbering Administrator 150 Isabella Street - Suite 605 Ottawa, ON Canada K1S 5H3 Telephone: 613-702-0016 ext 205 kelly.walsh@cnac.ca |
| Bill Mason Manager, Numbering Administration Canadian Radio-television and Telecommunications Commission Central Building Les Terrasses de la Chaudière 1 Promenade du Portage Gatineau, QC Canada K1A 0N2 Telephone: 819-953-8882 Fax: 819-953-0795 bill.mason@crtc.gc.ca | Danielle Paquin Director, Governmental Affairs – Québec Canadian Security Association (CANASA) Canada Telephone: (905) 513-0622 x 226 membership@canasa.org |
| Eric Smith Vice President, Regulatory Affairs Canadian Wireless Telecommunications Association (CWTA) 80 Elgin Street, Suite 30 Ottawa, ON Canada K1P 6R2 Telephone: 613-233-5884 Ext. 255 Fax: 613-233-2032 documentcontrol@cwta.ca | Chris Armstrong Sales & Marketing Manager CityWest cable & Telephone (formerly Prince Rupert Telephones) 248 Third Ave W. Prince Rupert, BC Canada V8J 1L1 Telephone: 250-627-0902 Fax: 250-627-0905 Chris.Armstrong@cwct.ca |
| Ofir Smadja President COMsolve 3601 Highway 7 East, Suite 400 Markham, ON Canada L3R 0M3 Telephone: 416-915-5008 info@comsolveinc.com | Edward Antecol VP Professional Services COMsolve Inc. 70 East Beaver Creek Road, #202 Richmond Hill, ON Canada L4B 3B2 Telephone: 416-915-5008 x106 edward.antecol@comsolveinc.com |
| CLEC Admin Comwave Networks 61 Wildcat Road Toronto, ON Canada M3J 2P5 clecteam@comwave.net | Sundar Nagulan Team Lead - Voice Engineering Comwave Networks 61 Wildcat Rd Toronto, ON M3J 2P5 Telephone: 647-427-8363 snagulan@comwave.net |
| Albert Yin Comwave Networks Inc. Telephone: 416-663-9700 Ext 330 Fax: 416-736-3165 ayin@comwave.net | Denis Viens Technicien Commutation Cooptel 5521, Chemin de l'Aéroport Valcourt, QC J0E2L0 Telephone: 450-532-5656 ext 1042 Fax: 450-532-3148 dviens@cooptel.coop |
| Numbering E-Mail Distributel Communications Limited 177 Nepean Street Ottawa, ON Canada K2P 0B4 numbering@distributel.ca | Geoff Batstone V.P., General Counsel Distributel Communications Limited 177 Nepean Street, Suite 300 Ottawa, ON Canada Telephone: 613-319-9964 geoff.batstone@distributel.ca |
| Don Cavanagh VP Distributel Communications Limited 177 Nepean Street, Suite 300 Ottawa, ON Canada K2P 0B4 Telephone: 613-237-7005 Fax: 613-237-7009 donald.cavanagh@distributel.ca | Sarah Reilly Porting Group Manager - Telecommunications Distributel Communications Limited 177 Nepean Street, Suite 300 Ottawa, ON Canada K2P 0B4 Telephone: 613-237-7191 sarah.reilly@distributel.ca |
| Regulatory Fibernetics Corporation 605 Boxwood Dr Cambridge, ON Canada N3E1A5 regulatory@corp.fibernetics.ca | Rick Schleihauf VP – Regulatory Affairs and Carrier Relations Fibernetics Corporation 605 Boxwood Drive Cambridge, ON Canada N3E 1A5 Telephone: 519-489-6700 ext 629 Fax: 519-653-7686 rschleihauf@corp.fibernetics.ca |
| Jennifer McCue N/A FlexITy Suite 800, 45 Vogell Rd Richmond, ON L4B 3p6 Telephone: 905-787-3547 Fax: 905-787-3599 jennifer.mccue@flexity.ca | Groupe Masketel ingops.telephonie@maskatel.qc.ca |
| Praba Gunam President/CEO InnSysVoice Corp. 4500 Sheppard Ave E, Suite 111 Toronto, ON Canada M1S 3R6 Telephone: 416-800-0797 praba@innsys.ca | Deirdre Massiah-Gomes Interested Party Canada Telephone: 416-684-3070 Massiahgomesdeirdre@gmail.com |
| Iristel team.regulatory@iristel.com | Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 didorders@iristel.com |
| Andreea Badea Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 Telephone: 416-800-4747 abadea@iristel.ro | Samer Bishay CEO Iristel Inc. 11 Bowan Court Toronto, ON Canada M2K 3A8 Telephone: 416-800-9999 Fax: 416-628-0891 sbishay@iristel.com |
| Andrew Matoga VP President ISP Telecom 1155 Boul Rene-Levesque O Suite 2500 Montreal, QC Canada H3B 2K4 Telephone: 416-548-4626 Fax: 416-548-4847 andrew@isptelecom.net | Jenoshan Balasingam IXICA Communications Inc. 174 Shropshire Drive Toronto, ON Canada M1P 1Z7 Telephone: 844-747-2729 ext: 1100 jenoshan@ixica.com |
| Phillip Koneswaran VP - Business IXICA Communications Inc. 174 Shropshire Drive Toronto, ON Canada M1P 1Z7 Telephone: 844-747-2729 ext: 2100 phillip@ixica.com | Sharon Ledwell Consultant for SSI Micro Ltd. Ledwell Inc 26 Brookside Ave Toront, ON M6S4G7 Telephone: 416-904-0480 sharon@ledwellinc.ca |
| Michel Gilbert Directeur Corporatif - Reglementation NorthernTel, Limited Partnership 87 rue Ontario ouest 5eme etage St-Urbain Montreal, QC Canada H2X 1Y8 Telephone: 514-493-5396 reglementa@telebec.com | Austin He Network Planning Analyst, Network Planning Primus Management ULC. 2680 Skymark Avenue, Suite 100 Mississauga, ON Canada L4W 5L6 Telephone: 416-207-3361 AHe@primustel.ca |
| Dennis Béland Director, Regulatory Affairs, Telecommunications Quebecor Media Inc. 612 St-Jacques, 15e étage Tour Sud Montreal, QC Canada H3C 4M8 Telephone: 514-380-4792 Fax: 514-380-4664 dennis.beland@quebecor.com | Rogers NumberAdmin@rci.rogers.com |
| Vivek Bhardwaj Traffic Specialist Rogers Communications 8200 Dixie Rd. Brampton, ON Canada L6T 0C1 Telephone: 647-747-3569 vivek.bhardwaj@rci.rogers.com | Jennifer Mack Traffic Specialist Rogers Communications 8200 Dixie Rd. Brampton, ON Canada L6T 0C1 Telephone: 647-747-2168 jennifer.mack@rci.rogers.ca |
| Emmanuel Shousha Senior Traffic Specialist Rogers Communications 800, Gauchetiere O, Bureau 4000 Montreal, QC Canada H5A 1K3 Telephone: 514-995-0000 se000895@rci.rogers.com | Jean-Michel Dupuis Senior Public Services Specialist Rogers Communications Canada Inc. 800 rue de la Gauchetiere Ouest, Suite 4000 Montreal, QC Canada H5A 1K3 Telephone: 1-866-501-7727 Fax: 1-800-506-3962 jeanmichel.dupuis@rci.rogers.com |
| Gerry Thompson Manager, Intercarrier Relations Rogers Communications Canada Inc. 350 Bloor Street East, 6th Floor Toronto, ON Canada M4W 0A1 Telephone: 416-935-5239 Fax: 416-935-7719 Gerry.Thompson@rci.rogers.com | Nicholas Bayly Carrier Services Specialist Shaw Business 3636 23 ST NE Calgary, AB Canada T2E 6Y7 Telephone: 403-538-5223 nicholas.bayly@sjrb.ca |
| Lien Kaura Carrier Service Specialist Shaw Communications Inc. 2441 37th Ave NE Calgary, AB Canada T2E 6Y7 Telephone: 587-390-2982 Lien.Kaura@sjrb.ca | Ken Shackleton Manager, Consumer Voice Technology and Infrastructure Shaw Communications Inc. 2728 Hopewell Place NE Calgary, AB Canada T1Y 7J7 Telephone: 403-303-4024 Fax: 403-930-1850 ken.shackleton@sjrb.ca |
| Bruce Uy TN Administrator Shaw Telecom Inc 2728 Hopewell Pl NE Calgary, AB T1Y 7J7 Telephone: 403-234-6271 Fax: 403-750-4501 bruce.uy@sjrb.ca | Regulatory Affairs Shaw Telecom Inc. 630 - 3 Ave SW Calgary, AB Canada T2P 4L4 regulatory@sjrb.ca |
| Dominic Germain Internet services and switching director Sogetel Inc. 111 Rue du 12-Novembre Nicolet, QC J3T1S3 Telephone: 819-293-1226 Fax: 819-293-6120 dominic.germain@sogetel.com | Krystle Nasr SSi Connexions Inc. 365B Old Airport Rd. Yellowknife, NT Canada X1A 3T4 Telephone: 613-271-6464 regulatory@ssimicro.com |
| Sabrena McBride Product Manager T-Mobile USA 3625 132nd Ave SE Bellevue, WA USA 98006 Telephone: 877-413-5903 Sabrena.mcbride32@t-mobile.com | Diane Dolan Voice Service Manager TekSavvy Solutions Inc 227 rue Montcalm Gatineau, QC Canada J8Y 3B9 Telephone: 819-484-1234 ddolan@teksavvy.ca |
| Chantal Beaudoin Collaboratrice principale - Coordination WNP & Gestion NPA Telebec 555, avenue Centrale Val-d’Or, QC J9P1P6 Telephone: 819-824-7227 Fax: 819-824-7282 cbeaudoin@telebec.com | Lucie Pugliese Administrator Telecommunications Alliance 1575 Saturne Brossard, QC Canada J4X 1N4 Telephone: 450-465-8277 Fax: 450-465-0703 lucie.pugliese@sympatico.ca |
| Telecommunications Xittel Inc 1350 rue Royale, bureau 800 Trois-Rivieres, QC Canada G9A 4J4 clec-admin@xittel.net | Olena Bilozerska Network Planning Manager I, TS CC Planning & Management TELUS 200 Consilium Place, Floor 6 Scarborough, ON Canada M1H 3G2 Telephone: 647-837-1798 Olena.Bilozerska@telus.com |
| Nancy McIntyre Mgr - Planning & Engineering TELUS 3777 Kingsway Floor 07S Burnaby, BC V5H 3Z7 Telephone: 604-908-2029 nancy.mcintyre2@telus.com | Karen Robinson Network Planning Manager – Translations & Traffic Network Operation TELUS 200 Consilium Place Scarborough, ON Canada M1H 3J3 Telephone: 647-684-3053 Karen.Robinson3@telus.com |
| Peter Szabo Sr. Engineer TELUS 7th Floor – 3777 Kingsway Burnaby, BC Canada V5H 3Z7 Telephone: 604-695-3188 Fax: 604-663-1300 peter.szabo@telus.com | Johny Fernandez Technology Strategy TELUS Mobility 200 Consilium Place, 6th Flr Scarborough, ON Canada M1H 3J3 Telephone: 647-453-4442 Johny.fernandez@telus.com |
| Marc Berruyer Network Planner Videotron General Partnership 2155 Boul. Pie IX, 3e etage, bloc A Montreal, QC Canada H1V 2E4 Telephone: 514-380-4255 Fax: 514-899-8452 marc.berruyer@videotron.com | Anh-Thu Nguyen Ingenieur Planifi. & Gestion Du Trafic Vidéotron ltée 2155 boul. Pie IX Montréal, QC Canada H1V 2E4 Telephone: 514-380-1764 Anh-Thu.Nguyen@videotron.com |