CRTC INTERCONNECTION STEERING COMMITTEE

CONTRIBUTION FORM:

Working Group:       CSCN                     Date of Submission: 2026-05-13

Contribution #: 312L

TIF #:      125                                                         File ID: CNCO312L

Task Title:  TBP Rollout Schedule

Related to Task(s) ID:  117, 118

Contributor:

Name:		 CSCN Secretary

Company:	 CSCN

Address:

Tel:

Fax:

E-mail:   Secretary-CSCN@cnac.ca

Distribution to:	CSCN

Subject:  Rollout Scheule for Thousand-Block Pooling (“TBP”)

Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada

Background and Commission Direction

On 28 November 2025, the Canadian Radio-television and Telecommunications Commission (CRTC) issued Telecom Decision CRTC 2025-321, “Modification of deadline for thousand-block pooling.” At paragraph 37 of the Decision, the Commission made several key requests and directives as follows:

a) requests the CSCN to develop a schedule for the phased-in implementation of TBP, by exchange, taking into account CO code demand and TSP readiness, and file it for information with the Commission no later than 30 March 2026, with:

i. the first exchange transitioning to TBP no later than 28 July 2026; and

ii. the final exchange transitioning to TBP no later than 28 July 2027

b) directs all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule; and

c) expects that all LECs and wireless carriers will continue to actively work towards TBP readiness as guided by the CSCN’s TBP checklist, as applicable.

### Rollout Approach

In accordance with the Decision, we have developed a phased rollout schedule commencing with a trial in Brampton, Markam and Victoria on 28 July 2026 and concluding with the final Exchange Area on 28 July 2027. As indicated in the carriers’ submission dated 24 July 2025, the carriers proposed an Exchange Area-based rollout that aligns with the phased approach successfully employed in the United States (U.S.). Consistent with the U.S. approach, which prioritized deployment in the Top 100 MSAs, we recommend an initial rollout encompassing the top 110 Canadian exchanges with highest demand for numbering resources according to the criteria detailed below.

Selection Criteria and Phase-Gate Conditions

Exchange Areas chosen for the first year of the rollout are those with at least 12 NPA-NXXs ordered between 2015 and 2025, according to data from the Canadian Numbering Administrator (CNA) in contribution CNCO313A. This criterion ensures TBP is deployed where it will be most effective and aligns with the U.S. approach, which prioritises larger, high-demand exchanges during the initial deployment year.

To provide further context for the scope and rationale of the rollout, we note that Canada has 2,996 Exchange Areas. The rollout schedule includes 110 Exchange Areas, selected based on demonstrated demand for numbering resources and phased in accordance with the timelines set out in this contribution. This targeted approach focuses industry effort where TBP will deliver measurable benefits; implementing TBP across all exchanges at this time many of which show little to no demand-would not be a prudent use of resources and would impose costs on legacy systems for which no commensurate benefit would be realized. As demand matures in additional Exchange Areas such that TBP would realize tangible benefits, those exchanges can be added to the TBP program and opened consistent with the implementation milestones and phase-gate criteria set out herein. The industry will bring forward a follow-up submission with respect to the Exchange Areas not included in the initial rollout schedule, in advance of the date by which all Exchange Areas are expected to be TBP-ready under Telecom Decision CRTC 2025-321.

Launch Trial

TBP will initially launch in 3 Exchange Areas (Markham, ON, Brampton, ON and Victoria, BC) on 28 July 2026 (see contribution CNCO292D.docx for details). The successful launch and evaluation of TBP in these Exchange Areas will serve as a foundation for expanding TBP to additional Exchange Areas, in phases, based on carrier readiness. The list of Exchange Areas included in the phased rollout plan are provided in the table below.

Obligations Applicable to All Carriers in Canada

LNP Query Readiness

Regardless of which Exchange Areas are launching in this initial phase, all Carriers operating in Canada must be performing LNP queries on a TBP ready query database by the Launch Date of July 28, 2026. This may entail changing LNP query provider.

Additional Requirements for Carriers in Pooled Exchange Areas

Carriers participating in a pooled Exchange Area are subject to further requirements beyond LNP query readiness (including successful production testing of TBP systems that enable block reservations and return).

Note: Exchange Areas involving entities with an ITPA presence are excluded until 28 July 2027. This exclusion is based on the list of ITPA members included in the ITPA Part 1 application submitted on 27 June 2025.

#### Phased Rollout Timeline

| Phase Order | Phase Name | Description | Date |
| --- | --- | --- | --- |
| 1 | Phase 1-Launch Trial | Phase kickoff meeting | 2026-03-24 |
| 1 | Phase 1-Launch Trial | Deadline for Affirmation forms | 2026-04-23 |
| 1 | Phase 1-Launch Trial | 3-Exchange Area Launch trial. | 2026-07-28 |
| 2 | Phase 1A | Phase 1A kickoff meeting | 2026-09-02 |
| 2 | Phase 1A | Deadline for Affirmation forms | 2026-10-02 |
| 2 | Phase 1A | Launch Exchange Areas within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories. | 2026-12-01 |
| 3 | Phase 1B | Phase 1B initial meeting | 2026-10-14 |
| 3 | Phase 1B | Deadline for Affirmation forms | 2026-11-13 |
| 3 | Phase 1B | Continue rollout in the same regions. | 2027-01-12 |
| 4 | Phase 2 | Phase 2 initial meeting | 2026-11-25 |
| 4 | Phase 2 | Deadline for Affirmation forms | 2026-12-25 |
| 4 | Phase 2 | Launch Exchange Areas in Alberta and Quebec. | 2027-02-23 |
| 5 | Phase 3 | Phase 3 initial meeting | 2027-02-24 |
| 5 | Phase 3 | Deadline for Affirmation forms | 2027-03-26 |
| 5 | Phase 3 | Launch Exchange Areas in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories. | 2027-05-25 |
| 6 | Phase 4 | Phase 4 initial meeting | 2027-04-29 |
| 6 | Phase 4 | Deadline for Affirmation forms | 2027-05-29 |
| 6 | Phase 4 | Include Exchange Areas with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases. | 2027-07-28 |

Phased Deployment Schedule for TBP Across Canadian Exchange Areas

(see the table above for the phase dates)

| Phase Order | Phase Name | Exchange Area (CNAS) | Rate Center (BIRRDS) | Province (Canada Post) |
| --- | --- | --- | --- | --- |
| 1 | 1-LaunchTrial | Brampton | BRAMPTON | ON |
| 1 | 1-LaunchTrial | Markham | MARKHAM | ON |
| 1 | 1-LaunchTrial | Victoria | VICTORIA | BC |
| 2 | 1A | 100 Mile House | 100 MILE HOUSE | BC |
| 2 | 1A | Abbotsford | ABBOTSFORD | BC |
| 2 | 1A | Ajax-Pickering | AJAX-PICKERING | ON |
| 2 | 1A | Aldergrove | ALDERGROVE | BC |
| 2 | 1A | Alliston | ALLISTON | ON |
| 2 | 1A | Aurora | AURORA | ON |
| 2 | 1A | Barrie | BARRIE | ON |
| 2 | 1A | Brockville | BROCKVILLE | ON |
| 2 | 1A | Chilliwack | CHILLIWACK | BC |
| 2 | 1A | Claremont | CLAREMONT | ON |
| 2 | 1A | Collingwood | COLLINGWOOD | ON |
| 2 | 1A | Cooksville | COOKSVILLE | ON |
| 2 | 1A | Cranbrook | CRANBROOK | BC |
| 2 | 1A | Huntsville | HUNTSVILLE | ON |
| 2 | 1A | Kanata-Stittsville | KANATA STITTSVILLE | ON |
| 2 | 1A | Kelowna | KELOWNA | BC |
| 2 | 1A | Maple | MAPLE | ON |
| 2 | 1A | Milton | MILTON | ON |
| 2 | 1A | Nanaimo | NANAIMO | BC |
| 2 | 1A | New Westminster | NEW WESTMINSTER | BC |
| 2 | 1A | Newmarket | NEWMARKET | ON |
| 2 | 1A | Niagara Falls | NIAGARA FALLS | ON |
| 2 | 1A | North Vancouver | NORTH VANCOUVER | BC |
| 2 | 1A | Oakville | OAKVILLE | ON |
| 2 | 1A | Oshawa | OSHAWA | ON |
| 2 | 1A | Prince George | PRINCE GEORGE | BC |
| 2 | 1A | Richmond | RICHMOND | BC |
| 2 | 1A | Richmond Hill | RICHMOND HILL | ON |
| 2 | 1A | Sault Ste. Marie | SAULT SAINTE MARIE | ON |
| 2 | 1A | South Kamloops | SOUTH KAMLOOPS | BC |
| 2 | 1A | St. Catharines-Thorold | SAINT CATHARINES THOROLD | ON |
| 2 | 1A | Streetsville | STREETSVILLE | ON |
| 2 | 1A | Sudbury | SUDBURY | ON |
| 2 | 1A | Thornhill | THORNHILL | ON |
| 2 | 1A | West Vancouver | WEST VANCOUVER | BC |
| 3 | 1B | Ottawa-Hull | OTTAWA-HULL | ON |
| 3 | 1B | Toronto | TORONTO | ON |
| 3 | 1B | Vancouver | VANCOUVER | BC |
| 4 | 2 | Alma | ALMA | QC |
| 4 | 2 | Banff | BANFF | AB |
| 4 | 2 | Calgary | CALGARY | AB |
| 4 | 2 | Chicoutimi | CHICOUTIMI | QC |
| 4 | 2 | Edmonton | EDMONTON | AB |
| 4 | 2 | Fort McMurray | FORT MCMURRAY | AB |
| 4 | 2 | Fox Creek | FOX CREEK | AB |
| 4 | 2 | Gatineau | GATINEAU | QC |
| 4 | 2 | Grande Prairie | GRANDE PRAIRIE | AB |
| 4 | 2 | High River | HIGH RIVER | AB |
| 4 | 2 | Lethbridge | LETHBRIDGE | AB |
| 4 | 2 | Maniwaki | MANIWAKI | QC |
| 4 | 2 | Medicine Hat | MEDICINE HAT | AB |
| 4 | 2 | Ottawa-Hull | OTTAWA-HULL | QC |
| 4 | 2 | Peace River | PEACE RIVER | AB |
| 4 | 2 | Pointe-Claire | POINTE-CLAIRE | QC |
| 4 | 2 | Quebec | QUEBEC | QC |
| 4 | 2 | Red Deer | RED DEER | AB |
| 4 | 2 | St-Jerome | SAINT-JEROME | QC |
| 4 | 2 | Ste-Genevieve | SAINTE-GENEVIEVE | QC |
| 4 | 2 | Valleyfield | VALLEYFIELD | QC |
| 5 | 3 | Amherst | AMHERST | NS |
| 5 | 3 | Bathurst | BATHURST | NB |
| 5 | 3 | Charlottetown | CHARLOTTETOWN | PE |
| 5 | 3 | Fredericton | FREDERICTON | NB |
| 5 | 3 | Halifax | HALIFAX | NS |
| 5 | 3 | Miramichi | MIRAMICHI | NB |
| 5 | 3 | Moncton | MONCTON | NB |
| 5 | 3 | Moose Jaw | MOOSE JAW | SK |
| 5 | 3 | Oakbank | OAKBANK | MB |
| 5 | 3 | Portage La Prairie | PORTAGE LA PRAIRIE | MB |
| 5 | 3 | Regina | REGINA | SK |
| 5 | 3 | Saint John | SAINT JOHN | NB |
| 5 | 3 | Saskatoon | SASKATOON | SK |
| 5 | 3 | St. John's | SAINT JOHNS | NL |
| 5 | 3 | Sydney | SYDNEY | NS |
| 5 | 3 | Truro | TRURO | NS |
| 5 | 3 | Whitehorse | WHITEHORSE | YT |
| 5 | 3 | Windsor | WINDSOR | NS |
| 5 | 3 | Winnipeg | WINNIPEG | MB |
| 5 | 3 | Yellowknife | YELLOWKNIFE | NT |
| 6 | 4 | Belleville | BELLEVILLE | ON |
| 6 | 4 | Brantford | BRANTFORD | ON |
| 6 | 4 | Burlington | BURLINGTON | ON |
| 6 | 4 | Chatham | CHATHAM | ON |
| 6 | 4 | Cornwall | CORNWALL | ON |
| 6 | 4 | Drummondville | DRUMMONDVILLE | QC |
| 6 | 4 | Essex | ESSEX | ON |
| 6 | 4 | Granby | GRANBY | QC |
| 6 | 4 | Guelph | GUELPH | ON |
| 6 | 4 | Hamilton | HAMILTON | ON |
| 6 | 4 | Joliette | JOLIETTE | QC |
| 6 | 4 | Kingston | KINGSTON | ON |
| 6 | 4 | Kitchener-Waterloo | KITCHENER-WATERLOO | ON |
| 6 | 4 | Leamington | LEAMINGTON | ON |
| 6 | 4 | Lindsay | LINDSAY | ON |
| 6 | 4 | Listowel | LISTOWEL | ON |
| 6 | 4 | London | LONDON | ON |
| 6 | 4 | Montreal | MONTREAL | QC |
| 6 | 4 | Peterborough | PETERBOROUGH | ON |
| 6 | 4 | Sarnia | SARNIA | ON |
| 6 | 4 | Sherbrooke | SHERBROOKE | QC |
| 6 | 4 | Sorel | SOREL | QC |
| 6 | 4 | St-Hyacinthe | SAINT-HYACINTHE | QC |
| 6 | 4 | Thunder Bay | THUNDER BAY | ON |
| 6 | 4 | Trois-Rivieres | TROIS-RIVIERES | QC |
| 6 | 4 | Victoriaville | VICTORIAVILLE | QC |
| 6 | 4 | Windsor | WINDSOR | ON |
| 6 | 4 | Woodstock | WOODSTOCK | ON |

The full Canadian Exchange Area listing may be found on the CNA Website at:
https://cnac.ca/reference_data/canadian_exchange_area_listing.htm, or
https://cnac.ca/data/ExchangeAreaListing.csv

Phase-gate for subsequent launches. Progression to subsequent TBP rollout phases is contingent on the successful completion of the preceding phase, determined by the following criteria:

- Carrier affirmations to TBP readiness are complete, and all carriers were able to successfully conduct production-level testing.

- No major routing issues or adverse customer impacts are reported for a period of two months following the launch of TBP in an Exchange Area.

- No material evidence of a marked increase in dual assignment or issues with portability requests is observed.

Future Deployment

Future deployment in additional exchanges beyond the rollout schedule should follow proposals and recommendations by the CSCN based on data provided by the CNA.

Conclusion

We submit that initiating TBP deployment in the Exchange Areas of Brampton, Markham and Victoria is the most pragmatic, least disruptive, and technically robust approach to begin TBP implementation in Canada. Subsequent phased rollouts (as per the schedule) will follow based on the lessons learned and data gathered from this initial deployment. This plan is designed to:

- Balance industry readiness by allowing larger carriers to advance while affording additional implementation time for smaller TSPs.

- Enable comprehensive carrier testing and identification of potential errors or misrouting.

- Produce actionable data for the CSCN and the Commission to inform and enhance future rollout phases.

- Support number conservation objectives effectively.

Carriers Intervention, Part 1 application by the independent telecommunications providers associations to delay the implementation of thousands-block pooling for small telecommunications service providers, 24 July 2025.

Pre-launch activities for any Exchange or group of Exchanges shall be as set out in CNCO237B to be amended and clarified.