## Coversheet
CRTC INTERCONNECTION STEERING COMMITTEE
CONTRIBUTION FORM:
Working Group: |  | CSCN |  | Date of Submission: |  | 2025-03-17
Contribution #: |  | 262I
TIF #: | 117 |  |  | File ID: | CNCO262I
Task Title: |  | Updated Task List for TBP
Related to Task(s) ID: |  |  | 118, 119, 120
Contributor:
Name: |  | Joey-Lynn Abdulkader & Marie-Christine Hudon
Company: |  | Bell Canada
Address:
Tel:
Fax:
E-mail:
Distribution to: |  | CSCN
Subject:
Thousands-Block Pooling Task List
(See next tab)

## TBP Task List
Thousand Block Pooling Task List
Activity # | Activity / Requirement | Task | Prime | TBP Activity Target Date | Dependency | Comments | Start Date | End Date | Progress
1 | NPAC Requirements | CLNPC to arrange for activation of Thousands-Block Pooling within the NPAC | CLNPC | Completed |  | Completed to support non-prod testing | Completed | COMPLETE
2 | NPAC Requirements | Information on availability of an NPAC testbed | CLNPC | Completed |  | Starting in January 2025, all SOA and LSMS vendors can test and have their systems certified to the Canadian NPAC. | Completed | COMPLETE
3a | Vendor Requirement | SOA and LSMS vendors need to complete certification and regression testing. (NON-PROD) | SOA and LSMS Vendors | End of March 2025 |  | Required prior to production testing | 2025-02-01 | COMPLETE
3b | Carrier Requirement | Creation of test plan for LSMS and SOA regarding activation of TBP capabilities (NON-PROD) | CLNPC | By February, 2025 |  | Required prior to non-prod testing | 2025-02-01 | COMPLETE
3c | Carrier Requirement | Creation of a test plan for SCP/QDB regarding activation of TBP capabilities (NON-PROD) | Each Carrier (network teams) | End of March 2025 |  | Required prior to non-prod testing |  |  | In progress
4 | Carrier Requirements | Test their LSMS and Signalling Control Points (handling of block records/ LNP queries) - (NON-PROD) | Carriers | End of March 2025 |  | Required prior to production testing | 2025-02-01 |  | In progress
5 | TBP Administrator Requirement | Need to test an interface from the PA to the NPAC for submission of Part 1Bs and Part 5s (if industry agrees its required) | CSCN | By April 1, 2025 |  | Cannot start prod-testing without this | 2025-03-01 | 2025-04-01 | In progress [ NTD ask ED and KT ]
6 | TBP Administrator Requirement | Creation of complete definition of the block ordering process | CSCN | By April 1 2025 (CNA Test) |  | Cannot start prod-testing without this | 2025-03-01 | COMPLETE
7a | Vendor Requirement | SOA and LSMS vendors need to complete certification and regression testing. (PRODUCTION TESTING) | SOA and LSMS Vendors | Earliest start is April 1, 2025 |  | Required prior prod-testing | 2025-03-01 | COMPLETE
7b | Carrier Requirement | Create/Adapt test plan for LSMS and SOA regarding activation of TBP capabilities. (PRODUCTION TESTING) | Each Carrier | By April 1, 2025 |  | Required prior prod-testing | 2025-03-01 | 2025-04-01 | In progress
7c | Carrier Requirement | Create/Adapt test plan for SCP/QDB regarding activation of TBP capabilities. (PRODUCTION TESTING) | All Carriers (network teams) | By April 1, 2025 |  | Required prior prod-testing | 2025-03-01 | 2025-08-01 | In progress
8 | Carrier Requirements | Modify ordering processes for CO Codes and Thousands-blocks | Carriers | By April 1, 2025 |  | Canadian CIGRR working on a training session in March/April for Canadian users (BIRRDS/LERG) - highly recommended that carriers receive F2F training | 2025-03-01 | 2025-04-01 | In progress
9 | Carrier Requirements | Develop processes for block returns/donations | Carriers | By April 1, 2025 |  |  | 2025-03-01 | 2025-04-01 | In progress
10 | Carrier Requirements | Develop processes for receiving contaminated blocks | Carriers | By April 1, 2025 |  |  | 2025-03-01 | 2025-04-01 | In progress
11 | Carrier Requirements | Develop processes for receiving non-contaminated blocks | Carriers | By April 1, 2025 |  |  | 2025-03-01 | 2025-04-01 | In progress
12 | Carrier Requirements | Develop processes for intra-carrier block transfers within the same Exchange Area | Carriers | By April 1, 2025 |  |  | 2025-03-01 | 2025-04-01
13 | Rules around LRN Requests | Activation of a new pooled CO Code | iconectiv | By April 1, 2025 |  |  | 2025-03-01 | COMPLETE?
14 | Tracking of carrier readiness for TBP | Tracking of carrier readiness for TBP based on a defined checklist | CNAC coordinator (TBD) | By April 1, 2025 |  |  | 2025-03-01 | 2025-04-01 | In progress
15 | Carrier Requirements | Modify their NPAC subscriptions to receive block information (LSMS profile, SOA profile) | Carriers | By start of production testing | Enable NPAC profile (non-prod complete) | Complete non-prod testing first | 2025-04-01 | 2025-04-30 | In progress
16 | Carrier Requirements | Must ensure SOAs support required Thousands-Block Pooling functionality | Carriers | By start of production testing |  |  | 2025-04-01 | 2025-04-30 | In progress
17 | Update the CSCN-Administered Guidelines | Central Office Code (NXX) Assignment Guideline (based on recommendations ) | CSCN | By October 6, 2025 | CRTC Decision | Some forms are coming together. |  | 2025-10-06 | In progress
18 | Update the CSCN-Administered Guidelines | NRUF Guideline (based on recommendations) | CSCN | By October 6, 2025 | CRTC Decision | Industry running out of time to introduce a new NRUF for July 2025 |  | 2025-10-06
19 | TBP Administrator Requirement | Create a set of TBP administrator requirements to define how the Pooling Administrator (PA) will administer numbering resources. | CNA/CSCN | By October 6, 2025 | CSCN Concurrence once drafted | CRTC dependencies (TIF 118 and TIF 119) and CNAS development risks. |  | 2025-10-06
20 | TBP Administrator Requirement | Need an online Canadian Numbering Administration System user interface for thousands-block pooling | CNA/CNAC | By October 6, 2025 | CNAC funding, successful RFP. Likely a manual process while new system developed and tested. |  |  | 2025-10-06
21 | TBP Administrator Requirement | Settle on the architecture of workflow confirmations amongst carriers, the PA and the NPAC | CNA/CSCN | By October 6, 2025 | Notes - WNP, CLNPC, BPWG | Mostly known, still some residual issues (i.e. will the carrier get a confirmation that the carriers block has been successfully activated or created in the NPAC) |  | 2025-10-06 | In progress
22 | TBP Administrator Requirement | Need a user manual for electronic portal for ordering thousands-blocks | CNA | By October 6, 2025 | Need CNAC funding and approval to build portal for electronic submission of TBP requests. | Deliverable under software development RFP |  | 2025-10-06
23 | TBP Administrator Requirement | Need to develop a way to take the rolling forecast data and integrate it with the block allocation process | CNA | By October 6, 2025 | Nice to have | CRTC dependency US model: Can only request CO code if forecast exceeds available 1000 blocks |  | 2025-10-06
24 | Carrier Requirements | Implement new forecasting processes | Carriers | By October 6, 2025 | NRUF Guideline + CRTC Decision TIF 118 (report forecasting 144A) |  |  | 2025-10-06 | In progress
25 | Carrier Requirements | Develop new snapback message handling - identify CO Code holder and block identifier | Carriers | By October 6, 2025 |  | Scope of Launch |  | 2025-10-06 | In progress
26 | Carrier Requirements | LERG Subscription changes from NXX level to Block Level and frequency to accommodate shorter activation timeframes | Carriers | By October 6, 2025 |  | Any LERG 6 processing needs to account for additional block records whether you use them or not and optionally carriers may consider call processing optimization to prevent routing to unallocated blocks. LERG 6 input to spam detection engines |  | 2025-10-06 | In progress
28 | Test Plan Prior to TBP Rollout | Testing of WNP clearinghouse function with TBP functionality enabled (using Neustar testbed) | All carriers with wireless trading partners | By October 6, 2025 |  | Wireline carriers will need to do intermodal testing |  | 2025-10-06 | In progress
29 | Test Plan Prior to TBP Rollout | New error types, and new ways (?) to implement certain key operations through WNP clearinghouse | CNA | By October 6, 2025 |  |  |  | 2025-10-06
30 | Processes related to mistakes | Review process maps re new error types and error paths e.g. block assigned by CNA, but on or just before Block Activation date, NPAC rejects block creation roughly 40 days after block is assigned and error could occur shortly after the block effective date. | TBD | By October 6, 2025 |  |  |  | 2025-10-06
31 | Processes related to mistakes | Process to recover a TN that a carrier failed to protect prior to a block donation or where a customer seeks to reinstate a cancelled service TN from a block that has been donated | TBD | By October 6, 2025 | dependent on scope of launch |  |  | 2025-10-06
32 | Processes related to mistakes | Dispute resolution processes (there will be changes to dispute resolution see example below from ATIS TBCOCAG sections 7.1.15 and 7.1.16 | TBD | By October 6, 2025 | dependent on scope of launch |  |  | 2025-10-06
33 | TBP Administrator Requirement | Need to develop a publicly accessible inventory of available blocks | CNA/CNAC | After October 6, 2025 | CNAC Funding |  |  | COMPLETE
34 | TBP Administrator Requirement | Need to develop a publicly accessible way to view block assignments | CNA/CNAC | After October 6, 2025 | CNAC Funding |  |  | COMPLETE
35 | Rules around LRN Requests | Process for transfer of CO Code responsibility | CSCN | After October 6, 2025 |  |  |  | 2025-12-31
36 | Rules around LRN Requests | Process for Facilitated LRN | CSCN | After October 6, 2025 |  |  |  | 2025-12-31
37 | Carrier Requirements | Implement changes to telephone number allocation consistent with recommendations to the CRTC | Carriers | TBD | Commission decision re: para 51 report (TIF 118) |  |  | TBD | In progress
38 | Carrier Requirements | Develop new fallout processes | Carriers | TBD | Tasks # 30, 31, 32 |  |  | TBD
40 | TBP Rollout Schedule | Develop the rollout schedule | CSCN | TBD |  |  |  | TBD | In progress
41 | Implement TBP in accordance with a Rollout Schedule |  | CSCN | TBD |  |  |  | TBD | In progress
42 | Industry Go/No-go | Industry-wide Go/No-go decision based on industry tracking | CRTC/CISC