
CRTC INTERCONNECTION STEERING COMMITTEE
CONTRIBUTION FORM:
Working Group:           CSCN                                           Date of Submission:  2026-09-17
Contribution #:  330A
TIF #:        117                                                                 File ID:  CNCO330A
Task Title:  TBP Implementation Monitoring
Related to Task(s) ID:  117, 118, 119, 120, 125
Contributor:
            Name:		David Comrie
            Company:	CNA
            Address:
            Tel:
            Fax:
            E-mail:		David.comrie@cnac.ca
Distribution to:		CSCN
Subject:	Draft Status Report #11, Thousand-Block Pooling, Canadian Implementation


CRTC INTERCONNECTION STEERING COMMITTEE
TIF REPORT
Date Submitted:		DD MMMM YYYY
WORKING GROUP:	CSCN
REPORT #:			XXXA		File ID:  CNREXXXA
REPORT TITLE:		Status Report #11, Thousand-Block Pooling, Canadian Implementation
OUTCOME: ONGOING
RELATED TASK(s) #: 118, 119, 120, 125
BACKGROUND: 
On 5 February 2024, the CRTC issued Telecom Regulatory Policy CRTC 2024-26 - Implementing thousand-block pooling.
Paragraph 31 of the Policy directs the CRTC Interconnection Steering Committee (CISC) to: 
· facilitate and monitor the implementation of TBP and assist in resolving any challenges;
· file quarterly progress reports on 30 March, 30 June, 30 September, and 30 December until TBP is operational; and
· as part of its first quarterly progress report, advise the Commission as to whether the segregation of numbers between wireless and wireline technology must be retained or whether this requirement can be eliminated as a further way to preserve numbers.
Accordingly, the CSCN, as a CISC working group, has taken on the task of providing the quarterly reports. 
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[bookmark: _Toc224546923]Background
On 5 February 2024, the CRTC issued Telecom Regulatory Policy CRTC 2024-26 - Implementing thousand-block pooling.
Paragraph 31 of the Policy directs the CRTC Interconnection Steering Committee (CISC) to: 
· facilitate and monitor the implementation of TBP and assist in resolving any challenges;
· file quarterly progress reports on 30 March, 30 June, 30 September, and 30 December until TBP is operational; and
· as part of its first quarterly progress report, advise the Commission as to whether the segregation of numbers between wireless and wireline technology must be retained or whether this requirement can be eliminated as a further way to preserve numbers.
· This advice was provided in the 30 March 2024 quarterly report
Accordingly, the CSCN, as a CISC working group, has taken on, via TIF 117, the task of providing the quarterly reports. 
[bookmark: _Toc224546924]TIF Work Breakdown
CSCN has formed the following TIFs for industry participants to define the guidelines and procedures for TBP:
[bookmark: _Hlk161735079]TIF 117 - TBP Implementation Monitoring
TIF 118 - Update CSCN-Administered Guidelines for Thousands-Block Pooling
TIF 119 - Report of inclusion of unused numbers from previously assigned CO Codes in pool
TIF 120 - Report on LIR expansion or Exchange Area consolidation opportunities
IF 125 - TBP Controlled Production Rollout
TIF 126 - Update the Canadian TBCOCAG and Appendix A (Audits)

[bookmark: _Toc224546925]Production Thousands-Block Pooling end-to-end testing
A collaborative group of CSCN Industry participants has established and is progressing through many end-to-end testing activities related to the launch of TBP in Canada.
As of the date of this report DD MMMM YYYY:
1. Production NPAC has been enabled for TBP (May 18, 2025).
1. All LSMS and SOA vendors used by Canadian carriers for number porting and routing have passed certification testing. (June 20, 2025)
Note: With the industry desire to receive TN range notifications from the NPAC, additional testing is required by LSMS and SOA vendors if carriers wish to enable TN range notifications.
An additional database was identified but has been since passed certification as of early September.
1. 27 test pooled CO Codes have been assigned by the CNA so far. The following table shows the planned and assigned codes. Codes missing the OCN and Date Assigned are currently only planned. (2026-09-14)
	#
	Exchange Area
	NPA
	NXX
	OCN
	Company
	Date Assigned

	1
	Vancouver
	257
	945
	8086
	TELUS
	2025-04-04

	2
	Vancouver
	257
	946
	497E
	Rogers
	2025-04-08

	3
	Halifax
	782
	945
	329A
	Bell
	2025-04-03

	4
	Halifax
	782
	946
	4878
	Eastlink
	2025-04-10

	5
	Toronto
	942
	945
	8051
	Bell
	2025-04-08

	6
	Toronto
	942
	946
	8821
	Rogers
	2025-04-09

	7
	Montreal
	263
	945
	328F
	Videotron
	2025-04-02

	8
	Montreal
	263
	946
	8050
	Bell
	2025-04-09

	9
	Regina
	474
	945
	9868
	SaskTel
	2025-04-08

	10
	Regina
	474
	946
	2782
	TELUS
	2025-04-04

	11
	Rimouski
	367
	945
	8083
	TELUS
	2025-04-04

	12
	Rimouski
	367
	946
	984C
	Bell
	2025-04-09

	13
	Ste-Victoire 
	354
	945
	818D
	CoopTEL
	2025-04-22

	14
	Ste-Victoire 
	354
	946
	843D
	Sogetel
	2025-06-26

	15
	Thunder Bay
	807
	945
	8303
	TELUS Mobility
	2025-08-13

	16
	Thunder Bay
	807
	946
	8094
	Thunder Bay Telephone
	2025-08-18

	17
	Brandon
	584
	945
	120F
	Westman Communications
	2025-08-28

	18
	Brandon
	584
	946
	8088
	Bell MTS
	2025-09-12

	19
	London
	382
	945
	2776
	MNSI
	2025-09-29

	20
	London
	382
	946
	8226
	Execulink Telecom Inc.
	2025-10-03

	21
	Terrace
	257
	947
	2933
	BELL West
	2025-09-29

	22
	Terrace
	257
	948
	705F
	City West
	2025-10-09

	23
	Yellowknife
	867
	945
	8092
	Northwestel
	2025-10-01

	24
	Yellowknife
	867
	946
	940G
	Ssi
	2025-10-01

	25
	Stratford
	382
	947
	004G
	Quadro
	2026-01-30

	26
	Stratford
	382
	948
	400E
	Mornington
	2026-02-02

	27
	Kingston
	753
	945
	
	Iristel
	

	28
	Kingston
	753
	946
	920D
	WTC
	2026-09-10



1. The following table shows the number of Thousands Blocks applications processed by the CNA, broken down by category. The categories are:
3.  Assigned - where a Block was successfully assigned),
3.  Recovered - where a Block was donated back and made available to other TSPs to test and
3.  Updated - where an application was processed to update a Block’s information, an application was denied (for various reasons) or it was cancelled by the applicant. 
(2026-09-14)
	Category
	Number of Applications Processed

	Assigned
	93

	Recovered
	60

	Updated
	19



Up-to-date status assignments are available on the CNA website at: https://cnac.ca/co_codes/co_block_status.htm 

1. Special NRUF was requested to capture utilization information prior to launch of TBP. The most recent S-NRUF results were reviewed and approved by CRTC staff and they were published on 25 March 2026. 
1. Carriers are in the process of updating their LSMS and SOA profiles to support TBP.
1. Directions to carriers for updating their LSMS profiles, SOA profiles and CO Code level filters are available from CLNPC, a copy of which is posted on the CSCN Drafts page.
1. Carrier checklist for TBP readiness has been approved by CSCN and sent to CNAC for use (20 June 2025). The CNAC TBP Coordinator has sent out requests for TSPs to complete the checklist online.
1. CNA interface to production NPAC is operational. 93 Part 1B forms and 48 Part 5 forms have been generated by the CNA for NPAC. (2026-09-14)
[bookmark: _Toc224546926]Thousand Block Pooling Task List 
A collaborative group of TIF 117 participants have been maintaining the task list noting progress to date for the overall industry implementation of TBP in the form of several updated contributions. Details of contributions since the last TIF 117 report are noted in the TIF 117 commentary below.
[bookmark: _Toc224546927]Carrier Checklist for Thousands Block Pooling 
A collaborative group of TIF 117 participants have created a checklist to monitor the progress to date.
[bookmark: _Toc224546928]TIF 117 - TBP Implementation Monitoring
This TIF met during CSCN 132 on 10 & 11 June 2025 and on 20 June 2025.Quarterly reports will be submitted on or before 30 March, 30 June, 30 September, and 30 December until TBP is operational.
	Contribution Name
	Submitter
	Date Posted

	CNCO262E - Bell/Sasktel/COMsolve contribution - TIF 117 - Thousand Block Pooling Task List
	Bell/Sasktel/COMsolve
	2025-02-07

	CNCO262F - Bell contribution - TIF 117 - Thousand Block Pooling Task List
	Bell/Sasktel/COMsolve
	2025-02-19

	CNCO284A - CLNPC/Teksavvy/Eastlink/CTA/Transunion contribution - TIF 117 - Clarification and suggested edits for TBP Task List
	CLNPC/Teksavvy/
Eastlink/CTA/Transunion
	2025-03-06

	CNCO285A - CSCN contribution - TIF 117 - Draft March 2025 TBP monitoring report
	CSCN
	2025-03-17

	CNCO262G - CSCN contribution - TIF 117 - TBP Task List
	CSCN
	2025-03-17

	CNCO262H - CSCN contribution - TIF 117 - TBP Task List
	CSCN
	2025-03-21

	CNCO288A - COMsolve/CTA/Bell contribution - TIF 117 - Carrier Checklist for Thousands Block Pooling
	CSCN
	2025-06-03

	CNCO288B - CSCN contribution - TIF 117 - Carrier Checklist for Thousands Block Pooling
	CSCN
	2025-06-13

	CNCO289A - CSCN contribution - TIF 117 - Draft quarterly TBP implementation report #6
	CSCN
	2025-06-13

	CNCO262I - Bell contribution - TIF 117 - Thousands-Block Pooling Task List
	Bell
	2025-10-02

	CNCO297A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #7
	CNA
	2025-09-12

	CNCO310A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #8
	CNA
	2025-12-03

	CNCO321A - CNA contribution - TIF 117 - Draft quarterly TBP implementation report #9
	CNA
	2026-03-03

	CNCO321B - CSCN Contribution - TIF 117 - TBP monitoring Mar 2026
	CSCN
	2026-03-17

	CNCO327A – CNA contribution – TIF 117 - Draft quarterly TBP implementation report #10
	CNA
	2026-06-02

	CNCO330A – CNA contribution – TIF 117 - Draft quarterly TBP implementation report #10
	CNA
	YYYY-MM-DD


[bookmark: _Toc224546929]TIF 118 - Update CSCN-Administered Guidelines for Thousands-Block Pooling
TIF 118 was worked on extensively during the CSCN 134 Face to Face meetings on 10 & 11 February 2026.
The following contributions have been received under TIF 118:
	Contribution Name
	Submitter
	Date Posted

	CNTF118A - TIF 118 (Proposed) - Update CSCN-Administered Guidelines for Thousands-Block Pooling
	CSCN
	2024-03-14

	CNCO234A - COMsolve contribution - TIF 118 - Flow chart of when to request a new CO Code in a pooled area
	COMsolve
	2024-04-12

	CNCO235A - COMsolve contribution - TIF 118 - TBP Guideline Definitions
	COMsolve
	2024-04-15

	CNCO237A - COMsolve contribution - TIF 119 - TBP implementation plan & milestones
	COMsolve
	2024-04-23

	CNCO238A - KRob Solutions contribution - TIF 118 - Thousands Block Pooling Utilization Exceptions
	KRob Solutions
	2024-04-25

	CNCO236B - COMsolve contribution - TIF 118 - TBP Block Return Checklist
	COMsolve
	2024-04-30

	CNCO240A - COMsolve contribution - TIF 118 - TBP Paragraph 51 questions
	COMsolve
	2024-05-02

	CNCO238B - KRob Solutions contribution - TIF 118 - Thousands Block Pooling Return Exceptions
	COMsolve
	2024-05-02

	CNCO236C - CSCN contribution - TIF 118 - TBP Block Return Checklist
	CSCN
	2024-05-03

	CNCO241A - COMsolve contribution - TIF 118 - Semi-annual forecasting requirements
	COMsolve
	2024-05-07

	CNCO242A - COMsolve contribution - TIF 118 - LSMS and SCP Functionality in a TBP Environment
	COMsolve
	2024-05-07

	CNCO244A - CNA contribution - TIF 118 - NECA company codes
	CNA
	2024-05-13

	CNCO248A - COMsolve contribution - TIF 118 - Draft paragraph 51 report
	COMsolve
	2024-05-15

	CNCO249A - Rogers/Bell/KRob Solutions contribution - TIF 118 - Recommendations on timeline and utilization for ordering numbering resources
	Rogers/Bell/KRob Solutions
	2024-05-28

	CNCO248B - Rogers\Bell\KRob Solutions contribution - TIF 118 - Draft paragraph 51 report
	Rogers/Bell/KRob Solutions
	2024-06-06

	CNCO252A - Cogeco contribution - TIF 118 - Sequential Numbering Assignment
	Cogeco
	2024-06-10

	CNCO248C - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	CSCN
	2024-06-12

	CNCO248D - TELUS contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	TELUS
	2024-06-17

	CNCO248E - Bell contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	Bell
	2024-06-17

	CNCO248F - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	CSCN
	2024-06-18

	CNCO248G - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	CSCN
	2024-06-20

	CNCO252B - Cogeco contribution - TIF 118 - Sequential Numbering Assignment
	Cogeco
	2024-06-21

	CNCO248H - CSCN contribution - TIF 118 - Draft report (NO MARKUP) for paragraph 51 from Telecom Regulatory Policy 2024-26
	CSCN
	2024-06-21

	CNCO248I - CSCN contribution - TIF 118 - Draft report for paragraph 51 from Telecom Regulatory Policy 2024-26
	CSCN
	2024-06-25

	CNCO258A - Bell Canada contribution - TIF 118 - Revisions to Recommendation 5 of Draft CNRE144A
	Bell
	2024-07-09

	CNCO258B - CNA contribution - TIF 118 - Revisions to Recommendation 5 of Draft CNRE144A
	CNA
	2024-07-09

	CNCO261A - COMsolve contribution - TIF 118 - Block Assignment Process
	COMsolve
	2024-08-15

	CNCO262C - Bell contribution - TIF 118 - Thousand Block Pooling Task List
	Bell
	2024-09-12

	CNCO262D - CSCN contribution - TIF 118 - Thousand Block Pooling Task List
	CSCN
	2024-09-16

	CNCO261B - COMsolve contribution - TIF 118 - Block Assignment Process
	COMsolve
	2024-09-19

	CNCO278B - CSCN contribution - TIF 118 - Proposed Part 1A form
	CSCN
	2024-12-17

	CNCO280A - COMsolve contribution - TIF 118 - Proposed Part 1B for use in Canada for 1K block assignments
	COMsolve
	2025-01-22

	CNCO281A - Rogers contribution - TIF 118 - TBP Critical Path Items
	Rogers
	2025-02-06

	CNCO282A - Bell Canada contribution - TIF 118 - Thousand Block Pooling (TBP) Bell Canada Assumptions
	Bell Canada
	2025-02-07

	CNCO283A - COMsolve contribution - TIF 118 - CNA Order Flow Diagram
	COMsolve
	2025-02-10

	CNCO278C - CSCN contribution - TIF 118 - Proposed Part 1A form
	CSCN
	2025-02-14

	CNCO298A - TIF 118 CDT contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F
	TIF 118 CDT
	2025-09-23

	CNCO298B - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F
	CSCN
	2025-10-20

	CNCO299A - TIF 118 CDT contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C
	TIF 118 CDT
	2025-09-23

	CNCO299B - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C
	CSCN
	2025-10-21

	CNCO299C - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix C
	CSCN
	2025-10-24

	CNCO302B - CNA contribution - TIF 118 - TBP updates to Appendix B of the CO Code Guideline
	CNA
	2025-10-20

	CNCO303A - COMsolve contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling
	COMsolve
	2025-10-02

	CNCO303B - CSCN contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling
	CSCN
	2025-10-20

	CNCO304A - COMsolve/CNA contribution - TIF 118 - Proposed Canadian TBCOCAG
	CNA/COMsolve
	2025-10-20

	CNCO305A - CNA contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP
	CNA
	2025-10-22

	CNCO305B - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP
	CSCN
	2025-10-24

	CNCO305C - KRob Solutions contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP
	Krob Solutions
	2025-10-29

	CNCO305D - CNA contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP
	CNA
	2025-10-29

	CNCO305E - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP
	CSCN
	2025-10-31

	CNCO308A - COMsolve contribution - TIF 118 - Discussion of TBCOCAG Section 4.2.3
	COMsolve
	2025-11-03

	CNCO311A - CSCN contribution - TIF 118 - Coversheet for TIF Report CNRE158A - Proposed Initial Canadian TBCOCAG – Version 1.0 (posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO304C - CSCN contribution - TIF 118 - Proposed Canadian TBCOCAG(posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO302C - CSCN contribution - TIF 118 - TBP updates to Appendix B of the CO Code Guideline(posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO303C - CSCN contribution - TIF 118 - Updated Appendix E for Thousands-Block Pooling(posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO298C - CSCN contribution - TIF 118 - Proposed changes to the CO Code Guideline Appendix F(posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO305F - CSCN contribution - TIF 118 - Proposed Confirmation of "Activation in the PSTN” (CAPSTN) Form for TBP(posted 2025-12-11)
	CSCN
	2025-12-11

	CNCO315A - CNA contribution - TIF 118 - Draft Part 1A for a Pooled CO Code or Block request
	CNA
	2026-02-03

	CNCO316A - CNA contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request
	CNA
	2026-02-03

	CNCO315B - CSCN contribution - TIF 118 - Draft Part 1A for a Pooled CO Code or Block request
	CSCN
	2026-02-12

	CNCO316B - CSCN contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request
	CSCN
	2026-02-12

	CNCO316C - CNA contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request
	CNA
	2026-02-24

	CNCO315C - CSCN contribution - TIF 118 - Draft Part 1A for a Pooled CO Code or Block request
	CSCN
	2026-07-28

	CNCO316D - CSCN contribution - TIF 118 - Draft Part 1B for a Pooled CO Code or Block request
	CSCN
	2026-07-30






[bookmark: _Toc224546930]TIF 119 - Report of inclusion of unused numbers from previously assigned CO Codes in pool
Consensus Report CNRE145A was sent to CISC on August 6th, 2024.
During CSCN 130, it was noted that there was no additional work required for TIF 119. Agreement was reached during the meeting to close TIF 119.
In Telecom Decision CRTC 2024-239, the Commission stated that with respect to the report on inclusion of unused numbers from previous assignments, they were open to the CSCN filing an extension request for a report if needed.
During the CSCN 131 meeting, participants discussed the possibility of revisiting donations of unused blocks from previously assigned codes after Thousand Block Pooling was implemented on October 6, 2025. The CSCN reached an agreement to change the status of TIF 119 to suspended and would re-open the TIF to address previously assigned codes once the Thousand Block Pooling implementation was completed.
During CSCN 135 on 10 June 2026, the group agreed to Suspend/Defer TIF 119.
[bookmark: _Toc224546931]TIF 120 - Report on LIR expansion or Exchange Area consolidation opportunities
There were no meetings for TIF 120 since the last TIF117 report submitted 30 December 2024.
During CSCN 135 on 10 June 2026, the group agreed to Suspend/Defer TIF 120.
There have been 4 contributions for TIF 120:
	Contribution Description
	Date posted

	CNCO264A - TELUS contribution - TIF 120 - Proposed criteria for Exchange Area consolidation
	2024-08-24

	CNCO264B – Bell contribution - TIF 120 - Proposed criteria for Exchange Area consolidation
	2024-10-16

	CNCO264C – CSCN contribution - TIF 120 - Proposed criteria for Exchange Area consolidation
	2024-10-17

	CNCO264D – Bell contribution - TIF 120 - Proposed criteria for Exchange Area consolidation
	2024-10-18


[bookmark: _Toc224546932]TIF 125 - TBP Controlled Production Rollout
This TIF was approved by the CSCN on 19 September 2025 and approved by the CISC on 29 September 2025. This TIF is used to coordinate the rollout implementation by way of various scheduling and planning documents.
The kick-off meeting for the first of six implementation phases was held on 24 March 2026. 
Meetings for the next 4 phases are currently scheduled as follows:
	Phase Order
	Phase Name
	Date

	3
	Phase 1B
	2026-10-14

	4
	Phase 2
	2026-11-25

	5
	Phase 3
	2027-02-24

	6
	Phase 4
	2027-04-29



The following TBP implementation planning documents have been approved for use by the CSCN under CSCN TIF 125. The documents are updated regularly and describe the overall plan to implement TBP in Canada in a selection of the most impactful Exchange Areas. The documents may be updated regularly by the CSCN as implementation work continues. The most current versions of these planning documents are provided with this report for information purposes to the CRTC.
· CNCO329A - TIF 125 - TBP Phase 1A Launch Implementation Plan (CSCN-approved 2026-09-02)
· CNCO312M - TIF 125 - TBP Canada Rollout Schedule (CSCN-approved 2026-06-10) 
· CNCO326D - TIF 125 - TBP Task Schedule for All Phases (CSCN-approved 2026-09-02) 
· CNCO318E - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges (CSCN-approved 2026-06-10)
· Sample Carrier Affirmation of TBP Readiness (3) Phase 1B(CSCN-approved 2026-05-12)
The most current versions of these documents are ‘published’ on the CNA website’s Thousands-Block Pooling (TBP) Implementation Page at the following URL:
· https://cnac.ca/co_codes/TBP/TBP_Implementation.htm 
The following contributions have been received by the CSCN for TIF 125:
	Contribution Description
	Date posted

	CNCO292A - Bell contribution - TIF 125 (Proposed) - TBP Trial Contribution
	2025-09-11

	CNCO292B - CSCN contribution - TIF 125 - TBP Trial Contribution
	2025-09-19

	CNCO292C - CSCN contribution - TIF 125 - TBP Trial Contribution
	2025-10-27

	CNCO292D - Bell contribution - TIF 125 - TBP Trial Contribution
	2025-10-29

	CNCO293A - CNA contribution - TIF 125 (Proposed) - TIF form for Proposed TIF 125
	2025-09-11

	CNCO294A - CNA contribution - TIF 125 (Proposed) - TIF report coversheet for Proposed TIF 125(
	2025-09-11

	CNCO294B - Bell contribution - TIF 125 - TIF report coversheet for Proposed TIF 125
	2025-09-26

	CNCO306A - CSCN contribution - TIF 125 - TBP Implementation Milestones
	2025-10-27

	CNCO307A - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years
	2025-10-28

	CNCO292D - Bell contribution - TIF 125 - TBP Trial Contribution
	2025-10-29

	CNCO312A - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-01-12

	CNCO313A - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years
	2026-01-12

	CNCO313B - CNA contribution - TIF 125 - Exchange Areas and Counts of OCNs, Codes and Codes Assigned in previous years
	2026-01-16

	CNCO312B - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-01-16

	CNCO312C - CSCN contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-01-16

	CNCO312D - Bell contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-02-06

	CNCO318A - CSCN contribution - TIF 125 - Steps for rolling out TBP in 1 or more Exchanges
	2026-02-12

	CNCO312E - CSCN contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-02-13

	CNCO319A - TIF 125 CDT contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form
	2026-02-18

	CNCO320A - TIF 125 CDT contribution - TIF 125 - TIF report for TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling
	2026-02-18

	CNCO312F - CNA contribution - TIF 125 - Proposed TBP Rollout Schedule
	2026-02-18

	CNCO319B - CSCN contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form
	2026-03-09

	CNRE160A - TIF 125 - Draft TIF Report - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling
	2026-03-09

	CNCO312G - Bell-CNA Contribution - TIF 125 - TBP Rollout Schedule 16 March 2026
	2026-03-17

	CNCO322A - Bell Canada Contribution - TIF 125 - TIF Report cover page for TBP rollout
	2026-03-17

	CNCO319C - Bell contribution - TIF 125 - Draft of Carrier Affirmation of Thousands-Block Pooling Readiness form
	2026-03-19

	CNRE160B - Bell contribution - TIF 125 - Draft TIF Report - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling
	2026-03-19

	CNCO323A - CSCN contribution - TIF 125 - TBP Phase 1-LaunchTrial Implementation Plan
	2026-03-26

	CNCO318B - CSCN contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges
	2026-03-26

	CNCO323B - CSCN Contribution - TIF 125 - TBP Phase 1-LaunchTrial Implementation Plan
	2026-03-26

	CNCO318C - CSCN Contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges
	2026-03-26

	CNCO319D - CSCN Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form
	2026-03-26

	DRAFT CNRE160C - TIF 125 - TBP Readiness Affirmation Form and Recommendations to Facilitate the Rollout of Thousands-Block Pooling
	2026-03-26

	CNCO312H - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-03-26

	DRAFT CNRE161A - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-03-26

	CNCO312I - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-04-23

	CNCO312J - Gosfield Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-04-30

	CNCO312K - CNA Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-05-04

	CNCO318D - CNA Contribution - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges
	2026-05-04

	CNCO319E - CNA Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form
	2026-05-04

	CNCO312L - CSCN Contribution - TIF 125 - Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada
	2026-05-13

	CNCO319F - CSCN Contribution - TIF 125 - Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form
	2026-05-13

	CNCO326A - CNA Contribution - TIF 125 - Task Schedule for all TBP Implementation Phases
	2026-05-27

	CNCO329A - TIF 125 - TBP Phase 1A Launch Implementation Plan
	2026-09-03

	CNCO326C - CSCN Contribution - TIF 125 - Task Schedule for all TBP Implementation Phases
	2026-09-03



[bookmark: _Toc224546933]TIF 126 - Update the Canadian TBCOCAG and Appendix A (Audits)
This TIF was approved by the CSCN 13 February 2026 and approved by the CISC on 31 July 2026.
During CSCN 135 on 10 June 2026, the group agreed to Suspend/Defer TIF 126.
The CSCN Chair has sent an extension request letter to the CRTC on 2 March 2026. The extension date requested was 26 March 2027.
	Contribution Description
	Date posted

	CNCO314A - Bell contribution - TIF 126 (Proposed) - TIF coversheet for proposed TIF 126 (Update to Appendix A of the Central Office Assignment Guidelines)
	2026-01-14

	CNTF126A - CSCN contribution - TIF 126 (Proposed) - Update to Appendix A of the Canadian TBCOCAG
	2026-01-22

	CNCO237B - CSCN contribution - TIF 126 - TBP implementation plan & milestones
	2026-01-29

	CNCO317A - CNA contribution - TIF 126 - Draft letter from CSCN Chair to the CRTC regarding updates to Appendix A of the CO Code
	2026-02-10

	CNCO317B - CSCN contribution - TIF 126 - Draft letter from CSCN Chair to the CRTC regarding updates to Appendix A of the CO Code
	2026-02-12





CNCO329A - TIF 125 - TBP Phase 1A Launch Implementation Plan (CSCN-approved 2026-09-02)


CNCO312M - TIF 125 - TBP Canada Rollout Schedule (CSCN-approved 2026-06-10) 



CNCO326D - TIF 125 - TBP Task Schedule for All Phases (CSCN-approved 2026-09-02) 



CNCO318E - TIF 125 - Template for Steps for rolling out TBP in 1 or more Exchanges (CSCN-approved 2026-06-10)



Sample Carrier Affirmation of TBP Readiness (3) Phase 1B(CSCN-approved 2026-05-12)


Lists of Operators and Exchanges included in each Phase
· 



· 

· 

· 

· 
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TBP Phase 1A Implementation Plan



1.0	Exchange Area Number Pooling Implementation Procedures - 2 September 2026



This contribution describes the responsibilities of the CNA and Carriers when Thousands-Block Pooling is to be implemented in one or more Exchange Areas in accordance with the implementation plan.



The decision to establish an Exchange Area Number Pool in any given location(s) shall be in accordance with a Thousands-Block implementation plan approved by the CSCN and filed with the CRTC.



2.0 Outline of Milestones



At least 3 months prior to the expected Implementation and Pool Start/Allocation Date for one or more Exchange Areas as set out in the approved Thousands-Block implementation plan, the CNA shall:



(i) provide a list of Carriers that have geographic numbering resources in the impacted Exchange Areas to the CSCN; 

(ii) schedule an initial CSCN meeting to discuss the implementation plan for rollout of TBP in the impacted Exchange Areas;

(iii) remind Carriers, using the CSCN distribution list, that Carriers operating in the impacted Exchange Areas must comply with paragraph 37 b of Telecom Decision CRTC 2025-321 which directs:

all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule

The meeting Chair shall present a proposed schedule of the implementation milestones which identifies the milestones that Carriers shall be required to meet in order to implement Thousands-Block Pooling by the Implementation plan date.



No later than 30 days after the initial implementation meeting (2 September 2026) for the Exchange Area(s), all Carriers operating in the geographic area where Thousands-Block Pooling is to be implemented must send a Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form to the Chair of the initial implementation meeting (CNA) that they are ready for Thousands-Block Pooling in the geographic area. If a Carrier is not ready they must provide a written reason and the date on which they will be ready, in which case, the date for implementation may be adjusted or restrictions may be placed on the Carriers that are not ready. 



Carriers that have not provided their affirmation of TBP readiness will not be eligible to receive or donate numbering resources in a Pooled Exchange Area until they have affirmed their readiness.



The CNA and participating Carriers determine the dates of the milestones in the proposed schedule.



The schedule is available on the CNA website here:  https://cnac.ca/co_codes/TBP/TBP_Implementation.htm#PhaseTaskSchedule 





2.1 Forecast Report Date – Not Applicable



(subject to implementation of near real-time aggregation of forecasts by CNA)



The Forecast Report Date is the deadline for Carriers to report their forecasted Thousands-Block demand to the CNA using a form equivalent to the current TBCOCAG Appendix 4.  This forecast shall be used by the CNA to establish the Exchange Area Number Pools and by Carriers to determine quantity of Thousands-Blocks to return.







2.2 Thousands-Block Protection and Block Donation/Return Identification Date 



Carriers shall identify all Thousands-Blocks that are to be donated/returned to the Exchange Area Number Pools.  These Thousands-Blocks must not exceed the Contamination threshold.



Carriers shall protect Thousands-Blocks to be returned from further Contamination as of the Thousands-Block Protection and Donation/Disconnect Identification Date. 





2.3	Thousands-Block Donation Due Date 



The interval between the Thousands-Block Protection and Donation/Disconnect Identification Date and the Thousands-Block Donation Due Date shall be determined by industry consensus. This time interval requires considerable verification work by Carriers so that all Available TNs are identified. Therefore, the length of the interval between the Thousands-Block Protection and Donation/Disconnect Identification Date and the Thousands-Block Donation Due Date should depend upon the quantity of contaminated Thousands-Blocks to be donated/returned. However, in no case shall the interval be less than 30 calendar days.



Carriers shall submit all Part 1A Thousands-Block disconnects to the CNA by the Thousands-Block Donation Due Date. 







2.4	CNA Assessment of Industry Inventory Surplus/Deficiency – Not Applicable



(subject to implementation of near real-time aggregation of forecasts by CNA)



For each Exchange Area Number Pooling implementation, the CNA shall evaluate whether there shall be enough Thousands-Blocks donated/returned to create an Exchange Area Number Pool with enough supply to meet the aggregate forecasted demand for TNs for 6 six months beyond the Implementation and Pool Start/Allocation Date.  If the CNA determines there shall be an insufficient supply to meet this demand, the CNA shall allow Carriers with a forecasted demand the option to apply for additional CO Codes.  



The CNA shall post the assessment of the Exchange Area Number Pool(s) to the CNA website for Carriers to view the results of the surplus/deficiency determination on the eighth calendar day after the Thousands-Block Disconnect Date.





2.5	 Implementation and Pool Start/Allocation Date



The Implementation and Pool Start/Allocation Date is the date the CNA may start allocating Thousands-Blocks from the Exchange Area Number Pool(s) to Carriers. This is also the start date for Carriers to send applications for Thousands-Blocks to the CNA.



The Implementation and Pool Start/Allocation Date may be as few as five business days following the Thousands-Block Donation Due Date: two calendar days are necessary to allow the NPAC download of ISP Ports to occur and two business days to allow the CNA to compile the necessary data; the additional three business days are for the initialization of the data in BIRRDS. The Pool Start/Allocation Date may also be established beyond five business days following the Thousands-Block Donation Due Date, depending on local circumstances.
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Plan for Phased Implementation of Thousand-Block Pooling (TBP) in Canada 



Background and Commission Direction

On 28 November 2025, the Canadian Radio-television and Telecommunications Commission (CRTC) issued Telecom Decision CRTC 2025-321, “Modification of deadline for thousand-block pooling.” At paragraph 37 of the Decision, the Commission made several key requests and directives as follows:

a) requests the CSCN to develop a schedule for the phased-in implementation of TBP, by exchange, taking into account CO code demand and TSP readiness, and file it for information with the Commission no later than 30 March 2026, with: 

i. the first exchange transitioning to TBP no later than 28 July 2026; and 

ii. the final exchange transitioning to TBP no later than 28 July 2027 

b) directs all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule; and

c) expects that all LECs and wireless carriers will continue to actively work towards TBP readiness as guided by the CSCN’s TBP checklist, as applicable.



Rollout Approach

In accordance with the Decision, we have developed a phased rollout schedule commencing with a trial in Brampton, Markam and Victoria on 28 July 2026 and concluding with the final Exchange Area on 28 July 2027. As indicated in the carriers’ submission dated 24 July 2025[footnoteRef:2], the carriers proposed an Exchange Area-based rollout that aligns with the phased approach successfully employed in the United States (U.S.). Consistent with the U.S. approach, which prioritized deployment in the Top 100 MSAs, we recommend an initial rollout encompassing the top 110 Canadian exchanges with highest demand for numbering resources according to the criteria detailed below. [2:  Carriers Intervention, Part 1 application by the independent telecommunications providers associations to delay the implementation of thousands-block pooling for small telecommunications service providers, 24 July 2025. 
] 




Selection Criteria and Phase-Gate Conditions

Exchange Areas chosen for the first year of the rollout are those with at least 12 NPA-NXXs ordered between 2015 and 2025, according to data from the Canadian Numbering Administrator (CNA) in contribution CNCO313A. This criterion ensures TBP is deployed where it will be most effective and aligns with the U.S. approach, which prioritises larger, high-demand exchanges during the initial deployment year.

To provide further context for the scope and rationale of the rollout, we note that Canada has 2,996 Exchange Areas. The rollout schedule includes 110 Exchange Areas, selected based on demonstrated demand for numbering resources and phased in accordance with the timelines set out in this contribution. This targeted approach focuses industry effort where TBP will deliver measurable benefits; implementing TBP across all exchanges at this time many of which show little to no demand-would not be a prudent use of resources and would impose costs on legacy systems for which no commensurate benefit would be realized. As demand matures in additional Exchange Areas such that TBP would realize tangible benefits, those exchanges can be added to the TBP program and opened consistent with the implementation milestones and phase-gate criteria set out herein. The industry will bring forward a follow-up submission with respect to the Exchange Areas not included in the initial rollout schedule, in advance of the date by which all Exchange Areas are expected to be TBP-ready under Telecom Decision CRTC 2025-321.



Launch Trial 

TBP will initially launch in 3 Exchange Areas (Markham, ON, Brampton, ON and Victoria, BC) on 28 July 2026 (see contribution CNCO292D.docx for details). The successful launch and evaluation of TBP in these Exchange Areas will serve as a foundation for expanding TBP to additional Exchange Areas, in phases, based on carrier readiness. The list of Exchange Areas included in the phased rollout plan is available on the CNA website here: https://cnac.ca/co_codes/TBP/TBP_Implementation.htm#PhaseTaskSchedule 

Obligations Applicable to All Carriers in Canada

LNP Query Readiness 

Regardless of which Exchange Areas are launching in this initial phase, all Carriers operating in Canada must be performing LNP queries on a TBP ready query database by the Launch Date of July 28, 2026. This may entail changing LNP query provider.  

Additional Requirements for Carriers in Pooled Exchange Areas

Carriers participating in a pooled Exchange Area are subject to further requirements beyond LNP query readiness (including successful production testing of TBP systems that enable block reservations and return).

Note: Exchange Areas involving entities with an ITPA presence are excluded until 28 July 2027. This exclusion is based on the list of ITPA members included in the ITPA Part 1 application submitted on 27 June 2025. 

Phased Rollout Timeline

Available on the CNA website here: https://cnac.ca/co_codes/TBP/TBP_Implementation.htm#PhaseTaskSchedule 



Phased Deployment Schedule for TBP Across Canadian Exchange Areas 



Available on the CNA website here: https://cnac.ca/co_codes/TBP/TBP_Implementation.htm#PhaseTaskSchedule 

The full Canadian Exchange Area listing may be found on the CNA Website at:
https://cnac.ca/reference_data/canadian_exchange_area_listing.htm, or https://cnac.ca/data/ExchangeAreaListing.csv


Phase-gate for subsequent launches. Progression to subsequent TBP rollout phases is contingent on the successful completion of the preceding phase, determined by the following criteria:

· Carrier affirmations to TBP readiness are complete, and all carriers were able to successfully conduct production-level testing[footnoteRef:3]. [3:  Pre-launch activities for any Exchange or group of Exchanges shall be as set out in CNCO237B to be amended and clarified.] 


· No major routing issues or adverse customer impacts are reported for a period of two months following the launch of TBP in an Exchange Area.

· No material evidence of a marked increase in dual assignment or issues with portability requests is observed.



Future Deployment 

Future deployment in additional exchanges beyond the rollout schedule should follow proposals and recommendations by the CSCN based on data provided by the CNA.



Conclusion

We submit that initiating TBP deployment in the Exchange Areas of Brampton, Markham and Victoria is the most pragmatic, least disruptive, and technically robust approach to begin TBP implementation in Canada. Subsequent phased rollouts (as per the schedule) will follow based on the lessons learned and data gathered from this initial deployment. This plan is designed to:

· Balance industry readiness by allowing larger carriers to advance while affording additional implementation time for smaller TSPs.

· Enable comprehensive carrier testing and identification of potential errors or misrouting.

· Produce actionable data for the CSCN and the Commission to inform and enhance future rollout phases.

· Support number conservation objectives effectively.
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All Phases

		Phase Order		Phase Name		Description		Date		DoW

		1		Phase 1-Launch Trial		Launch Trial kickoff meeting 		2026-03-24		Tuesday

		1		Phase 1-Launch Trial		Deadline for Affirmation forms 		2026-04-23		Thursday

		1		Phase 1-Launch Trial		Notice of Intent to Donate Blocks		2026-05-21		Thursday

		1		Phase 1-Launch Trial		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-06-04		Thursday

		1		Phase 1-Launch Trial		3-Exchange Area Launch trial.
		2026-07-28		Tuesday

		2		Phase 1A		Phase kickoff meeting 		2026-09-02		Wednesday

		2		Phase 1A		Deadline for Affirmation forms 		2026-10-02		Friday

		2		Phase 1A		Notice of Intent to Donate Blocks		2026-09-24		Thursday

		2		Phase 1A		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-10-08		Thursday

		2		Phase 1A		CNA send correspondence with due date to return testing resources		2026-11-03		Tuesday

		2		Phase 1A		Due date to return testing resources		2026-11-17		Tuesday

		2		Phase 1A		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2026-11-30		Monday

		2		Phase 1A		CNA recover any unreturned resources
		2026-11-30		Monday

		2		Phase 1A		Launch Exchange Areas within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories.
		2026-12-01		Tuesday

		3		Phase 1B		Phase kickoff meeting 		2026-10-14		Wednesday

		3		Phase 1B		Notice of Intent to Donate Blocks		2026-11-05		Thursday

		3		Phase 1B		Deadline for Affirmation forms 		2026-11-13		Friday

		3		Phase 1B		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-11-19		Thursday

		3		Phase 1B		CNA send correspondence with due date to return testing resources		2026-12-15		Tuesday

		3		Phase 1B		Due date to return testing resources		2026-12-29		Tuesday

		3		Phase 1B		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-01-11		Monday

		3		Phase 1B		CNA recover any unreturned resources
		2027-01-11		Monday

		3		Phase 1B		Continue rollout in the same regions.
		2027-01-12		Tuesday

		4		Phase 2		Phase kickoff meeting 		2026-11-25		Wednesday

		4		Phase 2		Notice of Intent to Donate Blocks		2026-12-17		Thursday

		4		Phase 2		Deadline for Affirmation forms 		2026-12-25		Friday

		4		Phase 2		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-12-31		Thursday

		4		Phase 2		CNA send correspondence with due date to return testing resources		2027-01-26		Tuesday

		4		Phase 2		Due date to return testing resources		2027-02-09		Tuesday

		4		Phase 2		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-02-22		Monday

		4		Phase 2		CNA recover any unreturned resources
		2027-02-22		Monday

		4		Phase 2		Launch Exchange Areas in Alberta and Quebec.		2027-02-23		Tuesday

		5		Phase 3		Phase kickoff meeting 		2027-02-24		Wednesday

		5		Phase 3		Notice of Intent to Donate Blocks		2027-03-18		Thursday

		5		Phase 3		Deadline for Affirmation forms 		2027-03-26		Friday

		5		Phase 3		Date for Donation Submission for Initial Pool
(Part 1A submission)		2027-04-01		Thursday

		5		Phase 3		CNA send correspondence with due date to return testing resources		2027-04-27		Tuesday

		5		Phase 3		Due date to return testing resources		2027-05-11		Tuesday

		5		Phase 3		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-05-24		Monday

		5		Phase 3		CNA recover any unreturned resources
		2027-05-24		Monday

		5		Phase 3		Launch Exchange Areas in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories.		2027-05-25		Tuesday

		6		Phase 4		Phase kickoff meeting 		2027-04-29		Thursday

		6		Phase 4		Notice of Intent to Donate Blocks		2027-05-21		Friday

		6		Phase 4		Deadline for Affirmation forms 		2027-05-29		Saturday

		6		Phase 4		Date for Donation Submission for Initial Pool
(Part 1A submission)		2027-06-04		Friday

		6		Phase 4		CNA send correspondence with due date to return testing resources		2027-06-30		Wednesday

		6		Phase 4		Due date to return testing resources		2027-07-14		Wednesday

		6		Phase 4		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-07-27		Tuesday

		6		Phase 4		CNA recover any unreturned resources
		2027-07-27		Tuesday

		6		Phase 4		Include Exchange Areas with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases. 		2027-07-28		Wednesday





Chronological Phase Dates

		Phase Order		Phase Name		Description		Date

		1		Phase 1-Launch Trial		Launch Trial kickoff meeting 		2026-03-24

		1		Phase 1-Launch Trial		Deadline for Affirmation forms 		2026-04-23

		1		Phase 1-Launch Trial		Notice of Intent to Donate Blocks		2026-05-21

		1		Phase 1-Launch Trial		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-06-04

		1		Phase 1-Launch Trial		3-Exchange Area Launch trial.
		2026-07-28

		2		Phase 1A		Phase kickoff meeting 		2026-09-02

		2		Phase 1A		Notice of Intent to Donate Blocks		2026-09-24

		2		Phase 1A		Deadline for Affirmation forms 		2026-10-02

		2		Phase 1A		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-10-08

		3		Phase 1B		Phase kickoff meeting 		2026-10-14

		2		Phase 1A		CNA send correspondence with due date to return testing resources		2026-11-03

		3		Phase 1B		Notice of Intent to Donate Blocks		2026-11-05

		3		Phase 1B		Deadline for Affirmation forms 		2026-11-13

		2		Phase 1A		Due date to return testing resources		2026-11-17

		3		Phase 1B		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-11-19

		4		Phase 2		Phase kickoff meeting 		2026-11-25

		2		Phase 1A		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2026-11-30

		2		Phase 1A		CNA recover any unreturned resources
		2026-11-30

		2		Phase 1A		Launch Exchange Areas within the two most populous provinces in the two largest Incumbent Local Exchange Carrier (ILEC) territories.
		2026-12-01

		3		Phase 1B		CNA send correspondence with due date to return testing resources		2026-12-15

		4		Phase 2		Notice of Intent to Donate Blocks		2026-12-17

		4		Phase 2		Deadline for Affirmation forms 		2026-12-25

		3		Phase 1B		Due date to return testing resources		2026-12-29

		4		Phase 2		Date for Donation Submission for Initial Pool
(Part 1A submission)		2026-12-31

		3		Phase 1B		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-01-11

		3		Phase 1B		CNA recover any unreturned resources
		2027-01-11

		3		Phase 1B		Continue rollout in the same regions.
		2027-01-12

		4		Phase 2		CNA send correspondence with due date to return testing resources		2027-01-26

		4		Phase 2		Due date to return testing resources		2027-02-09

		4		Phase 2		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-02-22

		4		Phase 2		CNA recover any unreturned resources
		2027-02-22

		4		Phase 2		Launch Exchange Areas in Alberta and Quebec.		2027-02-23

		5		Phase 3		Phase kickoff meeting 		2027-02-24

		5		Phase 3		Notice of Intent to Donate Blocks		2027-03-18

		5		Phase 3		Deadline for Affirmation forms 		2027-03-26

		5		Phase 3		Date for Donation Submission for Initial Pool
(Part 1A submission)		2027-04-01

		5		Phase 3		CNA send correspondence with due date to return testing resources		2027-04-27

		6		Phase 4		Phase kickoff meeting 		2027-04-29

		5		Phase 3		Due date to return testing resources		2027-05-11

		6		Phase 4		Notice of Intent to Donate Blocks		2027-05-21

		5		Phase 3		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-05-24

		5		Phase 3		CNA recover any unreturned resources
		2027-05-24

		5		Phase 3		Launch Exchange Areas in the Atlantic provinces, Manitoba, Saskatchewan, Yukon, and the Northwest Territories.		2027-05-25

		6		Phase 4		Deadline for Affirmation forms 		2027-05-29

		6		Phase 4		Date for Donation Submission for Initial Pool
(Part 1A submission)		2027-06-04

		6		Phase 4		CNA send correspondence with due date to return testing resources		2027-06-30

		6		Phase 4		Due date to return testing resources		2027-07-14

		6		Phase 4		CNA coordinate clean-up of phase testing resources in NPAC with NPAC Help Desk		2027-07-27

		6		Phase 4		CNA recover any unreturned resources
		2027-07-27

		6		Phase 4		Include Exchange Areas with an Independent Telecommunications Providers Association (ITPA) presence, i.e., those excluded from prior phases. 		2027-07-28





Exchanges

		Phase Order		Phase Name		Exchange Area
(CNAS)		Rate Center
(BIRRDS)		Province
(Canada Post)		Phase Implementation Date

		1		1-LaunchTrial		Brampton		BRAMPTON		ON		2026-07-28

		1		1-LaunchTrial		Markham		MARKHAM		ON		2026-07-28

		1		1-LaunchTrial		Victoria		VICTORIA		BC		2026-07-28

		2		1A		100 Mile House		100 MILE HOUSE		BC		2026-12-01

		2		1A		Abbotsford		ABBOTSFORD		BC		2026-12-01

		2		1A		Ajax-Pickering		AJAX-PICKERING		ON		2026-12-01

		2		1A		Aldergrove		ALDERGROVE		BC		2026-12-01

		2		1A		Alliston		ALLISTON		ON		2026-12-01

		2		1A		Aurora		AURORA		ON		2026-12-01

		2		1A		Barrie		BARRIE		ON		2026-12-01

		2		1A		Brockville		BROCKVILLE		ON		2026-12-01

		2		1A		Chilliwack		CHILLIWACK		BC		2026-12-01

		2		1A		Claremont		CLAREMONT		ON		2026-12-01

		2		1A		Collingwood		COLLINGWOOD		ON		2026-12-01

		2		1A		Cooksville		COOKSVILLE		ON		2026-12-01

		2		1A		Cranbrook		CRANBROOK		BC		2026-12-01

		2		1A		Huntsville		HUNTSVILLE		ON		2026-12-01

		2		1A		Kanata-Stittsville		KANATA STITTSVILLE		ON		2026-12-01

		2		1A		Kelowna		KELOWNA		BC		2026-12-01

		2		1A		Maple		MAPLE		ON		2026-12-01

		2		1A		Milton		MILTON		ON		2026-12-01

		2		1A		Nanaimo		NANAIMO		BC		2026-12-01

		2		1A		New Westminster		NEW WESTMINSTER		BC		2026-12-01

		2		1A		Newmarket		NEWMARKET		ON		2026-12-01

		2		1A		Niagara Falls		NIAGARA FALLS		ON		2026-12-01

		2		1A		North Vancouver		NORTH VANCOUVER		BC		2026-12-01

		2		1A		Oakville		OAKVILLE		ON		2026-12-01

		2		1A		Oshawa		OSHAWA		ON		2026-12-01

		2		1A		Prince George		PRINCE GEORGE		BC		2026-12-01

		2		1A		Richmond		RICHMOND		BC		2026-12-01

		2		1A		Richmond Hill		RICHMOND HILL		ON		2026-12-01

		2		1A		Sault Ste. Marie		SAULT SAINTE MARIE		ON		2026-12-01

		2		1A		South Kamloops		SOUTH KAMLOOPS		BC		2026-12-01

		2		1A		St. Catharines-Thorold		SAINT CATHARINES THOROLD		ON		2026-12-01

		2		1A		Streetsville		STREETSVILLE		ON		2026-12-01

		2		1A		Sudbury		SUDBURY		ON		2026-12-01

		2		1A		Thornhill		THORNHILL		ON		2026-12-01

		2		1A		West Vancouver		WEST VANCOUVER		BC		2026-12-01

		3		1B		Ottawa-Hull		OTTAWA-HULL		ON		2027-01-12

		3		1B		Toronto		TORONTO		ON		2027-01-12

		3		1B		Vancouver		VANCOUVER		BC		2027-01-12

		4		2		Alma		ALMA		QC		2027-02-23

		4		2		Banff		BANFF		AB		2027-02-23

		4		2		Calgary		CALGARY		AB		2027-02-23

		4		2		Chicoutimi		CHICOUTIMI		QC		2027-02-23

		4		2		Edmonton		EDMONTON		AB		2027-02-23

		4		2		Fort McMurray		FORT MCMURRAY		AB		2027-02-23

		4		2		Fox Creek		FOX CREEK		AB		2027-02-23

		4		2		Gatineau		GATINEAU		QC		2027-02-23

		4		2		Grande Prairie		GRANDE PRAIRIE		AB		2027-02-23

		4		2		High River		HIGH RIVER		AB		2027-02-23

		4		2		Lethbridge		LETHBRIDGE		AB		2027-02-23

		4		2		Maniwaki		MANIWAKI		QC		2027-02-23

		4		2		Medicine Hat		MEDICINE HAT		AB		2027-02-23

		4		2		Ottawa-Hull		OTTAWA-HULL		QC		2027-02-23

		4		2		Peace River		PEACE RIVER		AB		2027-02-23

		4		2		Pointe-Claire		POINTE-CLAIRE		QC		2027-02-23

		4		2		Quebec		QUEBEC		QC		2027-02-23

		4		2		Red Deer		RED DEER		AB		2027-02-23

		4		2		St-Jerome		SAINT-JEROME		QC		2027-02-23

		4		2		Ste-Genevieve		SAINTE-GENEVIEVE		QC		2027-02-23

		4		2		Valleyfield		VALLEYFIELD		QC		2027-02-23

		5		3		Amherst		AMHERST		NS		2027-05-25

		5		3		Bathurst		BATHURST		NB		2027-05-25

		5		3		Charlottetown		CHARLOTTETOWN		PE		2027-05-25

		5		3		Fredericton		FREDERICTON		NB		2027-05-25

		5		3		Halifax		HALIFAX		NS		2027-05-25

		5		3		Miramichi		MIRAMICHI		NB		2027-05-25

		5		3		Moncton		MONCTON		NB		2027-05-25

		5		3		Moose Jaw		MOOSE JAW		SK		2027-05-25

		5		3		Oakbank		OAKBANK		MB		2027-05-25

		5		3		Portage La Prairie		PORTAGE LA PRAIRIE		MB		2027-05-25

		5		3		Regina		REGINA		SK		2027-05-25

		5		3		Saint John		SAINT JOHN		NB		2027-05-25

		5		3		Saskatoon		SASKATOON		SK		2027-05-25

		5		3		St. John's		SAINT JOHNS		NL		2027-05-25

		5		3		Sydney		SYDNEY		NS		2027-05-25

		5		3		Truro		TRURO		NS		2027-05-25

		5		3		Whitehorse		WHITEHORSE		YT		2027-05-25

		5		3		Windsor		WINDSOR		NS		2027-05-25

		5		3		Winnipeg		WINNIPEG		MB		2027-05-25

		5		3		Yellowknife		YELLOWKNIFE		NT		2027-05-25

		6		4		Belleville		BELLEVILLE		ON		2027-07-28

		6		4		Brantford		BRANTFORD		ON		2027-07-28

		6		4		Burlington		BURLINGTON		ON		2027-07-28

		6		4		Chatham		CHATHAM		ON		2027-07-28

		6		4		Cornwall		CORNWALL		ON		2027-07-28

		6		4		Drummondville		DRUMMONDVILLE		QC		2027-07-28

		6		4		Essex		ESSEX		ON		2027-07-28

		6		4		Granby		GRANBY		QC		2027-07-28

		6		4		Guelph		GUELPH		ON		2027-07-28

		6		4		Hamilton		HAMILTON		ON		2027-07-28

		6		4		Joliette		JOLIETTE		QC		2027-07-28

		6		4		Kingston		KINGSTON		ON		2027-07-28

		6		4		Kitchener-Waterloo		KITCHENER-WATERLOO		ON		2027-07-28

		6		4		Leamington		LEAMINGTON		ON		2027-07-28

		6		4		Lindsay		LINDSAY		ON		2027-07-28

		6		4		Listowel		LISTOWEL		ON		2027-07-28

		6		4		London		LONDON		ON		2027-07-28

		6		4		Montreal		MONTREAL		QC		2027-07-28

		6		4		Peterborough		PETERBOROUGH		ON		2027-07-28

		6		4		Sarnia		SARNIA		ON		2027-07-28

		6		4		Sherbrooke		SHERBROOKE		QC		2027-07-28

		6		4		Sorel		SOREL		QC		2027-07-28

		6		4		St-Hyacinthe		SAINT-HYACINTHE		QC		2027-07-28

		6		4		Thunder Bay		THUNDER BAY		ON		2027-07-28

		6		4		Trois-Rivieres		TROIS-RIVIERES		QC		2027-07-28

		6		4		Victoriaville		VICTORIAVILLE		QC		2027-07-28

		6		4		Windsor		WINDSOR		ON		2027-07-28

		6		4		Woodstock		WOODSTOCK		ON		2027-07-28
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1.0	Exchange Area Number Pooling Implementation Procedures - Date of Meeting



This contribution describes the responsibilities of the CNA and Carriers when Thousands-Block Pooling is to be implemented in one or more Exchange Areas in accordance with the implementation plan.



The decision to establish an Exchange Area Number Pool in any given location(s) shall be in accordance with a Thousands-Block implementation plan approved by the CSCN and filed with the CRTC.



2.0 Outline of Milestones



At least 3 months prior to the expected Implementation and Pool Start/Allocation Date for one or more Exchange Areas as set out in the approved Thousands-Block implementation plan, the CNA shall:



(i) provide a list of Carriers that have geographic numbering resources in the impacted Exchange Areas to the CSCN; 

(ii) schedule an initial CSCN meeting to discuss the implementation plan for rollout of TBP in the impacted Exchange Areas;

(iii) remind Carriers, using the CSCN distribution list, that Carriers operating in the impacted Exchange Areas must comply with paragraph 37 b of Telecom Decision CRTC 2025-321 which directs:

all LECs and wireless carriers to actively participate in developing the exchange implementation timeline under the leadership of the CSCN, either individually or through consolidated groups with shared representation, and complete the implementation of TBP as detailed in the CSCN schedule

The meeting Chair shall present a proposed schedule of the implementation milestones which identifies the milestones that Carriers shall be required to meet in order to implement Thousands-Block Pooling by the Implementation plan date.



No later than 30 days after the initial implementation meeting (<date of meeting>) for the Exchange Area(s), all Carriers operating in the geographic area where Thousands-Block Pooling is to be implemented must send a Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness form to the Chair of the initial implementation meeting (CNA) that they are ready for Thousands-Block Pooling in the geographic area. If a Carrier is not ready they must provide a written reason and the date on which they will be ready, in which case, the date for implementation may be adjusted or restrictions may be placed on the Carriers that are not ready. 



Carriers that have not provided their affirmation of TBP readiness will not be eligible to receive or donate numbering resources in a Pooled Exchange Area until they have affirmed their readiness.



The CNA and participating Carriers determine the dates of the milestones in the proposed schedule.



The schedule is available on the CNA website here:  https://cnac.ca/co_codes/TBP/TBP_Implementation.htm#PhaseTaskSchedule 





2.1 Forecast Report Date



(subject to implementation of near real-time aggregation of forecasts by CNA)



The Forecast Report Date is the deadline for Carriers to report their forecasted Thousands-Block demand to the CNA using a form equivalent to the current TBCOCAG Appendix 4.  This forecast shall be used by the CNA to establish the Exchange Area Number Pools and by Carriers to determine quantity of Thousands-Blocks to return.







2.2 Thousands-Block Protection and Block Donation/Return Identification Date 



Carriers shall identify all Thousands-Blocks that to be donated/returned to the Exchange Area Number Pools.  These Thousands-Blocks must not exceed the Contamination threshold.



Carriers shall protect Thousands-Blocks to be returned from further Contamination as of the Thousands-Block Protection and Donation/Disconnect Identification Date. 





2.3	Thousands-Block Donation Due Date 



The interval between the Thousands-Block Protection and Donation/Disconnect Identification Date and the Thousands-Block Donation Due Date shall be determined by industry consensus. This time interval requires considerable verification work by Carriers so that all Available TNs are identified. Therefore, the length of the interval between the Thousands-Block Protection and Donation/Disconnect Identification Date and the Thousands-Block Donation Due Date should depend upon the quantity of contaminated Thousands-Blocks to be donated/returned. However, in no case shall the interval be less than 30 calendar days.



Carriers shall submit all Part 1A Thousands-Block disconnects to the CNA by the Thousands-Block Donation Due Date. 







2.4	CNA Assessment of Industry Inventory Surplus/Deficiency



(subject to implementation of near real-time aggregation of forecasts by CNA)



For each Exchange Area Number Pooling implementation, the CNA shall evaluate whether there shall be enough Thousands-Blocks donated/returned to create an Exchange Area Number Pool with enough supply to meet the aggregate forecasted demand for TNs for 6 six months beyond the Implementation and Pool Start/Allocation Date.  If the CNA determines there shall be an insufficient supply to meet this demand, the CNA shall allow Carriers with a forecasted demand the option to apply for additional CO Codes.  



The CNA shall post the assessment of the Exchange Area Number Pool(s) to the CNA website for Carriers to view the results of the surplus/deficiency determination on the eighth calendar day after the Thousands-Block Disconnect Date.





2.5	 Implementation and Pool Start/Allocation Date



The Implementation and Pool Start/Allocation Date is the date the CNA may start allocating Thousands-Blocks from the Exchange Area Number Pool(s) to Carriers. This is also the start date for Carriers to send applications for Thousands-Blocks to the CNA.



The Implementation and Pool Start/Allocation Date may be as few as five business days following the Thousands-Block Donation Due Date: two calendar days are necessary to allow the NPAC download of ISP Ports to occur and two business days to allow the CNA to compile the necessary data;  the additional three  business days are for the initialization of the data in BIRRDS. The Pool Start/Allocation Date may also be established beyond five business days following the Thousands-Block Donation Due Date, depending on local circumstances.

160
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Version 2, Dated 2026-05-13

Carrier Affirmation of Thousands-Block Pooling (TBP) Readiness 

TBP Implementation Phase:   (3) Phase 1B
Send to:   Secretary-CSCN@cnac.ca 

This form is to be completed prior to the launch of each of the 6 Phases in the Rollout Plan within 30 days of the Initial Implementation Meeting for each phase. 

Carriers that have not provided their affirmation of TBP readiness and are not fully prepared for TBP (both LNP queries and Inventory Management Systems) will not be eligible to receive or donate numbering resources in a Pooled Exchange Area until they have affirmed their full readiness.

The following form is to state the level of TBP preparedness of the Company below.

Table 1 – Company Information

		Company Name:



		



		Authorized Representative Name:



		



		Authorized Representative Email: 



		



		Authorized Representative Phone #: 



		



		Date of Affirmation (YYYY-MM-DD):

		







In Table 2 (below), the Company affirms that they have performed sufficient production level testing to confirm that their:

1. Inventory and porting systems can process Local Number Portability (LNP) Telephone Number (TN) disconnect notifications (i.e., Snapbacks) correctly in a TBP environment such that double TN assignments can be avoided;

1. intake into inventory of a contaminated Thousands-Block assigned by the CNA will avoid placing ported TNs into inventory, thereby causing double TN assignments; 

1. inventory systems can handle the donation/return of Thousands-Blocks; and

1. LNP database queries are performed on a database configured to receive Thousands-Block records.

The OCNs in Table 2 are fully ready for Thousands-Block Pooling (both Inventory Management System AND LNP queries) for the Exchange Areas included in this phase (1 OCN per row):

Table 2 – OCNs are Fully Ready

		#

		OCN



		1

		



		2

		



		3

		



		4

		



		5

		



		6

		



		7

		



		8

		



		9

		



		10

		





Add more rows as needed.



The OCNs in Table 3 are partially ready for TBP (Inventory Management System OR LNP queries) for the Exchange Areas included in this phase:

(Please select the item that is ready for each applicable OCN)

Table 3 – OCNs are Partially Ready

		#

		OCN

		LNP Queries are ready

		Inventory Management System is ready

		Comments



		1

		

		☐

		☐

		



		2

		

		☐

		☐

		



		3

		

		☐

		☐

		



		4

		

		☐

		☐

		



		5

		

		☐

		☐

		



		6

		

		☐

		☐

		



		7

		

		☐

		☐

		



		8

		

		☐

		☐

		



		9

		

		☐

		☐

		



		10

		

		☐

		☐

		







The OCNs in Table 4 are not ready for TBP (LNP queries AND Inventory Management System) for the Exchange Areas included in this phase:

Table 4 – OCNs are Not Ready

		#

		OCN

		Comments



		1

		

		



		2

		

		



		3

		

		



		4

		

		



		5

		

		



		6

		

		



		7

		

		



		8

		

		



		9

		

		



		10

		

		





Add more rows as needed.
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(1)_TBP_Phase_1-LaunchTrial-Operators_and_Exchanges_2026-09-01.xlsx
Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		1-LaunchTrial		575G		Beanfield Technologies Inc. (575G)		2

		1-LaunchTrial		8051		Bell Canada (8051)		34

		1-LaunchTrial		6574		Bell Mobility (6574)		23

		1-LaunchTrial		2933		Bell West Inc. (2933)		4

		1-LaunchTrial		221K		Cogeco Connexion Inc. (221K)                      		1

		1-LaunchTrial		160G		Comwave Networks (160G)		3

		1-LaunchTrial		081E		Distributel (081E)		5

		1-LaunchTrial		082E		Distributel (082E)		6

		1-LaunchTrial		3147		ExaTEL Inc. (3147)		1

		1-LaunchTrial		139J		FGLTEL Inc. (139J)		2

		1-LaunchTrial		464D		Fibernetics Corporation (464D)		14

		1-LaunchTrial		5643		Fido Solutions Inc. (5643)		13

		1-LaunchTrial		8506		GT Group Telecom Services Corp. (8506)		3

		1-LaunchTrial		383H		InnSysVoice Corp (383H)		3

		1-LaunchTrial		154E		Iristel Inc (154E)		76

		1-LaunchTrial		4727		ISP Telecom Inc. (4727)		3

		1-LaunchTrial		812H		IXICA Communications Inc. (812H)		5

		1-LaunchTrial		201A		Primus Telecommunications Canada Inc. (201A)		3

		1-LaunchTrial		571G		Rogers Communications Canada Inc. (571G)		1

		1-LaunchTrial		743B		Rogers Communications Canada Inc. (Cable-743B)		10

		1-LaunchTrial		8377		Rogers Communications Canada Inc. (Cable-8377)		10

		1-LaunchTrial		8821		Rogers Communications Canada Inc. (Wireless-8821)		21

		1-LaunchTrial		497E		Shaw Telecom Inc [Rogers taking] (497E)		10

		1-LaunchTrial		548H		TekSavvy Solutions Inc (548H)		2

		1-LaunchTrial		8086		TELUS (8086)		54

		1-LaunchTrial		2782		TELUS Integrated Communications (2782)		8

		1-LaunchTrial		646F		TELUS Mobility (646F)		1

		1-LaunchTrial		8301		TELUS Mobility (8301)		21

		1-LaunchTrial		8303		TELUS Mobility (8303)		8

		1-LaunchTrial		328F		Videotron Ltd. (328F)		2

		1-LaunchTrial		383F		Videotron Ltd. dba Freedom (383F)		7

		1-LaunchTrial		787G		Videotron Ltd. dba Freedom (787G)		3

		1-LaunchTrial		8304		Zayo Canada Inc. (8304)		8





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		1		1-LaunchTrial		Victoria		VICTORIA		BC

		1		1-LaunchTrial		Brampton		BRAMPTON		ON

		1		1-LaunchTrial		Markham		MARKHAM		ON
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(2)_TBP_Phase_1A-Operators_and_Exchanges_2026-09-01.xlsx
Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		1A		575G		Beanfield Technologies Inc. (575G)		10

		1A		709G		Bell Aliant, a division of Bell Canada (709G)		2

		1A		8051		Bell Canada (8051)		288

		1A		6574		Bell Mobility (6574)		141

		1A		2933		Bell West Inc. (2933)		21

		1A		421G		Bragg Communications Inc (421G)		2

		1A		4878		Bragg Communications Inc. (4878)		4

		1A		221K		Cogeco Connexion Inc. (221K)                      		7

		1A		160G		Comwave Networks (160G)		28

		1A		081E		Distributel (081E)		18

		1A		082E		Distributel (082E)		45

		1A		3147		ExaTEL Inc. (3147)		7

		1A		139J		FGLTEL Inc. (139J)		8

		1A		464D		Fibernetics Corporation (464D)		90

		1A		5643		Fido Solutions Inc. (5643)		71

		1A		8820		Fido Solutions Inc. (8820)		1

		1A		8506		GT Group Telecom Services Corp. (8506)		5

		1A		383H		InnSysVoice Corp (383H)		17

		1A		154E		Iristel Inc (154E)		254

		1A		4727		ISP Telecom Inc. (4727)		32

		1A		812H		IXICA Communications Inc. (812H)		41

		1A		078G		Navigata Communications Limited (078G)		4

		1A		201A		Primus Telecommunications Canada Inc. (201A)		17

		1A		571G		Rogers Communications Canada Inc. (571G)		10

		1A		743B		Rogers Communications Canada Inc. (Cable-743B)		45

		1A		8377		Rogers Communications Canada Inc. (Cable-8377)		45

		1A		8821		Rogers Communications Canada Inc. (Wireless-8821)		192

		1A		497E		Shaw Telecom Inc [Rogers taking] (497E)		49

		1A		548H		TekSavvy Solutions Inc (548H)		15

		1A		8086		TELUS (8086)		180

		1A		2782		TELUS Integrated Communications (2782)		62

		1A		646F		TELUS Mobility (646F)		7

		1A		8301		TELUS Mobility (8301)		104

		1A		8303		TELUS Mobility (8303)		90

		1A		328F		Videotron Ltd. (328F)		13

		1A		8306		Videotron Ltd. (8306)		1

		1A		383F		Videotron Ltd. dba Freedom (383F)		27

		1A		787G		Videotron Ltd. dba Freedom (787G)		7

		1A		8304		Zayo Canada Inc. (8304)		38





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		2		1A		100 Mile House		100 MILE HOUSE		BC

		2		1A		Abbotsford		ABBOTSFORD		BC

		2		1A		Aldergrove		ALDERGROVE		BC

		2		1A		Chilliwack		CHILLIWACK		BC

		2		1A		Cranbrook		CRANBROOK		BC

		2		1A		Kelowna		KELOWNA		BC

		2		1A		Nanaimo		NANAIMO		BC

		2		1A		New Westminster		NEW WESTMINSTER		BC

		2		1A		North Vancouver		NORTH VANCOUVER		BC

		2		1A		Prince George		PRINCE GEORGE		BC

		2		1A		Richmond		RICHMOND		BC

		2		1A		South Kamloops		SOUTH KAMLOOPS		BC

		2		1A		West Vancouver		WEST VANCOUVER		BC

		2		1A		Ajax-Pickering		AJAX-PICKERING		ON

		2		1A		Alliston		ALLISTON		ON

		2		1A		Aurora		AURORA		ON

		2		1A		Barrie		BARRIE		ON

		2		1A		Brockville		BROCKVILLE		ON

		2		1A		Claremont		CLAREMONT		ON

		2		1A		Collingwood		COLLINGWOOD		ON

		2		1A		Cooksville		COOKSVILLE		ON

		2		1A		Huntsville		HUNTSVILLE		ON

		2		1A		Kanata-Stittsville		KANATA STITTSVILLE		ON

		2		1A		Maple		MAPLE		ON

		2		1A		Milton		MILTON		ON

		2		1A		Newmarket		NEWMARKET		ON

		2		1A		Niagara Falls		NIAGARA FALLS		ON

		2		1A		Oakville		OAKVILLE		ON

		2		1A		Oshawa		OSHAWA		ON

		2		1A		Richmond Hill		RICHMOND HILL		ON

		2		1A		Sault Ste. Marie		SAULT SAINTE MARIE		ON

		2		1A		St. Catharines-Thorold		SAINT CATHARINES THOROLD		ON

		2		1A		Streetsville		STREETSVILLE		ON

		2		1A		Sudbury		SUDBURY		ON

		2		1A		Thornhill		THORNHILL		ON
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Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		1B		575G		Beanfield Technologies Inc. (575G)		2

		1B		8051		Bell Canada (8051)		598

		1B		6574		Bell Mobility (6574)		523

		1B		2933		Bell West Inc. (2933)		9

		1B		4878		Bragg Communications Inc. (4878)		1

		1B		221K		Cogeco Connexion Inc. (221K)                      		2

		1B		160G		Comwave Networks (160G)		6

		1B		081E		Distributel (081E)		12

		1B		082E		Distributel (082E)		39

		1B		3147		ExaTEL Inc. (3147)		2

		1B		139J		FGLTEL Inc. (139J)		1

		1B		464D		Fibernetics Corporation (464D)		50

		1B		5643		Fido Solutions Inc. (5643)		227

		1B		8506		GT Group Telecom Services Corp. (8506)		7

		1B		383H		InnSysVoice Corp (383H)		5

		1B		154E		Iristel Inc (154E)		184

		1B		346J		Iristel Inc (346J)		11

		1B		4727		ISP Telecom Inc. (4727)		23

		1B		812H		IXICA Communications Inc. (812H)		24

		1B		2776		Managed Network Systems Inc. (2776)		1

		1B		201A		Primus Telecommunications Canada Inc. (201A)		18

		1B		571G		Rogers Communications Canada Inc. (571G)		2

		1B		743B		Rogers Communications Canada Inc. (Cable-743B)		35

		1B		8377		Rogers Communications Canada Inc. (Cable-8377)		29

		1B		8821		Rogers Communications Canada Inc. (Wireless-8821)		681

		1B		497E		Shaw Telecom Inc [Rogers taking] (497E)		18

		1B		548H		TekSavvy Solutions Inc (548H)		2

		1B		8086		TELUS (8086)		185

		1B		2782		TELUS Integrated Communications (2782)		46

		1B		646F		TELUS Mobility (646F)		8

		1B		8301		TELUS Mobility (8301)		104

		1B		8303		TELUS Mobility (8303)		230

		1B		328F		Videotron Ltd. (328F)		14

		1B		8306		Videotron Ltd. (8306)		4

		1B		383F		Videotron Ltd. dba Freedom (383F)		52

		1B		787G		Videotron Ltd. dba Freedom (787G)		122

		1B		8304		Zayo Canada Inc. (8304)		61





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		3		1B		Vancouver		VANCOUVER		BC

		3		1B		Ottawa-Hull		OTTAWA-HULL		ON

		3		1B		Toronto		TORONTO		ON
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Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		2		575G		Beanfield Technologies Inc. (575G)		1

		2		709G		Bell Aliant, a division of Bell Canada (709G)		2

		2		8050		Bell Canada (8050)		152

		2		6574		Bell Mobility (6574)		337

		2		2933		Bell West Inc. (2933)		40

		2		421G		Bragg Communications Inc (421G)		1

		2		4878		Bragg Communications Inc. (4878)		4

		2		221K		Cogeco Connexion Inc. (221K)                      		6

		2		160G		Comwave Networks (160G)		17

		2		081E		Distributel (081E)		39

		2		083E		Distributel (083E)		18

		2		139J		FGLTEL Inc. (139J)		2

		2		464D		Fibernetics Corporation (464D)		49

		2		5643		Fido Solutions Inc. (5643)		72

		2		6996		Globalstar (6996)		4

		2		8506		GT Group Telecom Services Corp. (8506)		8

		2		383H		InnSysVoice Corp (383H)		4

		2		154E		Iristel Inc (154E)		208

		2		346J		Iristel Inc (346J)		8

		2		4727		ISP Telecom Inc. (4727)		28

		2		812H		IXICA Communications Inc. (812H)		31

		2		201A		Primus Telecommunications Canada Inc. (201A)		4

		2		743B		Rogers Communications Canada Inc. (Cable-743B)		9

		2		8377		Rogers Communications Canada Inc. (Cable-8377)		13

		2		8821		Rogers Communications Canada Inc. (Wireless-8821)		237

		2		497E		Shaw Telecom Inc [Rogers taking] (497E)		65

		2		548H		TekSavvy Solutions Inc (548H)		5

		2		247F		Telecommunications Xittel Inc (247F)		4

		2		8084		TELUS (8084)		474

		2		646F		TELUS Mobility (646F)		7

		2		8301		TELUS Mobility (8301)		251

		2		8303		TELUS Mobility (8303)		75

		2		2243		TELUS Quebec (2243)		38

		2		328F		Videotron Ltd. (328F)		46

		2		8306		Videotron Ltd. (8306)		41

		2		383F		Videotron Ltd. dba Freedom (383F)		18

		2		787G		Videotron Ltd. dba Freedom (787G)		37

		2		8304		Zayo Canada Inc. (8304)		35





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		4		2		Banff		BANFF		AB

		4		2		Calgary		CALGARY		AB

		4		2		Edmonton		EDMONTON		AB

		4		2		Fort McMurray		FORT MCMURRAY		AB

		4		2		Fox Creek		FOX CREEK		AB

		4		2		Grande Prairie		GRANDE PRAIRIE		AB

		4		2		High River		HIGH RIVER		AB

		4		2		Lethbridge		LETHBRIDGE		AB

		4		2		Medicine Hat		MEDICINE HAT		AB

		4		2		Peace River		PEACE RIVER		AB

		4		2		Red Deer		RED DEER		AB

		4		2		Alma		ALMA		QC

		4		2		Chicoutimi		CHICOUTIMI		QC

		4		2		Gatineau		GATINEAU		QC

		4		2		Maniwaki		MANIWAKI		QC

		4		2		Ottawa-Hull		OTTAWA-HULL		QC

		4		2		Pointe-Claire		POINTE-CLAIRE		QC

		4		2		Quebec		QUEBEC		QC

		4		2		St-Jerome		SAINT-JEROME		QC

		4		2		Ste-Genevieve		SAINTE-GENEVIEVE		QC

		4		2		Valleyfield		VALLEYFIELD		QC
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Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		3		280H		Access Communications Co-operative Limited (280H)		3

		3		8087		Aliant (Island Tel - 8087)		15

		3		8089		Aliant (MT&T - 8089)		96

		3		8090		Aliant (NB Tel - 8090)		103

		3		8085		Aliant (New Tel - 8085)		36

		3		6574		Bell Mobility (6574)		113

		3		329A		Bell Mobility Aliant (329A)		151

		3		2933		Bell West Inc. (2933)		10

		3		421G		Bragg Communications Inc (421G)		18

		3		4878		Bragg Communications Inc. (4878)		31

		3		160G		Comwave Networks (160G)		12

		3		081E		Distributel (081E)		21

		3		464D		Fibernetics Corporation (464D)		28

		3		5643		Fido Solutions Inc. (5643)		17

		3		8820		Fido Solutions Inc. (8820)		16

		3		8506		GT Group Telecom Services Corp. (8506)		3

		3		630G		Ice Wireless Inc. (630G)		2

		3		154E		Iristel Inc (154E)		173

		3		346J		Iristel Inc (346J)		17

		3		4727		ISP Telecom Inc. (4727)		10

		3		812H		IXICA Communications Inc. (812H)		10

		3		141F		LES.NET (1996) Inc.		4

		3		8088		MTS Inc. (8088)		118

		3		991B		MTS Inc. (991B)		40

		3		8092		Northwestel (8092)		15

		3		201A		Primus Telecommunications Canada Inc. (201A)		1

		3		498E		Provincial Tel Inc (498E)		3

		3		346G		RFNow Inc. (346G)		2

		3		571G		Rogers Communications Canada Inc. (571G)		5

		3		743B		Rogers Communications Canada Inc. (Cable-743B)		18

		3		8821		Rogers Communications Canada Inc. (Wireless-8821)		221

		3		8091		SaskTel (8091)		82

		3		9868		SaskTel Mobility (9868)		66

		3		497E		Shaw Telecom Inc [Rogers taking] (497E)		25

		3		940G		SSi Micro Ltd. (940G)		1

		3		2782		TELUS Integrated Communications (2782)		37

		3		646F		TELUS Mobility (646F)		4

		3		8303		TELUS Mobility (8303)		112

		3		328F		Videotron Ltd. (328F)		1

		3		383F		Videotron Ltd. dba Freedom (383F)		2

		3		8304		Zayo Canada Inc. (8304)		11





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		5		3		Oakbank		OAKBANK		MB

		5		3		Portage La Prairie		PORTAGE LA PRAIRIE		MB

		5		3		Winnipeg		WINNIPEG		MB

		5		3		Bathurst		BATHURST		NB

		5		3		Fredericton		FREDERICTON		NB

		5		3		Miramichi		MIRAMICHI		NB

		5		3		Moncton		MONCTON		NB

		5		3		Saint John		SAINT JOHN		NB

		5		3		St. John's		SAINT JOHNS		NL

		5		3		Amherst		AMHERST		NS

		5		3		Halifax		HALIFAX		NS

		5		3		Sydney		SYDNEY		NS

		5		3		Truro		TRURO		NS

		5		3		Windsor		WINDSOR		NS

		5		3		Yellowknife		YELLOWKNIFE		NT

		5		3		Charlottetown		CHARLOTTETOWN		PE

		5		3		Moose Jaw		MOOSE JAW		SK

		5		3		Regina		REGINA		SK

		5		3		Saskatoon		SASKATOON		SK

		5		3		Whitehorse		WHITEHORSE		YT
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Phase Operators

		PhaseName		OCN		EntityName		CodeCount

		4		843D		9164-3122 Quebec inc (Sogetel) (843D)		4

		4		575G		Beanfield Technologies Inc. (575G)		2

		4		709G		Bell Aliant, a division of Bell Canada (709G)		1

		4		8050		Bell Canada (8050)		371

		4		8051		Bell Canada (8051)		307

		4		984C		Bell Canada (984C)                                		1

		4		6574		Bell Mobility (6574)		504

		4		4878		Bragg Communications Inc. (4878)		5

		4		221K		Cogeco Connexion Inc. (221K)                      		24

		4		160G		Comwave Networks (160G)		22

		4		818D		Cooptel (818D)		7

		4		082E		Distributel (082E)		34

		4		083E		Distributel (083E)		27

		4		3147		ExaTEL Inc. (3147)		2

		4		8226		Execulink Telecom Inc. (8226)		7

		4		139J		FGLTEL Inc. (139J)		1

		4		464D		Fibernetics Corporation (464D)		87

		4		5643		Fido Solutions Inc. (5643)		154

		4		8820		Fido Solutions Inc. (8820)		2

		4		117H		Gosfield North Communication Co-operative (117H)		2

		4		8254		Groupe Maskatel Quebec LP (8254)		6

		4		383H		InnSysVoice Corp (383H)		19

		4		154E		Iristel Inc (154E)		259

		4		346J		Iristel Inc (346J)		4

		4		448K		ISP Telecom Inc. (448K)		1

		4		4727		ISP Telecom Inc. (4727)		30

		4		817D		IVIC Telecom s.e.n.c (817D)		1

		4		812H		IXICA Communications Inc. (812H)		34

		4		2776		Managed Network Systems Inc. (2776)		7

		4		400E		Mornington Communications Co-operative ltd. (400E)		1

		4		995D		Nexicom Telecommunications Inc (995D)		3

		4		201A		Primus Telecommunications Canada Inc. (201A)		15

		4		004G		Quadro Communications Co-operative Inc. (004G)		2

		4		571G		Rogers Communications Canada Inc. (571G)		5

		4		743B		Rogers Communications Canada Inc. (Cable-743B)		29

		4		8377		Rogers Communications Canada Inc. (Cable-8377)		36

		4		8821		Rogers Communications Canada Inc. (Wireless-8821)		443

		4		287H		Roxborough Telephone Company Ltd. (287H)		1

		4		497E		Shaw Telecom Inc [Rogers taking] (497E)		2

		4		548H		TekSavvy Solutions Inc (548H)		10

		4		247F		Telecommunications Xittel Inc (247F)		4

		4		8257		Telephone Drummond Inc (8257)		1

		4		2782		TELUS Integrated Communications (2782)		69

		4		646F		TELUS Mobility (646F)		10

		4		8303		TELUS Mobility (8303)		310

		4		2243		TELUS Quebec (2243)		46

		4		8094		Thunder Bay Telephone (8094)		23

		4		328F		Videotron Ltd. (328F)		124

		4		8306		Videotron Ltd. (8306)		66

		4		383F		Videotron Ltd. dba Freedom (383F)		24

		4		787G		Videotron Ltd. dba Freedom (787G)		18

		4		920D		Westport Telephone Company Limited (920D)		1

		4		138D		Wightman Communications Ltd (138D)		1

		4		8304		Zayo Canada Inc. (8304)		28





Phase Exchanges

		PhaseOrder		PhaseName		ExchangeName_CNAS		RCName_BIRRDS_long		Province_CanadaPost

		6		4		Belleville		BELLEVILLE		ON

		6		4		Brantford		BRANTFORD		ON

		6		4		Burlington		BURLINGTON		ON

		6		4		Chatham		CHATHAM		ON

		6		4		Cornwall		CORNWALL		ON

		6		4		Essex		ESSEX		ON

		6		4		Guelph		GUELPH		ON

		6		4		Hamilton		HAMILTON		ON

		6		4		Kingston		KINGSTON		ON

		6		4		Kitchener-Waterloo		KITCHENER-WATERLOO		ON

		6		4		Leamington		LEAMINGTON		ON

		6		4		Lindsay		LINDSAY		ON

		6		4		Listowel		LISTOWEL		ON

		6		4		London		LONDON		ON

		6		4		Peterborough		PETERBOROUGH		ON

		6		4		Sarnia		SARNIA		ON

		6		4		Thunder Bay		THUNDER BAY		ON

		6		4		Windsor		WINDSOR		ON

		6		4		Woodstock		WOODSTOCK		ON

		6		4		Drummondville		DRUMMONDVILLE		QC

		6		4		Granby		GRANBY		QC

		6		4		Joliette		JOLIETTE		QC

		6		4		Montreal		MONTREAL		QC

		6		4		Sherbrooke		SHERBROOKE		QC

		6		4		Sorel		SOREL		QC

		6		4		St-Hyacinthe		SAINT-HYACINTHE		QC

		6		4		Trois-Rivieres		TROIS-RIVIERES		QC

		6		4		Victoriaville		VICTORIAVILLE		QC






